## Commercial Construction
START | END | PROJECT CONCEPT | Choose Design Team
2020-08-01 | 2020-08-20 |  | Select Project Site
20 Days |  |  | Discuss and Select Construction Service
Identify Project Parameters / Feasibility
START | END | PLANNING AND DESIGN DEVELOPMENT | Identify Required Functionality & Aesthetics
2020-09-01 | 2020-10-31 |  | Complete Schematic Design
61 Days |  |  | Prepare Preliminary Estimate
Establish Preliminary Schedule
Complete Site Plan Approval Process
Perform Value Engineering
Secure financing
Finalize Construction Documents
Establish Final Project Budget
START | END | BIDDING AND AWARD | Identify Subcontractor List for Bidding
2020-11-01 | 2020-11-30 |  | Solicit Subcontractor Bids
30 Days |  |  | Award Subcontracts
START | END | MOBILIZATION | Obtain necessary Permits and Insurance
2020-12-01 | 2020-12-23 |  | Finalize Project Schedule
23 Days |  |  | Coordinate Project Start-up items
START | END | ACTIVE CONSTRUCTION AT JOB SITE | Construction Activity 1
2021-02-01 | 2021-08-01 |  | Construction Activity 2
182 Days |  |  | Construction Activity 3
Construction Activity 4
Construction Activity 5
Construction Activity 6
Construction Activity 7
Field Supervision / Quality Control
Manage Subcontractors
Manage Change Orders
Coordinate Local/County/State Inspections
Track Costs (budget vs. actual)
START | END | PROJECT CLOSEOUT | Substantial Completion
2021-08-10 | 2021-09-08 |  | Final Inspections
30 Days |  |  | Certificate of Occupancy
Punch List
Closeout Documentation
START | END | OCCUPANCY | Final Billing
2021-09-10 | 2021-09-15 |  | Final Walkthrough with Owner
6 Days |  |  | Final Clean up
COMMERCIAL CONSTRUCTION
Schedule Template

## ©
© TemplateLab.com