|  |  |  |
| --- | --- | --- |
| See the source image |  | **HOTEL CONSTRUCTION SCHEDULE TEMPLATE** |
|  | One Corporate Building |  | 07/25/2020 |
|  | CLIENT NAME |  | DATE |
|  | 4236 Bottom Lane, Findley Lake, New York 14736 |  | 10 |
|  | LOCATION |  | PAGE NO. |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task ID | Task Description | Start Date | End Date | % Completed | 2020 |
| 20-Jul | 21-Jul | 22-Jul | 23-Jul | 24-Jul | 25-Jul | 26-Jul | 27-Jul | 28-Jul | 29-Jul | 30-Jul | 31-Jul | 1-Aug | 2-Aug | 3-Aug |
| 56 |  Blow-In insulation | 07/05/2020 | 07/06/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57 |  Drywall nailing inspection | 07/07/2020 | 07/07/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 58 |  Order finish package | 07/07/2020 | 07/07/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 59 |  Tape and texture drywall | 07/07/2020 | 07/14/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 60 |  Deliver finish package | 07/14/2020 | 07/14/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 61 |  Finish carpentry | 07/15/2020 | 07/20/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 62 |  Painting | 07/20/2020 | 07/25/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 63 | Phase 4 Exterior Finish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 64 |  Install house wrap | 06/21/2020 | 05/22/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 65 |  Roofing | 06/22/2020 | 06/27/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 66 |  Masonry | 06/22/2020 | 06/29/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 67 |  Siding / Stucco | 06/29/2020 | 07/05/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 68 |  Concrete prefinal grade | 07/05/2020 | 06/30/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 69 |  Soffit & fascia | 07/05/2020 | 07/07/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 70 |  Pour driveway and walk | 07/06/2020 | 07/08/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 71 |  Foundation purging | 07/08/2020 | 07/11/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 72 |  Exterior painting | 07/11/2020 | 07/12/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 73 |  Landscaping | 07/12/2020 | 07/19/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 74 | Phase 5 Interior Finish |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 75 |  Order appliances | 07/25/2020 | 07/25/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 76 |  Tub & shower wall finish | 07/25/2020 | 07/28/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 77 |  Install resilient/hard floors | 07/28/2020 | 08/02/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 78 |  Install cabinets & countertops | 08/02/2020 | 08/03/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 79 |  Deliver appliances | 08/02/2020 | 08/02/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 80 |  Carpentry pick-up | 08/03/2020 | 08/04/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 81 |  Install appliances | 08/03/2020 | 08/04/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 82 |  Finish electrical | 08/03/2020 | 08/04/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 83 |  Test appliances | 08/05.2020 | 08/05.2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |