|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| See the source image |  | **HOTEL CONSTRUCTION SCHEDULE TEMPLATE** | | |
|  | One Corporate Building |  | 07/25/2020 |
|  | CLIENT NAME |  | DATE |
|  | 4236 Bottom Lane, Findley Lake, New York 14736 |  | 10 |
|  | LOCATION |  | PAGE NO. |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task ID | Task Description | Start Date | End Date | % Completed | 2020 | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 20-Jul | | 21-Jul | | 22-Jul | | 23-Jul | | 24-Jul | | 25-Jul | | 26-Jul | | 27-Jul | | 28-Jul | | 29-Jul | | 30-Jul | | 31-Jul | | 1-Aug | | 2-Aug | 3-Aug |
| 56 | Blow-In insulation | 07/05/2020 | 07/06/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 57 | Drywall nailing inspection | 07/07/2020 | 07/07/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 58 | Order finish package | 07/07/2020 | 07/07/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 59 | Tape and texture drywall | 07/07/2020 | 07/14/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 60 | Deliver finish package | 07/14/2020 | 07/14/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 61 | Finish carpentry | 07/15/2020 | 07/20/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 62 | Painting | 07/20/2020 | 07/25/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 63 | Phase 4 Exterior Finish |  |  |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 64 | Install house wrap | 06/21/2020 | 05/22/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 65 | Roofing | 06/22/2020 | 06/27/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 66 | Masonry | 06/22/2020 | 06/29/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 67 | Siding / Stucco | 06/29/2020 | 07/05/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 68 | Concrete prefinal grade | 07/05/2020 | 06/30/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 69 | Soffit & fascia | 07/05/2020 | 07/07/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 70 | Pour driveway and walk | 07/06/2020 | 07/08/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 71 | Foundation purging | 07/08/2020 | 07/11/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 72 | Exterior painting | 07/11/2020 | 07/12/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 73 | Landscaping | 07/12/2020 | 07/19/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 74 | Phase 5 Interior Finish |  |  |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 75 | Order appliances | 07/25/2020 | 07/25/2020 | 100% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 76 | Tub & shower wall finish | 07/25/2020 | 07/28/2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 77 | Install resilient/hard floors | 07/28/2020 | 08/02/2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 78 | Install cabinets & countertops | 08/02/2020 | 08/03/2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 79 | Deliver appliances | 08/02/2020 | 08/02/2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 80 | Carpentry pick-up | 08/03/2020 | 08/04/2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 81 | Install appliances | 08/03/2020 | 08/04/2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 82 | Finish electrical | 08/03/2020 | 08/04/2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |
| 83 | Test appliances | 08/05.2020 | 08/05.2020 | 0% | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  | |  |  |  |