## Residential Construction Sch.
RESIDENTIAL CONSTRUCTION
Schedule Template
Project Name: Anderson Single-family Dwelling
Company Name: Residential Construction PLT
| Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
| 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021
Plans and Permitting
Develop a set of plans with an architect
Plans sealing and energy form filling
Building Permit application
The Site Work and Masonry
Clear & level the land
Footings & stem wall
Lorem Ipsum
Framing
Roof trusses installation
Roof drying with tar paper
All interior framing
Plumbing, Electric & More
Electrical & HVAC
Plumbing
Wiring for telephones, electronics and security systems
Insulation, Drywall & Flooring
Fiberglass, foam or blanket insulation
Drywall
Cabinets, flooring, bathroom finishes
Landscaping & Exterior Aspects
Driveways, walkways, pools
Final inspection
Certificate of Occupancy
v

## ©
© TemplateLab.com