## Building projects
Construction Schedule Template
Contractor Name:
PROJECT TITLE AND REF NUMBER.
Program Prepared by:
|  | START | FINISH
REF | TRADE | DATE | DATE | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
1 | SITE PREPARATION
2 | DEMOLITION
3 | CONCRETE WORKS
4 | STRUCTURAL STEEL
5 | LIGHT STEEL FRAMING
6 | TIMBER CONSTRUCTION
7 | BLOCK CONSTRUCTION
8 | ROOFING
9 | DOORS AND WINDOWS
10 | CLADDING AND LININGS
11 | SUSPENDED CEILINGS
12 | PLASTERING
13 | JOINERY AND FIXTURES
14 | FINISHES
15 | PAINTING
16 | PLUMBING AND DRAINAGE
17 | ELECTRICAL INSTALLATIONS
18 | MECHANICAL INSTALLATIONS
19 | EXTERNAL WORKS
20 | FINAL CLEAN
Initial Issue Date:
| Amendments: |  |  |  | Guide Notes:
| 1. |  |  | 1 | Appropriately shade-in or cross-out each cell for the duration of the task ensuring that it corresponds
| 2. |  |  |  | with the start and finish dates.
| 3. |  |  | 2 | This is a sample construction programme and should only be used as a template, allow to modify as
| 4. |  |  |  | required to suit individual project requirements.
5.

## Civil Projects
Contractor Name:
PROJECT TITLE AND REF NUMBER.
Program Prepared by:
|  | START | FINISH
REF | TRADE | DATE | DATE | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
1 | ESTABLISHMENT AND REHABILITATION
2 | PROVISION FOR TRAFFIC
3 | CLEARING & GRUBBING
4 | EARTHWORKS
5 | PAVEMENTS
6 | STABILISATION
7 | SPRAY SEALING & ASPHALT
8 | CONCRETE WORKS
9 | DRAINAGE WORKS
10 | PROTECTION WORKS
11 | ROAD FURNITURE
12 | WATER SERVICES
13 | SEWER SERVICES
14 | ELECTRICAL SERVICES
15 | THRUST BORING
16 | LANDSCAPING
17 | DEMOBILISATION
Initial Issue Date:
| Amendments: |  |  |  | Guide Notes:
| 1. |  |  | 1 | Appropriately shade-in or cross out each cell for the duration of the task ensuring that it corresponds
| 2. |  |  |  | with the start and finish dates.
| 3. |  |  | 2 | This is a sample construction programme and should only be used as a template, allow to modify as
| 4. |  |  |  | required to suit individual project requirements.
5.