|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Invite your contractor and/or your designer into your home to discuss all of your hopes and requirements for your kitchen renovation. This will help confirm your space is planned in a way that will ensure convenience and ease of movement for you and your family. Remember to stick to your plan, and don't get caught up in the excitement or let yourself get talked into things you don't want or need. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | | | | | | |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | | | | | | |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | **Tear Out and Demolition** | | | | | | | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | Demolish and get rid of what’s outdated or worn out. Rip out anything you don’t want to keep including walls, cabinetry, flooring, fixtures, or more. Decision is to hire a licensed contractor to complete the work. Experienced teams possess the knowledge to avoid plumbing and pipes hidden behind walls or beneath cabinets. | | | | | | |  | Budget | |  |  |  |
|  |  |  |  | **$1,500.00** | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Start Date | End Date |  |  |  |
|  |  |  |  |  |  | 01/06/2020 | 05/06/2020 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | **Rough-In Work (Framing and Plumbing)** | | | | | | | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | Rough-in work including any framing and plumbing. Moving plumbing fixtures away from where they originally sat. Adding square footage to the space by pouring new concrete for an expansion. Decision is to leave this work to a professional construction crew. | | | | | | |  | Budget | |  |  |  |
|  |  |  |  | **$2,500.00** | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Start Date | End Date |  |  |  |
|  |  |  |  |  |  | 08/06/2020 | 12/06/2020 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | **Finishing Walls, Doors & Windows** | | | | | | | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | Hang, tape, and finish drywall according to the project plan. Add a coat of primer to the drywall.  Install doors or windows. Insulate them properly. Install trims to make cabinet installation more exact. I will do these activities with my own hands. | | | | | | |  | Budget | |  |  |  |
|  |  |  |  | **$1,500.00** | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Start Date | End Date |  |  |  |
|  |  |  |  |  |  | 15/06/2020 | 18/06/2020 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | **Cabinets and Plumbing Fixtures** | | | | | | | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | Installation of cabinets and plumbing fixtures. , followed by installation of new countertops. Add sink, faucet, and garbage disposal. With a little effort and the help of friends, this is a job I am willing to do on my own. | | | | | | |  | Budget | |  |  |  |
|  |  |  |  | **$2,500.00** | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Start Date | End Date |  |  |  |
|  |  |  |  |  |  | 19/06/2020 | 20/06/2020 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | **Bring in New Appliances** | | | | | | | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | Add the built-in microwave, stove, refrigerator, wine chiller, and water filtration system. If will attempt the process myself. | | | | | | |  | Budget | |  |  |  |
|  |  |  |  | **$6,500.00** | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Start Date | End Date |  |  |  |
|  |  |  |  |  |  | 22/06/2020 | 23/06/2020 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | **Install New Flooring** | | | | | | | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | | Install ceramic tiles. Black & white. Decision is to leave this work to a professional. | | | | | | |  | Budget | |  |  |  |
|  |  |  |  | **$1,500.00** | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Start Date | End Date |  |  |  |
|  |  |  |  |  |  | 24/06/2020 | 25/06/2020 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TOTAL Budget: | | | $16,000.00 | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | [© TemplateLab.com](http://templatelab.com/) | | | | |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |