## Task_Table1
ID | Task Name | Responsibility | Duration ( Days) | Start_Date | Finish_Date | Scheduled_Work (Total Hours) | Percentage Complete
1 | Office Move Planning
1.1 | Complete Move Request Form | Agency
1.2 | Submit Move Request Form | Agency
1.3 | Move Authorization (GR: Real Estate, WVOT PMO for Independent Moves) | Real Estate Division
1.4 | Identify Move Project Team | All
1.5 | Prepare and publish contact list | All
1.6 | Make list of key needs that must be met by new office space | Real Estate Division
1.7 | Identify potential office sites | Real Estate Division
1.8 | Make final decision on office space | Real Estate Division
1.9 | Identify major tenant improvement needs | Real Estate Division
1.10 | Acquire Property (purchase lease existing) | Real Estate Division
1.11 | Space Planning with the assistance from A&E | Real Estate Division
1.12 | Review space plans and jack locations for all equipment with Desktop Support Staff | All
1.13 | Finalize Space Plan | Real Estate Division
1.14 | Construction Drawings | Real Estate Division
1.15 | Finalize lease on office space | Real Estate Division
1.16 | Begin Procurement | Real Estate Division
1.16.1 | Obtain General Contractor | Real Estate Division
1.16.1.1 | Put out for bid for General Contractor | Real Estate Division
1.16.1.2 | Advertise for the General Contractor | Real Estate Division
1.16.1.3 | Pre Bid Conf - onsite with walk through | Real Estate Division
1.16.1.4 | Question and Answer | Real Estate Division
1.16.1.5 | Bid Submission | Real Estate Division
1.16.1.6 | Bid Review | Real Estate Division
1.16.1.7 | Bid Recommendation | Real Estate Division
1.16.1.8 | Purchasing Approval | Real Estate Division
1.16.1.9 | Bid Award | Real Estate Division
1.16.2 | New Construction | Real Estate Division
1.16.2.1 | New Contruction Turn Dirt | Real Estate Division
1.16.2.2 | New Construction Contruct Building | Real Estate Division
1.16.2.3 | Weekly Construction Meetings | Real Estate Division
1.16.2.4 | Certificate of Occupancy | Real Estate Division
1.16.3 | Carperting and Flooring | Real Estate Division
1.16.3.1 | Put out for bid | Real Estate Division
1.16.3.2 | Advertise | Real Estate Division
1.16.3.3 | Pre Bid Conf - onsite with walk through | Real Estate Division
1.16.3.4 | Question and Answer | Real Estate Division
1.16.3.5 | Bid Submission | Real Estate Division
1.16.3.6 | Bid Review | Real Estate Division
1.16.3.7 | Bid Recommendation | Real Estate Division
1.16.3.8 | Purchasing Approval | Real Estate Division
1.16.3.9 | Bid Award | Real Estate Division
1.16.4 | Moving Contractor | Real Estate Division
1.16.4.1 | Determine Agency Moving Needs | Real Estate Division
1.16.4.2 | Put out for bid | Real Estate Division
1.16.4.3 | Advertise | Real Estate Division
1.16.4.4 | Pre Bid Conf - onsite with walk through | Real Estate Division
1.16.4.5 | Question and Answer | Real Estate Division
1.16.4.6 | Bid Submission | Real Estate Division
1.16.4.7 | Bid Review | Real Estate Division
1.16.4.8 | Bid Recommendation | Real Estate Division
1.16.4.9 | Purchasing Approval | Real Estate Division
1.16.4.10 | Bid Award | Real Estate Division
1.16.4.11 | Building Inspection | Real Estate Division
1.17 | HVAC Installation and/or Maintenance | Real Estate Division
1.18 | Obtain estimates from contractors for major tenant improvements | Real Estate Division
1.19 | Identify costs for new office (chairs, desks, equipment) | Real Estate Division
1.20 | Prepare a budget for the move | Real Estate Division
1.21 | Select the move day | Real Estate Division
1.22 | Hire contractors for major tenant improvements | Real Estate Division
1.23 | Obtain necessary permits | Real Estate Division
1.24 | Communicate to employees | Real Estate Division
1.25 | Design office space | Real Estate Division
1.26 | Assign office space | Real Estate Division
1.27 | Order chairs | Real Estate Division
1.28 | Order desks | Real Estate Division
1.29 | Order systems furniture | Real Estate Division
1.30 | Order new office equipment | Real Estate Division
1.31 | Obtain estimates from moving companies | Real Estate Division
1.32 | Hire movers | Real Estate Division
1.33 | Install Outlet | Real Estate Division
1.34 | Customer Technology Needs Assessment | WVOT
1.34.1 | Review server/networking needs and initiate planning and design for new site | WVOT
1.34.2 | Evaluate phone system needs | WVOT
1.34.3 | Review telephone needs with the customer. | WVOT
1.34.4 | Review Security System (card access) | WVOT
1.34.5 | Assess Existing Structual Needs | WVOT
1.34.6 | Assess Electrical Needs | WVOT
1.34.7 | Review Wireless needs | WVOT
1.34.8 | Evaluate Server room needs | WVOT
1.35 | Secure Archictect and Engineering Services | WVOT
1.36 | Environment Services | WVOT
1.37 | Obtain initial floorplan | WVOT
1.38 | Data circurit Assessment | WVOT
1.39 | Cabling Assessment | WVOT
1.4 | Floor Plan Assessment
1.40.1 | Server location | WVOT
1.40.2 | Cabling rack locations | WVOT
1.40.3 | Server and Wiring Closet | WVOT
1.40.4 | PC Locations | Agency
1.40.5 | Printer Locations | Agency
1.40.6 | Fax Locations | Agency
1.40.7 | Telephone Locations | Agency
1.40.8 | Numbe / Location of Phone Jacks | Agency
1.40.9 | Number / Location Network Jacks | Agency
1.41 | Building Assessment
1.41.1 | Obtain insurance underwriting | Real Estate Division
1.41.2 | ADA Compliance Check | Real Estate Division
1.41.3 | Fire alarm Configuration | Real Estate Division
1.41.4 | Fire Marshal Certification | Real Estate Division
1.41.5 | Elevator Inspection/Maintenance | Real Estate Division
1.41.6 | Order change of address labels for notification | Agency
1.41.7 | Order new address labels for notification | Agency
1.41.8 | Obtain estimates from signage companies | Agency
1.41.9 | Order signage for new location | Agency
1.42 | Arrange internal maintenance service | Agency
1.43 | Arrange external maintenance service | Agency
1.44 | Arrange for trash disposal | Agency
1.45 | Arrange for cleaning service | Agency
1.46 | Arrange for recycling | Agency
1.47 | Appraise assets being transferred to new location | Agency
1.48 | Obtain business insurance quotes for new space | Agency
1.49 | Purchase insurance for new space | Agency
1.5 | Order security system | Agency
1.51 | Determine Security Needs (Access Cards) | Agency
1.52 | Order keys, access cards | Agency
1.53 | Arrange for beverage service | Agency
1.54 | Send change-of-address notices to all vendors | Agency
1.55 | Send change-of-address notices to all customers | Agency
1.56 | Send change-of-address notices to all subscriptions | Agency
1.57 | Notify all leasers of equipment move | Agency
1.58 | Order checks with new address | Agency
1.59 | Order long-distance service | Agency
1.6 | Transfer toll-free numbers or order new numbers | Agency
1.61 | Plan for disposal of old office equipment | Agency
1.62 | Dispose of old office equipment | Agency
1.63 | Plan for disposal of old office furniture | Agency
1.64 | Dispose of old office furniture | Agency
1.65 | Order new letterhead and envelopes | Agency
1.66 | Order new business cards | Agency
1.67 | Order new business forms | Agency
1.68 | Schedule disconnection of utilities | Agency
1.69 | Repair new office | Agency
1.7 | Clean new office | Agency
1.71 | Identify closest overnight drop off boxes | Agency
1.72 | Inventory existing office furniture (general) | Agency
1.73 | Inventory existing computers | Agency
1.74 | Inventory existing furniture by office | Agency
1.75 | Shred documents | Agency
1.76 | Purge old, obsolete materials | Agency
1.77 | Create new office extension directory | Agency
1.78 | Create new office layout map and travel instructions | Agency
1.79 | Create new fax cover sheet | Agency
1.8 | Create driving instructions to new location for employees | Agency
1.81 | Obtain public transportation information for new location | Agency
1.82 | Get shipping labels | Agency
1.83 | Notify post office of change of address | Agency
1.84 | Update company website with new information | Agency
1.85 | Order moving boxes | Agency
1.86 | Pack up desks, personal spaces | Agency
1.87 | Pack up common areas | Agency
1.88 | Label all fragile items | Agency
1.89 | Take down systems furniture | Agency
1.9 | Store property that will not be moved | Agency
1.91 | Label items to be moved | Agency
1.92 | Move to central location | Agency
1.93 | Install systems furniture at new location | Agency
1.94 | Distribute new keys, cards | Agency
1.95 | Collect old keys, cards; distribute new keys, cards | Agency
1.96 | Empty, defrost and clean refrigerator | Agency
1.97 | Code new office space on a map for movers | Agency
1.98 | Create a moving day team to provide direction to movers | Agency
1.99 | Evaluate computer networking needs | WVOT
1.1 | Order phone system | WVOT
1.101 | Order phone lines - TCR - Voice | WVOT
1.102 | Order phone lines - TCR -Data | WVOT
1.103 | Install network wiring at new location | WVOT
1.104 | Install Cabling | WVOT
1.105 | Install Circuit | WVOT
1.106 | Install phone lines | WVOT
1.107 | Install phone system | WVOT
1.108 | Assign new phone numbers, extensions | WVOT
1.109 | Title Search | Real Estate Division
1.11 | Finance Plan | Real Estate Division
1.111 | Lease Bonds | Real Estate Division
1.112 | Supply WVOT with list of people and phone #s | Real Estate Division
2 | Office Move Executing | Agency
2.1 | Client Move Preparation | Agency
2.1.1 | Obtain moving supplies | Agency
2.1.2 | Confirm Delivery of supplies | Agency
2.1.3 | Ensure PCs are labelled | Agency
2.1.4 | Label Box/ bag with employee cube contents | Agency
2.1.5 | Label cubes with unique identification and worker's name. | Agency
2.1.6 | Finalize start date and time of move | Agency
2.2 | OT Move Preparation
2.2.1 | Install Security System | Agency
2.2.2 | Enter Heat ticket for Address Change | Agency
2.2.3 | Inventory existing equipment and hardware before the move | Agency
2.2.4 | Post a set of floor plans next to the patch panels | Agency
2.2.5 | Post a set of floor plans near the entry | Agency
2.2.6 | Label Printers with current IP, network ID, and division name. | WVOT
2.2.7 | Label the router, dial-up modem, switches, server, monitor of server, etc. before move | WVOT
2.2.8 | Prepare a detailed contact list for move purposes, and distribute /publish ## weeks prior to move | Agency
2.2.8.1 | Ensure that the local staff contact will be onsite when needed | WVOT
2.2.8.2 | Ensure that WVOT Networking staff contact will be available | WVOT
2.3 | Move the Customer/Agency | Agency
2.3.1 | Determine Move vs. Surplus of equipment | Agency
2.3.2 | Move Furniture | Agency
2.3.3 | Install Furniture | Agency
2.3.4 | Customer Pack | Agency
2.3.5 | Post coded signs in new office for movers | Agency
2.3.6 | Put moving day team in place | Agency
2.3.7 | Protect main moving paths | Agency
2.3.8 | Move plants and fine art in separate moving van | Agency
2.3.9 | Physical Move Complete
2.3.9.1 | Tear down of Network Equipment and server | WVOT
2.3.9.2 | Unhook all equipment from the network ports and also PCs, Network printers, monitors, etc before movers start moving any computer equipment. | WVOT
2.3.9.3 | Perform a walk around to collect any leftover surge protectors, power cords, and verify all technology related equipment has been collected | Agency
2.3.9.4 | Start moving computer equipment | Agency
2.3.9.5 | Begin transport of server and network related items to new office location | Agency
2.3.9.6 | Setup equipment at new location | WVOT
2.3.9.7 | Record CAT jack # and activate port | WVOT
2.3.9.8 | Verify all technology equipment is working (each PC, connection, printers, etc) | WVOT
2.3.9.9 | Verify if network connection is functioning | WVOT
2.3.10 | If needed, contact WVOT Service Desk for Networking assistance | WVOT
2.4 | Follow up Visit with customer | WVOT
2.5 | Post-Move
2.5.1 | Check carefully for any damaged or missing items | Agency
2.5.2 | Schedule phone training | WVOT
2.5.3 | Schedule security training | Agency
2.5.4 | Schedule fire drill | Agency
2.5.5 | Periodically visit old office to pick up mail | Agency
2.5.6 | Schedule open house for clients | Agency
2.5.7 | Office move project complete | Agency
3 | Move Close Out
3.1 | Obtain Agency Sign Off | WVOT or Real Estate Division