## Project Gantt Chart Template
PROJECT: TEMPLATELAB PROTOTYPE DESIGN
Project Manager: Owen Armstrong
ACTIVITY PLAN
| WEEK > |  |  |  |  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5
# | Activity |  |  | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
20 | PROJECT MANAGEMENT | 2020-06-01 | 2020-07-03 | 1 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
40 | PROTOTYPE DESIGN | 2020-06-01 | 2020-06-11 | 1 | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
41 | Review conceptual design | 2020-06-01 | 2020-06-05 | 1 | 5 | 1 | 1 | 1 | 1 | 1
42 | Check compliance of all parts and their availability | 2020-06-08 | 2020-06-10 | 8 | 10 | [7 empty] | 1 | 1 | 1
43 | Final Design Approval | 2020-06-11 | 2020-06-11 | 11 | 11 | [10 empty] | 1
60 | PRODUCTION DOCUMENTATION | 2020-06-12 | 2020-06-22 | 12 | 22 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
61 | Electrical drawings | 2020-06-12 | 2020-06-19 | 12 | 19 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
62 | Mechanical drawings & workshop drawings | 2020-06-12 | 2020-06-19 | 12 | 19 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
63 | BOM definition and Requisition list generation | 2020-06-22 | 2020-06-22 | 22 | 22 | [21 empty] | 1
80 | PROCUREMENT | 2020-06-23 | 2020-07-02 | 23 | 32 | [22 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
100 | SOFTWARE DEVELOPMENT | 2020-06-23 | 2020-07-03 | 23 | 33 | [22 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
101 | C++ Coding | 2020-06-23 | 2020-07-01 | 23 | 31 | [22 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
102 | Vision system setup | 2020-06-23 | 2020-07-03 | 23 | 33 | [22 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
|  | Total (hrs) | MANPOWER |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
|  | 47 | Project Manager |  |  | 1 | 1 | 1 | 1 | 4 |  |  | 1 | 1 | 1 | 1 | 4 |  |  | 1 | 1 | 1 | 1 | 4 |  |  | 1 | 2 | 2 | 2 | 4 |  |  | 2 | 2 | 2 | 2 | 4
|  | 64 | Mechanical Constructor |  |  | 1 1: 8; 2 2: 8; 3 3: 8; 4 4: 8; 5 5: 8; 9 9: 8; 10 10: 8; 11 11: 8
|  | 80 | Mechanical Engineer |  |  | 8 8: 8; 9 9: 8; 10 10: 8; 12 12: 8; 15 15: 8; 16 16: 8; 17 17: 8; 18 18: 8; 19 19: 8; 22 22: 8
|  | 144 | Automation Engineer 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 |  | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
|  | 23 | Procurement Officer |  |  | 23 23: 8; 24 24: 8; 25 25: 1; 26 26: 1; 29 29: 1; 30 30: 1; 31 31: 1; 32 32: 1; 33 33: 1
|  | 0 | Quality Manager

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "D" and "E" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change LOGO image, right click on it and choose CHANGE PICTURE.

## ©
© TemplateLab.com