|  |
| --- |
| **SIMPLE GANTT CHART TEMPLATE** |
| **Customer Management System (Training Schedule)** |  | **3/5/2019** |  | **1/28/2021** |  | **11/1/2020** |
| PROJECT NAME |  | START DATE |  | END DATE |  | LAST UPDATE DATE |
| TaskID | Task Name | Start Date | End Date | % Completed | 8/22/2020 | 8/29/2020 | 9/5/2020 | 9/12/2020 | 9/19/2020 | 9/26/2020 | 10/3/2020 | 10/10/2020 | 10/17/2020 | 10/24/2020 | 10/31/2020 | 11/7/2020 | 11/14/2020 | 11/21/2020 | 11/28/2020 | 12/5/2020 | 12/12/2020 | 12/19/2020 | 12/26/2020 | 1/2/2021 | 1/9/2021 | 1/16/2021 | 1/23/2021 | 1/30/2021 | 2/6/2021 |
| 11 | Training | 10/24/2020 | 12/12/2020 | 25% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11a | Training Facilities | 10/24/2020 | 12/12/2020 | 25% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11b | Training Material | 10/1/2020 | 10/31/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11c | Identify Trainers | 8/29/2020 | 9/12/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11d | Prepare Trainers | 9/19/2020 | 10/17/2020 | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11e |  Training Schedule | 9/19/2020 | 11/21/2020 | 70% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11f | Identify Participants | 9/26/2020 | 11/28/2020 | 60% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11g | Send Invitations | 10/18/2020 | 12/5/2020 | 20% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11h | Confirm Attendance | 10/26/2020 | 12/12/2020 | 10% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11i | Distribute Materials | 11/7/2020 | 12/19/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11j | Training Sessions | 11/14/2020 | 12/26/2020 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11k | Training Certificate | 11/21/2020 | 1/2/2021 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11l | Evaluate Trainings | 11/28/2020 | 01/09/2021 | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **Remarks:** |  | **Approved By** |
| Training facilities shall be provided by the client.List of participants will be coursed to the client Training Coordinator.Meals and snacks are to be provided by the client. |  |  |  | Mm/dd/yyyy |
|  | PROJECT MANAGER |  | DATE |