| SCOPE OF WORK TEMPLATE Organization Name: |  |
| --- | --- |
| Project Title: | Linkage Lab |
| GOAL STATEMENT: | Develop contractual relationships with the health plans from the eight duals counties. |

| Objective 1: Participate in organizational capacity building, including executive leadership and management development as well as organizational readiness preparation through participation in 4 seminars (up to 10 days total) |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Finalize senior management team selection: Required: Executive Director or Chief Executive Officer Chief Financial Officer/Director of Finance Chief Operating Officer/ Director of Programs Plus staff in charge of: Outreach Marketing Operations Point of Contact for project team – must be one of the project team members. | January 1, 2015 | Completed contact sheet including names, titles, phone numbers and email addresses. |
| Status: |
| 1.2 Attend 3 – day kick-off seminar in Southern California | January 14 – 16, 2015 | Team member attendance Assessment of organizational capabilities Development of strategic plan to offer Long-Term Service and Supports on a contractual basis with health care partner |
| Status: |
| 1.3 Attend three additional 2 - 3day seminars in locations to be determined | June 2015 December 2015 May 2016 | Team member attendance Work Assignment from previous seminar has been completed and turned in Organizational capacities are improved and the organization is prepared to enter into a contractual partnership with a health care provider |
| Status: |

| Objective 2: Select 1 member for participation in Advisory Board |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 2.1 Attend twelve, 1-hour Advisory Board calls. | Feb 2014 March 2014 April 2014 May 2014 July 2014 August 2014 September 2014 October 2014 November 2014 January 2016 February 2016 March 2016 April 2016 June 2016 | Team member attendance Reports on progress towards assigned tasks Preparation for upcoming seminars |
| Status: |

| Objective 3: Participate in Learning Collaborative through use of web based platform |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 3.1 Provide monthly updates on activities and progress via web based platform | January 2015 – June 2016 | Monthly Reports |
| Status: |

| Objective 4: Participate in technical assistance activities with identified consultants. |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Host two in-person technical assistance meetings for your organization ranging from 3-5 hours | February 2015 August 2015 | Agenda Technical assistance summary Team member attendance |
| Status: |
| 4.2 Participate in monthly technical assistance support calls | January 2015 – June 2016 | Agenda Technical assistance summary Team member attendance |
| Status: |

| Objective 5: Complete a Root Cause Analysis (RCA) to determine what causes high costs and low quality care for the target population |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Consumer interviews, potential partner discussions, chart reviews, review of QIO data (if applicable), etc. Hone in on Target Population Identification of needs of the target population Identification of potential health care partner’s needs Understanding of what the new models/ interventions are needed to address the issues revealed in the RCA |  | Final Report |
| Status: |
| Conduct an external scan of the market to understand existing health care and community-based services, resources, under-utilized assets, gaps in service areas, potential areas of duplication, etc. Understanding of existing services and gaps Identification of potentially needed CBO partnerships |  | Final Report |
| Status: |

| Objective 6: Identify Potential Partnership with the Health Care Sector (represent new business opportunity) |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 6.1 Identify potential partners (health care and managed care providers) |  | List of identification of potential partnerships |
| Status: |
| Facilitate an assessment of your organization’s core offerings / gaps, consider what the potential partners might need from your organization, and create a framework for strategic-oriented partnership discussions |  | Final strategy and plan for ongoing partnership development |
| Status: |
| Determine messaging around core offerings and strategies for new service development |  | Initial concept paper / executive summary that can be shared with potential partners |
| Status: |
| Schedule and host meetings; determine follow up and ongoing communication plan with potential partner |  | Dates, agendas and summaries of partner meetings and an ongoing plan for fostering the relationships |
| Status: |

| Objective 7: Determine if other CBO Partnerships are needed for Model Design and Service Delivery |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Determine organizational gaps and identify the services for what type of collaborative relationships may be needed other CBOs |  | Final report of Organizational Assessment and an understanding of the services offered by potential CBO partners |
| Status: |
| 7.2 Identify CBO partners if needed |  | List of identified CBO partners |
| Status: |
| Host meetings with potential CBO partners, determine collaborative structure for multi-organization involvement, and a plan for ongoing meetings/ communications |  | Summary of Collaborative Structure for working together |
| Status: |
| Craft and sign Memorandum of Agreement (MOA) for working together, if needed |  | Agreed upon and signed MOA |
| Status: |

| Objective 8: Design Service Delivery Model |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Research existing models / interventions that meet the needs discovered via RCA, interviews, market scan, etc. |  | Summary of Model Research findings |
| Status: |
| Determine interventions / strategies / key foundational areas of focus based upon RCA findings, market and consumer research, etc. |  | Final report including Model Design |
| Status: |
| Determine model operations, protocols, integration strategies, overall management, staffing, intake / referral, assessment, and service delivery process |  | Final report including Model Operations |
| Status: |
| Define measurements and how performance will be evaluated |  | Final report including Performance Measurements |
| Status: |
| Assess organizational level of readiness for service delivery and determine a plan for capacity building |  | Final report including Capacity Building for Implementation |
| Status: |
| Develop strategy and implementation plan with documented tasks, roles, and timelines |  | Final report including Strategy and Implementation plan with documented tasks, roles, and timelines |
| Status: |

| Objective 9: Develop a Budget and Rate Structure |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Define services/ interventions, cost of delivery, volume, staffing, wages, expenses, training, rate structure, etc., and develop financial model to reflect a variety of situations |  | Final plan defining Budget and Rate Structure |
| Status: |

| Objective 10: Develop an Approach to Marketing |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Define and craft messaging around new service / model in a manner that is important to potential partners and develop marketing material |  | Final plan defining Communication Strategy and Marketing Material |
| Status: |
| Determine additional training / support needed to promote services on an ongoing basis |  | Marketing Training |
| Status: |
| Determine strategies for education, outreach, and the development of new business |  | Final plan defining Business Development plan including projections, target partnerships, strategies per partnership, roles, and timelines |
| Status: |

| Objective 11: Finalize the Business Plan |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Create a business planning framework and a plan that includes (executive summary, target market, service description, organizational structure, partnerships & alliances, budget, implementation plan, outreach plan, growth plan, etc.) |  | Business Plan Outline for Further Proposal Development |
| Status: |

| Objective 12: Formalize a partnership with a Healthcare or Managed Care provider |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| Finalize structure of the partnership including an outline of services, implementation plan, communication plan, performance standards, and an agreed upon and signed legal agreement |  | Formalized partnership |
| Status: |

| Objective 13: Participate in Evaluation Activities |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 13.1 As developed and implemented by The SCAN Foundation participate in evaluation activities. |  | Formalized partnership |
| Status: |

| Objective 14: Additional Activities |
| --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 14.1 |  |  |
| Status: |