## Software Development Gantt
| FEBRUARY 2022 | [19 empty] | MARCH 2022
| 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 26
Lisa Dunson (Project Manager)
Neill Back (SME – outsourced)
Harry Joy (Assistant)
Ken Morris (Analyst)
Julia Foster (Marketing analyst)
Zoe Cloud (IT specialist)
Bob Wallander (IT specialist)
Margaret Pitt (QA)
Zoe Cloud (IT Specialist)
Ben Nilsson (CEO)
Brainstorm
Backup
Research
Keywording
Prototype
Development
Build
Testing
Software Release
Plug-In
SOFTWARE DEVELOPMENT GANTT CHART
Project: Ultimate software V2.0.1

## ©
© TemplateLab.com