DRAFT

STANDARD SHORT FORM CONTRACT FOR PROFESSIONAL SERVICES BETWEEN LANDSCAPE ARCHITECT AND CLIENT

Preliminary Provisions

Date

This Agreement is made as of June 18th , 2019, between the Client and the Landscape Architect for Landscape Architectural Services as provided herein.

Client

Village of Hastings on Hudson

NAME

7 Maple Avenue, Hastings on Hudson, NY 10706

ADDRESS / CITY / STATE / ZIP

RELATIONSHIP TO PROJECT OWNER

Landscape Architect

Peter Gisolfi Associates

NAME

ENTITY

SOLE PROPRIETOR,PARTNERSHIP,CORPORATION,LIMITED LIABILITY COMPANY	LIMITED LIABILITY PARTNERSHIP

566 Warburton Avenue, Hastings on Hudson, NY 10706

ADDRESS / CITY / STATE / ZIP

914-478-3677

CONTACT INFORMATION

Project

(general description of Project: name, purpose, baseline information )

Hastings Downtown Streetscape Improvement

Prepare Conceptual Design for the Hastings on Hudson Village followed by construction documents for improvements for an estimated budget of $200,000.00-$400,000.00. The project is arranged in three phases: 1) Overall Design Plan, 2) Construction Documents, and 3) Construction Administration. See Attached Scope of Services (Appendix A).

Compensation

Compensation for the Scope of Services to be performed under this Agreement shall be the

| Fixed Fee | of $ 8,000.00 plus Reimbursable Expenses. |  |
| --- | --- | --- |
| Standard Short Form Contract | Page 1 of 5 |

© 201 American Society of .C. 2000-898-

Article 1

Landscape Architectural Services

1.1	Standard of Care

The Landscape Architectural Services shall be performed with care and diligence in accordance with the professional standards applicable at the time and in the location of the Project and appropriate for a project of the nature and scope of this Project.

1.2	Scope of Services

Landscape Architectural Services to be provided under this Agreement are:

See Attached Scope of Services (Appendix A)

Phase 1: Analysis and Design Plan: 25%

Phase 2: Construction Drawings and Specifications: 40%

Phase 3: Construction Administration: 35%

1.3	Supplemental Services

Supplemental Services are in addition to the basic Scope of Services and, when requested in writing by the Client, shall entitle the Landscape Architect to additional compensation beyond the Compensation stated above. Supplemental Services under this Agreement expressly include but are not limited to:

Additional Phases/Design beyond attached Scope of Services (Appendix A).

Reduced Hourly Rates:

Partner $120

Associate Partner $120

Senior Landscape Architect $120

Draftsperson $90

1.4	Changes to Approved Services

Revisions to drawings or other documents shall constitute Supplemental Services when made necessary because of Client-requested changes to previously approved drawings or other documents, or because of Client changes to previous Project budget parameters or Project requirements.

1.5	Schedule of Performance

to begin providing services for the Project. The Landscape Architect shall perform the services as expeditiously as is consistent with the standard of care as described:

See Attached Schedule (Appendix B)

Phase 1: Analysis and Design Plan: 8 weeks

Phase 2: Construction Drawings and Specifications: 10 weeks

Phase 3: Construction Administration: 14 weeks

Standard Short Form Contract	Page 2 of 5

© 201 American Society of .C. 2000-898-

Article 2

2.1	Information

The Client shall provide data about the site and other information on which the design is

shall be entitled to rely on the accuracy and completeness of information provided by the Client.

2.2	Budget

The Landscape Architect shall reasonably strive to propose designs and prepare

Architect as a part of the Scope of Services, opinions of probable construction costs are based

on the  familiarity with the landscape construction industry and are

provided only to assist the Client. Such opinions shall not be construed to provide a guarantee or warranty that the actual construction costs will be within the Project budget parameters at the time construction bids are solicited or construction contracts negotiated.

2.3	Approvals

the Landscape Architect in a timely manner so as not to delay the performance of the Landscape Architectural Services.

2.4	Project Permit and Review Fees

The Client shall pay all fees required to secure jurisdictional approvals for the Project.

Article 3

Ownership of Documents

The Landscape Architect shall be deemed the author and owner of all documents and deliverables developed pursuant to this Agreement and provided to the Client by the Landscape Architect ( Reimbursable Expenses owed to the Landscape Architect, the Landscape Architect grants to the Client an irrevocable, non-exclusive license to reproduce the Design Materials solely for the construction of the Project and for information and reference with respect to the use of the Project.

Article 4

Landscape Architect Compensation

4.1 Compensation for the Landscape Architectural Services performed under this Agreement shall be as indicated in the Preliminary Provisions plus Reimbursable Expenses as defined below. Supplemental Services, when requested in writing by the Client, shall require additional compensation to be determined on an hourly basis or on the basis of a negotiated fee.

Standard Short Form Contract	Page 3 of 5

© 201 American Society of .C. 2000-898-

4.2 Reimbursable Expenses are expenditures made by the Landscape Architect, its employees, and consultants in the interest of the Project plus an administrative fee of 10 %.

Reimbursable Expenses include but are not limited to travel expenses, costs of reproduction of documents, postage, services of professional consultants which cannot be quantified at the time of contracting, and other, similar, direct Project-related expenditures.

4.3 Monthly payments to the Landscape Architect shall be based on (1) the percentage of the Scope of Services completed, and shall include payments for (2) Supplemental Services performed, and (3) Reimbursable Expenses incurred.

4.4  invoice. Invoiced amounts unpaid 45 days after the invoice date shall be deemed overdue and shall accrue % simple  payments may be grounds for termination or suspension of services.

4.5 If through no fault of the Landscape Architect, the Scope of Services to be provided under this Agreement has not been completed within 18 mo. (indicate calendar days or months) of the initial notice to proceed, the compensation for services rendered after that time period shall be equitably adjusted.

Article 5

Indemnification

Client and Landscape Architect each agree to indemnify and hold harmless the other, and their respective officers, employees and representatives, from and against liability for losses, damages and expenses, including reasonable attorneys' fees, to the extent such losses, damages, or expenses are solely caused by indemnifying party’s negligent acts, errors, or omissions. The landscape architect shall neither have control over or charge of, nor be responsible for the construction means, methods, techniques, sequences or procedures, or for safety precautions and programs in connection with the Services.

Article 6

Dispute Resolution

6.1 If a dispute arises out of or relates to this Agreement, the parties shall endeavor to resolve their differences first through direct discussions. If the dispute has not been settled

within 14 days of the initial discussions, the parties shall submit the dispute to mediation, the cost of which shall be shared equally by the parties. The potential damages or costs assigned to the Landscape Architect shall not exceed the total compensation paid to the Landscape Architect.

6.2 Nothing in these provisions shall limit rights or remedies not expressly waived under applicable lien laws.

Standard Short Form Contract	Page 4 of 5

© 201 American Society of .C. 2000-898-

Article 7

Termination

This Agreement may be terminated by either party on seven (7)  should the other party fail substantially to perform in accordance with its terms through no fault of the party initiating the termination, provided the defaulting party has not cured or in good faith diligently commenced to cure the breach during the 7-day notice period.

Article 8

Other Terms and Conditions

8.1	Assignment

Neither party shall assign their interest in this Agreement without the express written consent of the other, except as to the assignment of proceeds.

8.2	Governing Law

ss shall govern this Agreement.

8.3	Complete Agreement

This Agreement represents the entire understanding between the Client and the Landscape Architect and supersedes all prior negotiations, representations, or agreements, whether written or oral with respect to its subject matter. The person(s) signing this Agreement on behalf of the parties hereby individually warrant that they have full legal power to execute this Agreement on behalf of the respective parties and to bind and obligate the parties with respect to all provisions contained herein. This Agreement may be amended only in a writing signed by both the Client and the Landscape Architect.

Landscape Architect

Peter Gisolfi AIA ASLA LEED AP	Date

Client

Date

Standard Short Form Contract	Page 5 of 5

© 201 American Society of .C. 2000-898-

PETER	GISOLFI	ASSOCIATES

Appendix A: Scope of Work

- Phase I: Analysis and Design Plan

  - Roles of consultants and Village Officials ∙∙ Analysis

∙∙ Site assessment:

-- Neighborhood context -- Parking

-- Vehicular and pedestrian circulation -- Opportunities and constraints

∙∙ Adjacencies analysis

∙∙ Architectural character

∙∙ Potential sustainability strategies ∙∙ Opportunities and constraints

∙∙ Review with Village Board of Trustees

  - Objectives

∙∙ Interviews with administration, staff, and Board of Trustees ∙∙ Case studies of other streetscape projects ∙∙ Preliminary objectives

∙∙	Preliminary review of Village streetscape elements

∙∙	Revisions to objectives

∙∙	Final objectives

∙∙	Regular reviews with Village Board of Trustees

- Design Alternatives

∙∙	Diagrammatic transformation options for review

∙∙	Focus on preferred alternatives

∙∙	Alternative implementation strategies

∙∙ Continued reviews with the Village Board of Trustees ∙∙ Presentation to Village Board of Trustees

- Order of Magnitude Budgets

∙∙	Budgets for preferred alternatives

Project Approach and Schedule

PETER	GISOLFI	ASSOCIATES

- Phase II: Construction Drawings and Specifications

- Preferred Design

∙∙	Selection of preferred option

∙∙	Landscape Architectural design drawings and narratives

∙∙	Perspective sketches

∙∙	Budget estimate

∙∙	Project implementation strategy and schedule

∙∙ Continued reviews with Village Board of Trustees ∙∙ Presentations to wider community as required

  - Budgets

  - Construction Documents for limited budget ($200,000.00 - 400,000.00)

C. Phase III: Implementation

  - Bidding

  - Award

  - Construction administration

Project Approach and Schedule

PETER	GISOLFI	ASSOCIATES

Appendix B: Preliminary Schedule

Month

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |

| Phase I: | Analysis and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Design Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase II: | Drawings and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Specifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase III: | Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

*Schedule to be modified throughout the course of the project according to the needs of the client and scope.

Project Approach and Schedule