IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

Project Risk Identification

The Risk Matrix shown in the tables below sets out a synopsis of principal risk areas, how they are commonly allocated, managed or eliminated in typical concession projects, and provides a brief explanation of potential consequences, likelihood and an indicative sensitivity analysis methodology. The Risk Registry is also annotated as to whether the particular risk is applicable prior to NTP2, following NTP2, or both before and after NTP2. Environmental risks are outlined in Exhibit C.

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	1

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

|  |  |  |  |  |  |  |  | Table 1: Preliminary Risk Management Matrix |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Before/ |  |  | Risk Description |  |  | Potential Consequences |  |  | Likelihood |  | Risk Allocation | Risk Mitigation Strategy |  | Risk Sensitivity Analysis |  |
|  |  | After NTP 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Design Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Failure/ Inadequate design and/or non |  | Damage to works, delays, design, construction |  | Low | Developer | Back-to-back contract with contractor; Design |  | N/A |
|  |  |  |  |  | compliance with Design Standards & |  | and/or O&M additional costs; penalties |  |  |  |  | audit by an independent consultant; |  |  |  |
|  |  |  |  |  | Criteria |  |  |  |  |  |  |  | Professional indemnity cover |  |  |  |
|  |  | After | Overloaded design & engineering market |  | Delays, additional costs. |  | Low | Developer/ TxDOT | Rational sequencing and phasing of the |  | N/A |
|  |  |  |  |  | capacity |  |  |  |  |  |  |  | facilities |  |  |  |
|  |  | After | Ability to meet established design |  | Delay; increased costs; penalties; cancellation and |  | Low | Developer | Back-to-back contract with contractor; |  | Analysis with different process lengths |
|  |  |  |  |  | milestones; Performance / efficiency |  | costs |  |  |  |  | Adequate quality management plan |  |  |  |
|  |  |  |  |  | shortfalls |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Owner-directed changes and design |  | Delays, additional costs. |  | Low | Developer/ TxDOT | Adequate analysis prior to Facility Agreement |  | N/A |
|  |  |  |  |  | reviews |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Changes in Design Standards & Criteria |  | Delays, additional costs. |  | Medium | Developer/ TxDOT | Compensation if changes occur after |  | N/A |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Execution of CDA |  |  |  |
|  |  | After | Non-compliance with Design Standards & |  | Delays, additional costs. |  | Low | Developer | Back-to-back contract with contractor; Audit by |  | N/A |
|  |  |  |  |  | Criteria due to the use of inadequate |  |  |  |  |  |  |  | an independent consultant. |  |  |  |
|  |  |  |  |  | Technology |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Geotechnical and other data inaccuracies |  | Damage to works, delays, additional costs. |  | Medium | Developer | Back-to-back contract with contractor; |  | N/A |
|  |  |  |  |  | (input/output) |  |  |  |  |  |  |  | Adequate quality management plan; Audit by |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | an independent consultant |  |  |  |
|  |  | After | Design defects affecting constructability |  | Delays, additional costs |  | Low | Developer | Back-to-back contract with contractor; Audit by |  | N/A |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | an independent consultant |  |  |  |
|  |  | After | Latent defects in property following |  | Damage and costs of reinstatement/repair Delay; |  | Low | Developer | Back-to-back contract with contractor; |  | N/A |
|  |  |  |  |  | handback – transfer of title |  | penalties; inability to accept traffic; loss of revenue. |  |  |  |  | Adequate quality management plan; Audit by |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | an independent consultant |  |  |  |
|  |  | After | Failures; Non conforming work and |  | Delays; additional costs; Total/partial Interruption |  | Medium | Developer | Back-to-back contract with contractor; |  | Analysis of impact of different |
|  |  |  |  |  | defects discovered prior and post- |  | in infrastructure service |  |  |  |  | Construction oversight by an independent |  | construction period lengths and different |
|  |  |  |  |  | Acceptance |  |  |  |  |  |  |  | consultant; Insurance |  | construction prices |
|  |  | After | Loss, destruction or damage to existing |  | Debris removal, construction delay, additional |  | Low | Developer | Back-to-back contract with contractor; |  | Analysis of impact of different |
|  |  |  |  |  | property, project facilities or construction |  | costs, penalties |  |  |  |  | Insurance, time extension |  | construction period lengths and different |
|  |  |  |  |  | plant and equipment; Theft |  |  |  |  |  |  |  |  |  | construction prices |
|  |  | After |  | Differing Subsurface (Ground water level |  | Construction delay; additional costs |  | Low | Developer | Back-to-back contract with contractor; |  | Analysis of impact of different |
|  |  |  |  |  | and contamination, geologic formations, |  |  |  |  |  |  |  | Adequate quality control during design stage |  | construction period lengths and different |
|  |  |  |  |  | etc) and Surface Conditions |  |  |  |  |  |  |  |  |  | construction prices |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	2

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

|  |  | Before/ |  |  | Risk Description |  |  | Potential Consequences |  |  | Likelihood |  | Risk Allocation | Risk Mitigation Strategy |  | Risk Sensitivity Analysis |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | After NTP 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Incorrect control survey data | Delays, additional costs |  | Low | Developer | Back-to-back contract with contractor; |  | Analysis of impact of different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor’s adequate quality control |  | construction period lengths |
|  |  | After | Adequacy of construction access | Construction delay; additional costs |  | Low | Developer | Back-to-back contract with contractor; |  | Analysis of impact of different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor’s adequate construction planning |  | construction period lengths |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | and schedule |  |  |  |
|  |  | After | Early construction/Design changes |  | Construction delay; additional costs |  | Low | Developer | Back-to-back contract with contractor; |  | Analysis of impact of different |
|  |  |  |  |  | affecting construction already underway |  |  |  |  |  |  |  | Contractor’s adequate construction planning |  | construction period lengths |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | and schedule |  |  |  |
|  |  | After | Coordination with other projects and with |  | Construction delay; additional costs |  | Low | Developer | Back-to-back contract with contractor; |  | Analysis of impact of different |
|  |  |  |  |  | adjacent property owners |  |  |  |  |  |  |  | Contractor’s adequate management, |  | construction period lengths |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction planning and schedule |  |  |  |
|  |  | After | Lack of general maintenance during |  | Construction delay; additional costs |  | Low | Developer | Back-to-back contract with contractor; |  | N/A |
|  |  |  |  |  | construction; maintenance of traffic |  |  |  |  |  |  |  | Contractor adequate management, |  |  |  |
|  |  |  |  |  | requirements |  |  |  |  |  |  |  | construction planning |  |  |  |
|  |  | After | Adverse weather |  | Construction delay; additional costs |  | Medium | Developer | Back-to-back contract with contractor |  | Analysis of impact of different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction period lengths and different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction prices |
|  |  | After | Identification, requirements, agreements |  | Construction delay; additional costs |  | Low | Developer | Back-to-back contract with contractor | Analysis of impact of different |
|  |  |  |  |  | and relocation of utilities |  |  |  |  |  |  |  |  |  | construction period lengths and different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction prices |
|  |  | After | Contractual non-performance |  | Construction delay; additional costs |  | Medium | Developer | Back-to-back contract with contractor | Analysis of impact of different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction period lengths and different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction prices |
|  |  | After | Breach of site - Health & Safety |  | Injuries of workers; increased costs; delays |  | Medium | Developer | Back-to-back contract with contractor; |  | N/A |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Insurance |  |  |  |
|  |  | After | Breach of site - Security | Increased costs and delays |  | Low | Developer | Back-to-back contract with contractor; |  | N/A |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Insurance |  |  |  |
|  |  | After | Quality and availability of Equipment, |  | Construction delay; additional costs |  | Medium | Developer | Back-to-back contract with contractor | Analysis of impact of different |
|  |  |  |  |  | Materials and Labor |  |  |  |  |  |  |  |  |  | construction period lengths and different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction prices |
|  |  | After | Quality and availability of Equipment, |  | Construction delay; additional costs |  | Medium | Developer | Back-to-back contract with contractor | Analysis of impact of different |
|  |  |  |  |  | Materials and Labor |  |  |  |  |  |  |  |  |  | construction period lengths and different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | construction prices |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	3

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

|  |  | Before/ |  |  | Risk Description |  |  | Potential Consequences |  |  | Likelihood |  | Risk Allocation | Risk Mitigation Strategy |  | Risk Sensitivity Analysis |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | After NTP 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Political/ Legal Risks |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Before/ |  | Change in law (including taxes) | Additional cost |  | Medium | TxDOT/ Developer | General changes in law are borne by the |  | N/A |
|  |  | After |  |  |  |  |  |  |  |  |  |  | Developer. Discriminatory changes in law are |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | likely borne by TxDOT. Compensation may be |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | in the form of temporary relief from various |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | obligations, time extension or compensation. |  |  |  |
|  |  | Before/ |  | Change sales tax | Increased costs |  | Low | TxDOT | Compensation | Analysis with different sales tax rates |
|  |  | After |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Before/ |  | Breach of existing |  | Penalties, delay, consequential losses, additional |  | Low | Developer | Adequate legal advice; |  | N/A |
|  |  | After |  | legislation |  | costs, loss of revenue |  |  |  |  | experienced management |  |  |  |
|  |  | Before/ |  | Breach of obligations/ agreements by |  | Penalties, suspension of payment, suspension of |  | Low | Developer | Back-to-back contract with contractor; |  | N/A |
|  |  | After |  | private sector |  | performance, application of sums to credit of |  |  |  |  | experienced management |  |  |  |
|  |  |  |  |  |  |  |  | retention account, termination and costs |  |  |  |  |  |  |  |  |
|  |  | Before/ |  | Breach of obligations by public sector |  | Penalties/ suspension/ termination and costs |  | Low | TxDOT | Compensation; rights to termination |  | N/A |
|  |  | After |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Before/ |  | Breach of third party intellectual property |  | Penalties, damages |  | Low | Developer | Adequate legal advice | N/A |
|  |  | After |  | rights |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Before/ |  | Force majeure (natural catastrophes, war, |  | Delay additional costs; Parties relieved from |  | Low | TxDOT | Typically borne by the public sector, the |  | N/A |
|  |  | After |  | sabotage, terrorism) |  | liabilities to the extent they are not able to perform |  |  |  |  | Developer is provided with adequate |  |  |  |
|  |  |  |  |  |  |  |  | their obligations under the agreement; termination; |  |  |  |  | compensation; relief with respect to certain |  |  |  |
|  |  |  |  |  |  |  |  | Cancellation; costs to date; |  |  |  |  | contractual obligations; time extension; rights |  |  |  |
|  |  |  |  |  |  |  |  | damage/reinstatement/rectification costs |  |  |  |  | to termination |  |  |  |
|  |  | After | Protestor action, Strikes/Labor disputes |  | Delay, additional costs, damage |  | Medium | TxDOT/ Developer | Compensation; time extension; rights to |  | N/A |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | termination |  |  |  |
|  |  | After | Requisition/ seizure of project facilities by |  | Termination; cost incurred |  | Low | TxDOT | Compensation; time extension; rights to |  | N/A |
|  |  |  |  |  | TxDOT |  |  |  |  |  |  |  | termination |  |  |  |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	4

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

Financial Risks

|  | After | Traffic projections are not realized | Loss of revenues | Medium | Developer | Investment grade traffic studies are prepared | Analysis with different traffic |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | and audited by an independent specialist | assumptions |
|  |  |  |  |  |  | consultant to provide enough comfort to |  |
|  |  |  |  |  |  | lenders |  |
|  | After | Toll evasion | Loss of revenue | Medium | TxDOT/ Developer | Prosecution of the vehicles that don’t pay the | Analysis carried out with different |
|  |  |  |  |  |  | toll fees. Enforcement by the State and its | percentages of loss of the total toll |
|  |  |  |  |  |  | police force as well as barriers and ETC | revenue |
|  |  |  |  |  |  | systems can also help mitigate these risks |  |
|  | Before / | Competing Facilities built | Loss of revenue | Low | TxDOT/ Developer | Clarity in concession agreements regarding | Traffic and revenue forecasts defining |
|  | After |  |  |  |  | what constitutes a Competing Facility and | competing facility scenarios |
|  |  |  |  |  |  | measures to address in one is developed |  |
|  | Before/ | Connecting Facilities not built | Loss of revenues | Medium | TxDOT/ Developer | Coordination with local entities and realistic | Traffic and revenue forecasts defining |
|  | After |  |  |  |  | traffic and revenue forecasts considering | connecting facility scenarios |
|  |  |  |  |  |  | competing facilities scenarios |  |
|  | Before/ | Inflation | Increased costs | Medium | Developer | Fixed lump sum is part of Back-to-back | Analysis carried out with different CPI |
|  | After |  |  |  |  | contract with contractor. Operational costs are | Forecasts |
|  |  |  |  |  |  | indexed being mostly covered through |  |
|  |  |  |  |  |  | indexation of toll rates |  |
|  | Before | Interest rates (pre- | Increased costs | Low | TxDOT/ Developer | Public sector typically bears this risk. | N/A |
|  |  | financial close) |  |  |  | Developers might also be able to take this risk |  |
|  |  |  |  |  |  | depending on time period between bid |  |
|  |  |  |  |  |  | submission and financial close |  |
|  | After | Interest rates (post | Increased costs | Low | Developer | Hedging plan established in accordance with | Analysis carried out with different |
|  |  | financial close) |  |  |  | lenders’ request. The Developer will conclude | interest rates |
|  |  |  |  |  |  | a fixed interest rate swap for all/part of the loan |  |
|  |  |  |  |  |  | term. Alternatively the Developer can borrow |  |
|  |  |  |  |  |  | the funds using fixed rate instruments. |  |
|  | Before/ | Insufficient TIFIA Funds available | Increased costs of financing | Medium | TxDOT | Confirm and maintain interest on Capitol Hill | N/A |
|  | After |  |  |  |  | for TIFIA funds needed for project |  |
|  | Before/ | Capital Markets Appetite insufficient for | Increased costs of financing | Medium | Developer | Assessments of capital markets appetite for | Analysis carried out with alternative |
|  | After | issues |  |  |  | issues to be considered. Underwriter to share | financial structures and interest rates |
|  |  |  |  |  |  | risk of full subscription. |  |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	5

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

|  |  | Before/ |  |  | Risk Description |  |  | Potential Consequences |  |  | Likelihood |  | Risk Allocation | Risk Mitigation Strategy |  | Risk Sensitivity Analysis |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | After NTP 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Refinancing |  | Additional (or lower) cost of financing |  | Low | Developer | For concessions under 40 years, sufficiently |  | Analysis carried out with alternative |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | long term financing can be put in place to |  | financing structures to the extent this |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | eliminate this risk although refinancing gains |  | risk is not already mitigated |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | can also occur as project risks typically |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | decrease after construction, the project may |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | outperform expectations and there may be a |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | general decrease in rates. For longer |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | concession period, the private sector takes a |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | view on long-term rates and the level of |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | refinancing risk. |  |  |  |
|  |  | Before/ |  | Insufficient PABs available or delays in |  | Additional cost of |  | Medium | Developer/TxDOT | Confirm and maintain interest on Capitol Hill |  | Analysis carried out on alternative |
|  |  | After |  | introducing them |  | financing |  |  |  |  | for PABs funds needed for project. |  | financing structures |
|  |  | Planning and Approvals Risks |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Before/ |  | Procurement and performance of Federal, |  | Delay, increase costs; penalties; Cancellation; |  | Medium | Developer | Back-to-back contract with contractor | Analysis of impact of different |
|  |  | After |  | State Agencies and Local Agencies |  | costs to date |  |  |  |  |  |  | construction period lengths |
|  |  |  |  |  | permits and approvals (environmental and |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | others) |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Planning approval overturned | Delay, increase costs, penalties |  | Low | Developer | Back-to-back contract with contractor | Analysis of impact of different |
|  |  |  |  |  |  |  |  | Cancellation; costs to date |  |  |  |  |  |  | construction period lengths |
|  |  | After | Planning approval not covering all works | Delay, increased costs; penalties; |  | Low | Developer | Back-to-back contract with contractor | Analysis of impact of different |
|  |  |  |  |  |  |  |  | Cancellation; costs to date |  |  |  |  |  |  | construction period lengths |
|  |  | Operation and Maintenance Risks |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Operating performance | Penalties, additional costs |  | Low | Developer | Operations manual that will describe the |  | Analysis carried out with different |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | operating procedures to maintain the standard |  | operation costs. |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | levels. |  |  |  |
|  |  | After | Liability to users | User’s claims. |  | Medium | Developer | Adequate customer service. | N/A |
|  |  | After | Collisions | Decreasing in level of service |  | Medium | Developer | Establishment of an emergency service |  | N/A |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | operation procedure |  |  |  |
|  |  | After | Inadequate infrastructure maintenance |  | Decreasing in level of service. |  | Low | Developer | Developer will establish an adequate |  | Analysis with different maintenance |
|  |  |  |  |  |  |  |  | Close of infrastructure |  |  |  |  | maintenance procedure plan. |  | costs |
|  |  | After | Identification and establishment of Right of |  | Delays, increased costs |  | Low | Developer | Adequate control during the design process | N/A |
|  |  |  |  |  | Way limits (utility easements, temporary |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | construction easements) |  |  |  |  |  |  |  |  |  |  |  |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	6

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

|  |  | Before/ |  |  | Risk Description |  |  | Potential Consequences |  |  | Likelihood |  | Risk Allocation | Risk Mitigation Strategy |  | Risk Sensitivity Analysis |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | After NTP 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Injury, damage or financial loss caused by |  | Legal liability to pay claimants costs and expenses |  | Low | Developer | Insurance should include legal liability/ |  | N/A |
|  |  |  |  |  | or arising from the project (other than |  | and own costs and expenses |  |  |  |  | contractual liability |  |  |  |
|  |  |  |  |  | injury to own employees) |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Unavoidable loss, destruction or damage |  | Legal liability to pay claimant’s costs and expenses |  | Low | TxDOT/ Developer | Insurance should include legal liability/ |  | N/A |
|  |  |  |  |  | to third party property |  |  |  |  |  |  |  | contractual liability; time extension |  |  |  |
|  |  | After | Employees’ injury, death, etc. sustained |  | Legal liability to pay claimants costs and expenses |  | Low | TxDOT/ Developer | Insurance | N/A |
|  |  |  |  |  | by other project participants/ staff |  | and own costs and expenses |  |  |  |  |  |  |  |  |
|  |  | After | Employees’ liabilities relating to breach of |  | Legal liability to pay claimant costs and expenses |  | Low | Developer | Adequate management of human resources | N/A |
|  |  |  |  |  | contract / wrongful dismissal / loss of |  | and own costs and expenses |  |  |  |  |  |  |  |  |
|  |  |  |  |  | earnings |  |  |  |  |  |  |  |  |  |  |  |
|  |  | After | Cost of procuring subcontractors |  | Increased costs |  | Medium | Developer | Back-to-back contract with contractor; |  | N/A |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Quality Procedures |  |  |  |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	7

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

Risk Quantification

Once risks have been identified, a risk quantification methodology will be applied that will address the CDA requirements.

The quantification methodology applied is based on the multiplication of the following factors:

- Probability index or risk likelihood occurrence. It is determined in the risk matrix and it is based in the evaluator’s expertise and judgment:

- High (3) when its probability of occurrence ranges from 75% to 100%.

- Medium (2) when its probability of occurrence ranges from 50% to 75%.

  - Low (1) when its probability of occurrence is below 50%.

- Determination of the risk potential impact. It is based on the evaluator’s judgment and logic, quantified as follows:

  - High (3).

- Medium (2).

- Low (1).

As a rule, due to higher uncertainty over requirements imposed by third parties and the inability to control third parties decisions, all risks dealing and related to third parties are often given a high impact rating. The impact is understood as negative impact either to the Developer or to TxDOT.

The ratings found in the following table are calculated by multiplying the probability index and the potential impact.

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	8

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

Table 2: Risk Quantification

Risk

Failure/Inadequate design and/or non compliance with Design Standards & Criteria

Probability	Impact	Rating

Design Risks

1	1	1

| Overfloated design & engineering market capacity | 1 | 1 | 1 |
| --- | --- | --- | --- |
| Ability to meet established design milestones; Performance/ | 1 | 1 | 1 |
| efficiency shortfalls |  |  |  |
| Owner directed changes and design reviews | 1 | 2 | 2 |
| Changes in Design Standards & Criteria | 2 | 2 | 4 |
| Non compliance with Design Standards & Criteria due to the | 1 | 2 | 2 |
| use of inadequate Technology |  |  |  |
| Design defects affecting constructability | 1 | 2 | 2 |
| Geotechnical and other data inaccuracies (input/ output) | 2 | 1 | 2 |
| Latent defects in property following hand back-transfer of title | 1 | 2 | 2 |
| Construction Risks |  |  |  |
| Failures; Non conforming work and defects discovered prior | 2 | 2 | 4 |
| and post-Acceptance |  |  |  |
| Loss, destruction or damage to existing property, project | 1 | 1 | 1 |
| facilities or construction plant and equipment; Theft |  |  |  |
| Differing Subsurface (Ground water level and contamination, | 1 | 1 | 1 |
| geologic formations, etc.) |  |  |  |
| Incorrect survey control data | 1 | 1 | 1 |
| Adequacy of construction access | 1 | 1 | 1 |
| Early construction/ Design changes affecting construction | 1 | 2 | 2 |
| already underway |  |  |  |
| Coordination with other projects and with adjacent property | 1 | 2 | 2 |
| owners |  |  |  |
| Lack of general maintenance during construction; | 1 | 1 | 1 |
| maintenance of traffic requirements |  |  |  |
| Adverse weather | 2 | 2 | 4 |
| Identification, requirements, agreements and relocation of | 1 | 1 | 1 |
| utilities |  |  |  |
| Contractual non-performance | 2 | 2 | 4 |
| Breach of site- Health & Safety | 2 | 3 | 6 |
| Breach of site- Security | 1 | 1 | 1 |
| Quality and availability of Equipment, Materials and Labor | 2 | 1 | 2 |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	9

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

|  | Risk |  |  |  |  |  | Impact |  |  | Rating |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Probability |  |  |  |  |  |  |  |  |
|  | Political/ Legal Risks |  |  |  |  |  |  |  |  |
|  | Change in law | 2 | 3 |  | 6 |  |  |
|  | Change in taxes | 1 | 3 |  | 3 |  |  |
|  | Breach of existing legislation | 1 | 3 |  | 3 |  |  |
|  | Breach of obligations/ agreements by private sector | 1 | 2 |  | 2 |  |  |
|  | Breach of obligations by public sector | 1 | 3 |  | 3 |  |  |
|  | Breach of third party intellectual property rights | 1 | 1 |  | 1 |  |  |
|  | Force majeure (natural catastrophes, war, sabotage, | 1 | 3 |  | 3 |  |  |
|  | terrorism) |  |  |  |  |  |  |
|  | Protestor action, Strikes/ Labor disputes | 2 | 1 |  | 2 |  |  |
|  | Requisition/ seizure of project facilities by TxDOT | 1 | 3 |  | 3 |  |  |
|  |  | Financial Risks |  |  |  |  |  |  |  |  |
|  | Traffic projections are not realized | 2 | 2 |  | 4 |  |  |
|  | Toll evasion | 2 | 1 |  | 2 |  |  |
|  | Competing Facilities built | 1 | 2 |  | 2 |  |  |
|  | Connecting Facilities not built | 2 | 1 |  | 2 |  |  |
|  | Inflation | 2 | 3 |  | 6 |  |  |
|  | Interest rates (pre financial close) | 3 | 2 |  | 6 |  |  |
|  | Interest rates (post financial close) | 3 | 2 |  | 6 |  |  |
|  | Insufficient TIFIA Funds available | 2 | 3 |  | 6 |  |  |
|  | Capital Markets Appetite insufficient for issues | 2 | 3 |  | 6 |  |  |
|  | Refinancing | 1 | 2 |  | 2 |  |  |
|  | Insufficient PABs available or delays in introducing them | 2 | 2 |  | 4 |  |  |
|  | Public Funding | 1 | 3 |  | 3 |  |  |
|  | Planning and Approvals Risks |  |  |  |  |  |  |  |  |
|  | Procurement and performance of Federal, State and Local |  | 2 |  | 3 |  | 6 |  |  |
|  | Agencies permits and approvals (environmental and others) |  |  |  |  |  |  |  |  |
|  | Planning approval overturned | 1 | 3 |  | 3 |  |  |
|  | Planning approval not covering all works | 1 | 3 |  | 3 |  |  |
|  | Defective title | 1 | 3 |  | 3 |  |  |
|  | Operation And Maintenance Risks |  |  |  |  |  |  |  |  |
|  | Operating performance |  | 1 |  | 2 |  | 2 |  |  |
|  | Liability to users | 2 | 2 |  | 4 |  |  |
|  | Collisions | 2 | 1 |  | 2 |  |  |
|  | Inadequate infrastructure maintenance | 1 | 2 |  | 2 |  |  |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	10

IH 635 Managed Lanes Project

Exhibit A to Project Development Plan

Risk Management Matrix

|  | Risk |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  | Probability |
|  | Other | Events Risks |
|  | Identification and establishment of Right-of-Way limits (utility | 1 |
|  | easements, temporary construction easements) |  |
|  | Injury, damage or financial loss caused by or arising from the | 1 |
|  | project (other than injury to own employees) |  |
|  | Inevitable loss, destruction or damage to third party property | 1 |
|  | Employees’ injury, death, etc. sustained by other project | 1 |
|  | participants/staff |  |
|  | Employees’ liabilities relating to breach of contract/ wrongful | 1 |
|  | dismissal/ loss of earnings |  |
|  | Cost of procuring sub-contractors | 2 |
|  | Residual value risk | 2 |

| Impact | Rating |  |
| --- | --- | --- |
| 3 | 3 |  |
| 2 | 2 |  |
| 2 | 2 |  |
| 3 | 3 |  |
| 1 | 1 |  |
| 1 | 2 |  |
| 2 | 4 |  |

IH 635 Managed Lanes Project	Exhibit A to Project Development Plan	11