Risk Assessment Matrix

An Example for Project Managers

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com v1

What is A Risk Assessment Matrix?

- A Risk Assessment Matrix is a tool.

–  Helps organize concerns and risks you foresee with a given project

–  Includes potential impacts to the project

–  Identifies the person(s) responsible for managing each risk item

–  Computes the cost associated with each risk

–  States the likelihood a risk will occur

–  Sums the total potential risk for a project as a function of cost

- A Risk Assessment Matrix helps Project Teams plan for problems, manage

risk, prioritize action, and communicate to others.

- The potential cost of risk value you calculate can be factored into your financial model to build a stronger business case.

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

Key Steps in Building a Risk Assessment Matrix

- Identify the Risk

- Evaluate the Impacts of Each Risk

- Define Ways to Mitigate Each Item

- Calculate the Total Cost of Each Risk

- Define the Probability of Each Item

- Sum the Total Potential Risk Value of a Project

For Step-By-Step Instructions and to Download The Template:

http://www.managersresourcehandbook.com/project-risk-matrix-template/

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  |  | Project Information |  |  |  |  |  |  | Project Financial Summary: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer |  | Watkins Smith Corporation |  |  |  |  |  | Initial ROS: |  | 42% |
| Project |  | RF-30 Upgrade |  |  |  |  | Risk Category Definition | Current ROS: |  | 41% |
| Project Manager | Jessica Abrams |  |  |  |  |  | Estimated Investment: |  | $2.351M |
| Project Start Date | May 1, 2016 |  |  |  |  |  | Current Investment: |  | $1.595M |
| Planned Completion Date | October 1, 2018 | C |  |  |  | Cost | % Budget Spend |  | 68% |
| Estimated Completion Date | August 12, 2018 |  | S |  |  | Schedule | Estimated % Complete: |  | 75% |
| Reporting Date | December 3, 2017 |  |  | R |  | Resources | Initial Risk Value: |  | $119,643 |
| Project Status | On Track |  |  |  | O | Other | Current Risk Value: |  | $100,845 |
|  |  |  |  | Category |  |  |  | Risk Values |  |
| Number |  | Risk Description | Impact of Risk | C | S | R | O | Mitigation Strategy | Risk Owner | Total Risk | Probability of | Predicted |
|  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |
|  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |
|  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |
| 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |
|  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |
|  |  |  |  |  |  |  |  | between payments |  |  |  |  |
|  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |
|  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |
|  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |
| 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | -Seek funding for changes to help absorb | G. DuBois | $33,050 | 50% | $16,525 |
|  |  |  | need to be reduced |  |  |  |  | non-recurring costs impacts |  |  |  |  |
|  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |
|  |  |  | -Purchase of additional software |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |
|  |  | Specialize software is needed |  |  |  |  |  | standard' software |  |  |  |  |
|  |  |  | necessary |  |  |  |  |  |  |  |  |  |
| 3 |  | based on current project |  | X | X | X |  | -Charge customer for added cost of special | R. Nelson | $77,000 | 25% | $19,250 |
|  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |  |
|  |  | requirements |  |  |  |  |  | software under scope change clause. |  |  |  |  |
|  |  |  | -Efficiency loss due to learning curve |  |  |  |  |  |  |  |  |  |
|  |  | Produce Validation Testing | -Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |
|  |  |  | -Added cost of paying 3rd party |  |  |  |  | equipment |  |  |  |  |
| 4 |  | must be performed by 3rd |  | X | X |  | X |  | C. Jenkins | $113,000 | 20% | $22,600 |
|  |  |  | -Schedule impact due to logistics |  |  |  |  | -Work with customer to see what tests they |  |  |  |  |
|  |  | party |  |  |  |  |  | can perform on our behalf |  |  |  |  |
|  |  |  | -Recurring Cost in excess of business |  |  |  |  |  |  |  |  |  |
|  |  | Product Parts List exceeds | case |  |  |  |  | -Negotiate component costs with suppliers |  |  |  |  |
| 5 |  | estimated value by more than | -Reduced profit margin if price | X |  |  |  | -Renegotiate contract price with customer | M. Hart | $8,400 | 30% | $2,520 |
|  |  | 10% | remains unchanged |  |  |  |  | based on customer-driven changes. |  |  |  |  |
|  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |
|  |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |
|  |  | Customer IT system/formats | internally |  |  |  |  | -Test software export abilities within first |  |  |  |  |
|  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  |  |  |
| 6 |  | cannot receive project |  | X | X |  |  |  | R. Nelson | $18,500 | 70% | $12,950 |
|  |  |  | software |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |
|  |  | deliverables |  |  |  |  |  |  |  |  |  |  |
|  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |
|  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | $294,950 |
|  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  | Project Information |  |  | Project Financial Summary: |  |
| --- | --- | --- | --- | --- | --- |
| Customer | Watkins Smith Corporation |  |  | Initial ROS: | 42% |
| Project | RF-30 Upgrade |  | Risk Category Definition | Current ROS: | 41% |
| Project Manager | Jessica Abrams |  |  | Estimated Investment: | $2.351M |
| Project Start Date | May 1, 2016 |  |  | Current Investment: | $1.595M |
| Planned Completion Date | October 1, 2018 | C | Cost | % Budget Spend | 68% |
| Estimated Completion Date | August 12, 2018 | S | Schedule | Estimated % Complete: | 75% |
| Reporting Date | December 3, 2017 | R | Resources | Initial Risk Value: | $119,643 |
| Project Status | On Track | O | Other | Current Risk Value: | $100,845 |

|  |  |  |  |  |  |  | Category |  | Create a Header |  |  |  | Risk Values |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Risk | Probability of | Predicted |  |  |
| Number | Risk Description |  |  |  | Impact of Risk | C | S | R | O |  |  | Mitigation Strategy |  | Risk Owner |  | Value | Occurrence | Risk Value |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |  |  |  |  |  |
|  | product into market |  |  | - |  | a Risk Assessment |  |  | clause of contract |  |  |  |  |  |  | as a |  |  |  |
|  |  |  | d |  |  |  |  |  | Matrix is used by a project team and |  |  |  |
| 1 | Customer delays release of |  | -D lay in inve tment recovery |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |  |  |  |
|  |  | Since |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Reduced Sales next year |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |  |  |  |  |  |
|  |  | reporting tool, create | a |  |  |  |  |  |  |  | project. |  |  |  |
|  |  |  |  |  | header of key information about the |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | b tween payments |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Reduction in total projected revenue |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |  |  |  |  |  |
|  | Customer seeks to renegotiateYou may want to include: |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Business case m y ot be as strong |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |  |  |  |  |  |
| 2 | price based on final design |  | -Sales contribution from project may | X |  |  | X |  |  | G. DuBois | $33,050 | 50% | $16,525 |  |  |  |
|  |  |  | need to be reduced |  |  |  |  | -Seek funding for changes to help absorb | Project Information |  |  |  |  |
|  |  |  |  |  |  |  |  |  | non-recurring costs impacts |  |  |  |  |  |
|  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Customer |  |  |  |  | Watkins Smith Corporation |  |
|  |  | • | Project Name |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Purchase of additional software |  |  |  |  | standard' software |  |  |  |  |  | RF-30 Upgrade |  |
| 3 | Specialize software is needed | Customer | X | X | X | Project |  |  |  | R. Nelson |  | $77,000 |  |  |
|  | based on current project• |  |  |  |  |  | -Charge customer for added cost of special |  |  |  |  | 25% | $19,250 |  |  |  |
|  |  |  |  | nece | ary |  |  |  | Project Manager |  |  |  |  |  | Jessica Abrams |  |
|  |  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |  |  |  |
|  | requirements | • |  | -Efficiency loss due to learni curve |  |  |  |  | software under scope change clause. |  |  |  |  |  |  |  |  |  |
|  |  |  | Program Manager |  | Project Start Date |  |  |  |  | May 1, 2016 |  |
|  | Produce Validation Testing |  | -Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  | October 1, 2018 |  |
|  |  | Key Dates |  |  |  | Planned Completion Date |  |  |  |  |  |  |
| 4 |  | • |  | X | X |  | X | equipment |  |  |  | C. Jenkins |  | $113,000 | 20% | $22,600 |  |  |  |
|  | must be performed by 3rd |  | -Added cost of paying 3rd party |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Schedule impact due to logistics |  |  |  | Estimated Completion Date |  |  |  |  | August 12, 2018 |  |
|  | party |  |  |  |  |  |  |  | -Work with cust mer to see what tes s they |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | can perform on our behalf |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Reporting Date |  |  |  |  |  | December 3, 2017 |  |
|  |  |  |  | -Recurring Cost in excess of business |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Project Status |  |  |  |  |  | On Track |  |
|  | Product Parts List exceeds |  | case |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | -Negotiate component costs with suppliers |  |  |  |  |  |  |  |  |  |
| 5 | estimated value by more than |  | -Reduced profit margin if price | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Renegotiate contract price with customer |  | M. Hart |  | $8,400 | 30% | $2,520 |  |  |  |
|  | 10% |  |  | remains unchanged |  |  |  |  | based on customer-driven changes. |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | internally |  |  |  |  | -Test software export abilities within first |  |  |  |  | Impact | of Risk |  |  |  |
|  | Customer IT system/formats |  | -May require specialize conversion |  |  |  |  | Number |  | Risk Description |  |  |  |  |  |  |  |
| 6 | cannot receive project |  |  |  | X | X |  |  | 90 days |  |  |  | R. Nelson | $18,500 | 70% | $12,950 |  |  |  |
|  |  |  |  | software |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |  |  |  |  |
|  | deliverables |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |  |  |  |  |  |
|  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 1 |  | Customer delays release of end -Delay in investment recovery |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | product into market | Total Potential Risk (Unweighted) | $294,950 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact-Reduced(Weighted)Sales next$100,845year |  |  |

C

C

C

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  |  |  |  |  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Financial Summary: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Customer |  |  | Watkins Smith Corporation |  |  |  |  |  |  |  |  |  |  | Initial ROS: |  |  | 42% |  |
|  |  | Project |  |  | RF-30 Upgrade |  |  |  |  |  |  | Risk Category Definition |  |  |  |  | Current ROS: |  |  | 41% |  |
|  |  | Project Manager |  | Jessica Abrams |  |  |  |  |  |  |  |  |  |  |  |  | Estimated Investment: |  |  | $2.351M |  |
|  |  | Project Start Date |  | May 1, 2016 |  |  |  |  |  |  |  |  |  |  |  |  | Current Investment: |  |  | $1.595M |  |
|  |  | Planned Completion Date |  | October 1, 2018 |  |  | C |  |  |  | Cost |  |  |  |  |  | % Budget Spend |  |  | 68% |  |
|  |  | Estimated Completion Date | August 12, 2018 |  |  |  | S |  |  | Schedule |  |  |  |  |  | Estimated % Complete: |  |  | 75% |  |
|  |  | Reporting Date |  | December 3, 2017 |  |  |  |  | R |  | Resources |  |  |  |  |  | Initial Risk Value: |  |  | $119,643 |  |
|  |  | Project Status |  | On Track |  |  |  |  |  | O | Other |  |  |  |  |  | Current Risk Value: |  |  | $100,845 |  |
|  |  |  |  |  |  |  |  |  |  |  | Category |  |  |  |  |  |  |  |  |  |  | Risk Values |  |  |
|  |  | Number |  | Risk Description | Impact of Risk |  |  | C | S | R | O |  | Mitigation Strategy |  |  | Risk Owner |  | Total Risk | Probability of | Predicted |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |  |
|  |  |  |  |  |  |  |  | Create a Header |  | - (Continued)laysAddcustomer-driven |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | to penalties |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 1 |  |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept |  | T. Franklin |  |  | $45,000 | 60% |  | $27,000 |  |
|  |  |  |  |  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |  |  |  |  |  |  |
|  |  | Since | a Risk Assessment Matrix is used |  |  |  | and | as a |  |  |  |  |
|  |  |  |  | by a project team |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | between p yments |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Reduction in total project | revenue |  |  |  |  | -Track detailed cost changes through |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | headerstrong |  |  |  |  | information | about |  | the | project. |  |  |  |  |
|  |  | reporting tool, create-Businss case may not be as | of key |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 2 |  |  | Customer seeks to renegotiate | -Sales contribution from project may | X |  |  | X | design evolution to show cost adjustments |  | G. DuBois |  |  | $33,050 | 50% |  | $16,525 |  |
|  |  |  |  |  |  | price based on final design |  |  |  |  |  | -Seek funding for changes to help absorb |  |  |  |  |  |  |  |  |  |  |
|  |  | You may want to include: |  |  |  |  |  |  | non-recurring costs impacts |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | eed to be reduced |  |  |  |  |  |  |  | Project Financial Summary: |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |  |  |  | 42% |  |  |  |
|  |  |  |  |  |  |  |  | -Purchase of additional software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | • |  |  |  |  |  |  |  |  |  |  |  | Initial ROS: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Specialize software is needed |  |  |  |  |  |  |  | standard' software |  |  |  |  |  |  |  |  | 41% |  |  |  |
|  |  |  | 3 | Return on Sales (ROS) |  |  | X | X | X | Current ROS: |  |  |  |  | R. Nelson |  | $77,000 |  |  | $19,250 |  |
|  |  |  |  |  |  | based on current project | necessary |  |  |  |  |  | -Charge customer for added cost of special |  |  |  |  | 25% |  |  |  |
|  |  |  |  |  |  | Risk Category Definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | requirements |  | -Employees will need training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | • |  |  |  |  |  |  |  |  |  |  |  |  | software under scope change clause. |  |  |  |  |  | $2.351M |  |  |  |
|  |  |  |  | Total Investment |  |  |  |  | Estimated Investment: |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Efficiency loss due to learning curve |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Produce Validation Testing | -Need to identify potential suppliers |  |  |  |  |  | -Setup test program o use only internal |  |  |  |  |  | $1.595M |  |  |  |
|  |  | • 4 |  |  |  |  |  |  |  |  |  | Current Investment: |  |  |  |  |  |  |  |  |  |
|  |  |  | % of Budget Spent |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | must be performed by 3rd | -Added cost of paying 3rd party |  | X | X |  |  | equipment |  |  |  |  |  | C. Jenkins |  | $113,000 | 20% |  | $22,600 |  |
| C |  |  |  |  |  |  |  |  |  |  |  |  |  | % Budget Spend |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Cost |  | -Schedule impact due to logistics |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 68% |  |  |  |
|  |  | • |  |  |  | party |  |  |  |  |  |  |  | -Work with customer to see what tests they |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Risk Values |  |  |  |  |  |  |  | can perform on our behalf |  |  |  |  |  |  |  |  |  |  |  |  |
| S |  |  |  |  | -Recurring Cost in excess of business |  |  |  | Estimated % Complete: |  |  |  |  |  |  | 75% |  |  |  |
|  |  |  |  | Schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R |  |  |  |  | Product Parts List exceeds | case |  |  |  |  |  |  | -Negoti te component costs with suppliers |  |  |  |  | $119,643 |  |  |  |
|  |  |  |  | Resources |  |  |  |  |  |  |  |  | Initial | Risk Value: |  |  |  |  |  |  |  |  |  |
|  |  |  | 5estimated value by more than | -Reduced profit margin if price |  | X |  |  |  | -Renegotiate contract price with customer |  | M. Hart |  | $8,400 | 30% |  | $2,520 |  |
|  |  |  | O | Other |  | remains unchanged |  |  |  |  |  | Current Risk Value: |  |  |  |  |  | $100,845 |  |  |  |
|  |  |  |  |  |  | 10% |  |  |  |  |  |  |  |  | based on customer- driven changes. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Category |  |  | Customer IT system/formats | internally |  |  |  |  |  |  | -Test software export abilities within first |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  | Risk Values |  |  |  |  |  |  |
|  |  |  | 6 |  |  | cannot receive project | software |  |  | X | X |  |  | -Have customer provide list of formats to |  | R. Nelson | of | $18,500 | 70% |  | $12,950 |  |
| C S | R | O |  |  | deliverables | Mitigation | Strategy |  |  |  | Risk |  | Owner | Total Risk |  | Probability |  | Predicted |  |  |
|  |  |  |  |  |  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  | Occurrence | Risk Value |  |  |
|  |  |  |  |  |  |  |  | cannot be resolved |  |  |  |  |  |  |  | Value |  |  |  |  |  |
|  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | $294,950 |  |
|  |  |  |  | clause of contract |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |  |
| © All rights reserved. The Managers Resource Handbook by MHX Global LLP |  |  |  | $45,000 |  |  |  | www.ManagersResourceHandbook.com v1 |
| X |  |  | X | -Add milestone payments for Initial Concept |  | T. Franklin |  |  |  | 60% |  |  | $27,000 |  |  |  |

|  |  |  |  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Financial Summary: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Customer |  |  |  | Watkins Smith Corporation |  |  |  |  |  |  |  |  |  |  |  |  |  | Initial ROS: |  |  |  |  | 42% |  |  |  |
|  |  |  | Project |  |  |  |  | RF-30 Upgrade |  |  |  |  |  |  |  |  |  | Risk Category Definition |  | Current ROS: |  |  |  |  | 41% |  |  |  |
|  |  |  | Project Manager |  |  |  | Jessica Abrams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Estimated Investment: |  |  |  | $2.351M |  |  |  |
|  |  |  | Project Start Date |  |  |  |  | May 1, 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Current Investment: |  |  |  | $1.595M |  |  |  |
|  |  |  | Planned Completion Date |  |  |  | October 1, 2018 |  |  | C |  |  |  |  |  | Cost |  |  |  |  |  | % Budget Spend |  |  |  |  | 68% |  |  |  |
|  |  |  | Estimated Completion Date |  |  |  | August 12, 2018 |  |  |  | S |  |  |  |  | Schedule |  |  |  | Estimated % Complete: |  |  |  |  | 75% |  |  |  |
|  |  |  | Reporting Date |  |  |  | December 3, 2017 |  |  |  |  | R |  |  | Resources |  |  |  | Initial Risk Value: |  |  |  | $119,643 |  |  |  |
|  |  |  | Project Status |  |  |  |  | On Track |  |  |  |  |  |  | O | Other |  |  |  |  |  | Current Risk Value: |  |  |  | $100,845 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Category |  |  |  |  |  |  |  |  |  | Risk Values |  |  |  |  |  |
|  |  |  | Number |  | Risk Description |  |  |  | Impact of Risk |  |  | C | S | R | O |  |  |  | Mitigation Strategy |  | Risk Owner | Total Risk | Probability of | Predicted |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Create a Header |  |  | - (Continued)Addcustomer-drivendelaysto penalties |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  |  |  |  | clause of contract |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 1 |  |  |  |  |  |  | X |  |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |  |  |  |
|  |  |  |  |  |  | product into market |  | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Since | a Risk Assessment Matrix is used |  |  |  |  | and as a |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | between payments |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | by a project team |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Reduction in total project | evenue |  |  |  |  |  |  | -Track detailed cost cha ges througho |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | header |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | information | about |  | the project. | You |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Business case may not be as strong |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | reporting tool, create- | a |  |  | of key |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 2 |  |  | Customer seeks to renegotiate | -Sal s contribution from project may | X |  |  |  | X | design evolution to show cost adjustments |  | G. DuBois | $33,050 | 50% | $16,525 |  |  |  |
|  |  |  |  |  |  | price based on final design |  |  |  |  |  |  |  |  |  |  |  |  | -Seek funding for changes to help absorb |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | may want to include:neto be reduced |  |  |  |  |  |  |  |  | non-recurring costs impacts |  |  |  |  |  |  |  |  | Project Financial |
|  |  |  |  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ustomer |  |  |  |  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Initial ROS: |  |
|  |  |  |  |  |  |  |  | Watkins Smith Corporation |  |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Purchase of additional software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| oject |  |  |  |  |  | Specialize s ftware is need |  |  |  |  |  |  |  | standard' software Risk Category Definition |  |  |  |  | Current ROS: |  |
|  |  |  |  |  |  |  |  |  | RF-30 Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | • 3 |  |  |  |  | necessary |  |  |  | X | X |  | X | -Charge customer for added cost of special |  | R. Nelson | $77,000 |  | 25% | $19,250 |  |  |  |
|  |  |  |  |  | based on current projectLegend | of Definitions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| oject Manager |  |  | A Key or |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Estimated Investment: |  |
|  |  |  |  |  |  |  |  |  | Jessica Abrams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Employees will need training |  |  |  |  |  |  |  |  | software under scope change clause. |  |  |  |  |  |  |  |  |  |  |  |
| oject Start Date |  |  | requirements |  | -Efficiency loss due to learning curve |  |  |  |  |  |  |  |  |  |  |  |  | Current Investment: |  |
|  |  |  |  |  |  |  | May 1, 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| anned Completion Date |  | -Need to identify potential suppliers |  |  |  |  |  |  | - | Setup | test program to use only internal |  |  |  |  |  | % Budget Spend |  |
|  |  |  |  | October 1, 2018 |  |  |  |  |  |  | C |  |  |  | Cost |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Produce Validation Testing | -Added cost of paying 3rd party |  | X | X |  |  |  | X |  | equipment | Schedule |  |  | C. Jenkins | $113,000 |  | 20% | $22,600 |  |  |  |
|  |  |  | 4must be performed by 3rd |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| timated Completion Date |  |  |  | August 12, 2018 |  |  |  |  |  |  |  |  | S |  |  |  |  |  |  |  |  | Estimated % Complete: |  |
|  |  |  |  |  |  | party |  | -Schedule impact due to logistics |  |  |  |  |  |  | - | Work | with | customer to see what tests they |  |  |  |  |  |  |  |  |  |  |  |
| eporting Date |  |  |  |  |  |  |  | December 3, 2017 |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  | Initial Risk Value: |  |
| oject Status |  |  |  |  |  |  | -Recurring Cost in excess of business |  |  |  |  |  |  |  |  |  | O | Other |  |  |  |  |  |  | Current Risk Value: |  |
|  |  |  |  |  |  |  |  |  |  | On Track |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Product Parts List exceeds | case |  |  |  |  |  |  |  |  |  |  | -Negotiate | component costs with suppliers |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 5estimated value by more than | -Reduced profit margin if price |  | X |  |  |  |  |  | -Renegotiate contract price with customer |  | M. Hart | $8,400 | 30% | $2,520 |  |  | Ris |
|  |  |  |  |  |  | 10% |  | remains unchanged |  |  |  |  |  |  |  |  | b s d on customer-driven changes. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Category |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Risk | Pr |
| umber |  |  | Risk | Description |  | -Will need to convert formats |  |  |  |  |  |  |  | C S | R O |  | Mitigation | Strategy |  |  | Risk Owner |  |  |  |
|  |  |  |  |  |  |  |  | Impact of Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Value | O |
|  |  |  |  |  |  | Customer IT system/formats | internally |  |  |  |  |  |  |  |  |  | -Test software export abilities within first |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | -May require specialize conversion |  |  |  |  |  |  | 90 days |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 6 |  |  | cannot receive project |  |  | X | X |  |  |  |  |  | -Add customer-driven | delaysR.Nelsonto penalties$18,500 | 70% | $12,950 |  |  |  |
|  |  |  |  |  |  |  |  | software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | deliverables |  |  |  |  |  |  |  |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | evaluate import capabilities |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Customer |  |  |  |  |  | -Schedule impact if formatting issues |  |  |  |  |  |  |  |  |  |  | clause of contract |  |  |  |  |  |  |  |  |  |  |  |
|  |  | delays release of end -Delay in investment recovery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  |  |  |  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept |  | T. Franklin |  |  | $45,000 |  |
|  | product | into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | and Design Acceptance | to shorten time |  |  |  | $294,950 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | between payments |  | Total Estimated Impact (Weighted) | $100,845 |  |  |  |
|  | © All rights reserved. The Managers Resource Handbook by MHX Global LLP |  |  |  |  |  |  |  |  |  |  |  | www.ManagersResourceHandbook.com | v1 |  |

-Reduction in total projected revenue

-Track detailed cost changes throughout

|  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Financial Summary: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Customer |  | Watkins Smith Corporation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Initial ROS: |  |  |  |  | 42% |  |
|  | Project |  | RF-30 Upgrade |  |  |  |  |  | Risk Category Definition |  |  | Current ROS: |  |  |  |  | 41% |  |
|  | Project Manager | Jessica Abrams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Estimated Investment: |  |  |  |  | $2.351M |  |
|  | Project Start Date | May 1, 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Current Investment: |  |  |  |  | $1.595M |  |
|  | Planned Completion Date | October 1, 2018 |  | C |  |  |  | Cost |  |  |  |  |  |  |  | % Budget Spend |  |  |  |  | 68% |  |
|  | Estimated Completion Date | August 12, 2018 |  |  | S |  |  | Schedule |  |  |  |  |  |  |  | Estimated % Complete: |  |  |  |  | 75% |  |
|  | Reporting Date | December 3, 2017 |  |  |  | R |  | Resources |  |  |  |  |  |  | Initial Risk Value: |  |  |  |  | $119,643 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project | Information |  |  |
|  | Project Status | On Track |  |  |  |  | O | Other |  |  |  |  |  |  |  |  |  | $100,845 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Current Risk Value: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Customer |  |  |  |  |  | Risk Values Watkins | Smith Corpora |
|  |  |  |  |  |  | Category |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Project |  |  |  |  |  | Total Risk | Probability of |  | Predicted | 30 Upgrade |
|  | Number |  | Risk Description | Impact of Risk |  | C | S | R | O |  |  |  |  |  |  |  | Risk Owner |  |  |  |  |  |  | RF- |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Mitigation Strategy |  |  | Value | Occurrence |  | Risk Value |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Project Manager |  |  | The Risk |  |  |  |  | Jessica Abrams |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | to penalties |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | -Add customer-drivenStepdlays 1: Identify |  |  |  |  |  |  |  |
|  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  |  | clause of |  | ntra t |  |  |  |  |  |  |  |  |  |  |  | May 1, 2016 |
|  | 1 |  |  |  |  |  | X |  | X |  |  | Project Start Date | T. Franklin |  | $45,000 | 60% |  |  |
|  |  |  | product into market | -Reduced Sales next year |  |  |  |  |  | -Add milestone payments for Initial Concept |  |  |  |  |  | $27,000 |  |
|  |  |  |  |  |  |  |  |  |  | and Design Acceptance to shorten | me |  |  |  |  |  |  |  | October 1, 2018 |
|  |  |  |  |  | • |  |  |  |  |  |  | Planned Completion Date |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | be ween payments |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Meet with Project Team |  |  |  |  |  |  |  |  |
|  |  |  |  | -Reduction in total projected revenue |  |  |  |  |  |  | Estimated Completion Date |  |  |  |  |  |  | August 12, 2018 |
|  |  |  |  |  |  |  |  |  | -Track detailed cost changes | hroughout |  |  |  | concerns |  | December 3, 2017 |
|  |  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Reporting Date |  |  |  |  |  |  |  |
|  |  |  | Customer seeks to renegotiate |  | • |  | Brainstorm all possible issues and |  |  |
|  | 2 |  |  | -Sales contribution from project may | X |  |  | X | design evolution to show cost adjustments | G. DuBois |  | $33,050 | 50% |  | $16,525 |  |
|  |  |  | price based on final design |  |  |  |  |  | -Seek funding for changes | help absorb |  |  |  |  |  |  |  |
|  |  |  |  |  | • |  |  |  |  |  |  | Project Status |  |  |  |  |  |  |  |  | On Track |
|  |  |  |  | need to be reduced |  |  | Groupnon- | recurringthemcosts impactsinto main buckets |  |  |  |  |  |  |  |
|  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Purchase of additional software |  |  |  |  |  | -Negotiate with | customer to use 'industry |  |  |  |  |  |  |  |  |  |
|  |  |  | Specialize software is needed |  |  |  |  |  |  | standard' software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 |  | based on current project |  |  | X | X | X | -Charge customer | for | added cost of special | R. Nelson |  | $77,000 |  |  | 25% |  | $19,250 |  |
|  |  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | requirements |  |  |  |  |  |  | software under scope | change clause. |  |  |  |  |  |  |  | Impact of Risk |
|  |  |  |  | -Efficiency loss due to learning curve |  |  |  |  |  |  | Number |  |  | Risk Description |  |  |  |  |  |  |
|  |  |  | Produce Validation Testing | -Need to identify potential suppliers |  |  |  |  | -Setup test program to | use only internal |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Added cost of paying 3rd party |  |  |  |  |  | equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | must be performed by 3rd |  |  | X | X |  | X |  |  |  |  |  |  |  | C. Jenkins |  | $113,000 |  |  | 20% |  | $22,600 |  |
|  |  |  | -Schedule impact due to logistics |  |  |  |  |  | -Work with customer to see what tests they |  |  |  |  |  |  |  |  |  |
|  |  |  | party |  |  |  |  |  |  | can perform on our | behalf |  |  |  |  |  |  | - | Delay in investment recove |
|  |  |  |  |  |  |  |  |  |  |  |  | Customer delays release of end |  |  |
|  |  |  |  | -Recurring Cost in excess of business |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | product into market |  |  |  | - | Reduced Sales next year |
|  |  |  | Product Parts List exceeds | case |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | -Negotiate component costs with suppliers |  |  |  |  |  |  |  |  |  |
|  | 5 | estimated value by more than | -Reduced profit margin if price |  | X |  |  |  | -Renegotiate contract price with customer | M. Hart |  | $8,400 |  |  | 30% |  | $2,520 |  |
|  |  |  | 10% | remains unchanged |  |  |  |  |  | based on customer-driven changes. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Will need to convert formats | • |  |  |  |  |  |  |  |  |  |  |  |  |  |  | but | realistic! |  | -Reduction in total projected |
|  |  |  |  | internally |  |  |  |  |  | -Test software export abilities within first |  |  |  |  |
|  |  |  | Customer IT system/formats |  |  |  | NOTE: Be thorough… |  |  |  | -Business case may not be as |
|  |  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 |  | cannot receive project | software |  | X | X |  |  | -Have customer provide list of f | ats to | R. Nelson |  | $18,500 |  | 70% |  | $12,950 |  |
|  |  |  | deliverables |  |  |  |  |  |  |  |  |  |  |  |  |  | Customer seeks to | renegotiate |  | -Sales contribution from pro |
|  |  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate | import capabilities |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 2 |  |  | price based on final | design |  |  |
|  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | need to be reduced |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | -Cost |  | $294,950 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | reduction | may be need |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $100,845 |  |
| © All rights reserved. The Managers Resource Handbook by MHX Global LLP |  |  |  |  |  |  |  |  |  |  |  |  | www.ManagersResourceHandbook.com v1 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -Purchase of additional softw |

|  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Financial Summary: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Customer |  |  | Watkins Smith Corporation |  |  |  |  |  |  |  |  |  | Initial ROS: |  |  | 42% |  |  |  |  |
|  | Project |  |  |  |  | RF-30 Upgrade |  |  |  |  |  | Risk Category Definition |  |  |  | Current ROS: |  | 41% |  |  |  |  |
|  | Project Manager |  |  |  | Jessica Abrams |  |  |  |  |  |  |  |  |  | Estimated Investment: |  | $2.351M |  |  |  |  |
|  | Project Start Date |  |  |  | May 1, 2016 |  |  |  |  |  |  |  |  |  | Current Investment: |  | $1.595M |  |  |  |  |
|  | Planned Completion Date |  | October 1, 2018 |  | C |  |  |  | Cost |  |  |  | % Budget Spend |  | 68% |  |  |  |  |
|  | Estimated Completion Date |  | August 12, 2018 |  |  | S |  |  | Schedule |  |  | Estimated % Complete: |  | 75% |  |  |  |  |
|  | Reporting Date |  | December 3, 2017 |  |  |  | R |  | Resources |  |  |  | Initial Risk Value: |  | $119,643 |  |  |  |  |
|  | Project Status |  |  |  | On Track |  |  |  |  | O | Other |  |  | Current Risk Value: |  | $100,845 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Category |  |  |  |  |  |  |  |  |  | Risk Values |  |  |  |  |  |
|  | Number |  | Risk Description |  |  |  | Impact of Risk |  | C | S | R | O | Mitigation Strategy |  | Risk Owner |  | Total Risk | Probability of | Predicted |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Project Information |  |  |  | Value | Occurrence | Risk Value |  |  |  |  |
|  |  |  |  |  |  |  | Customer |  |  |  |  | -Add customer-driven delays to penalties | Watkins | Smith | Corporation |  |  |  |  |  |
|  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Franklin |  |  | 45,000 | 60% | $27,000 |  |  |  |  |
|  | 1 |  |  |  |  |  | Project |  |  | X |  | X | -Add milestone payments for Initial Concept | T. |  |  |  |  |  |  |  |  |  |  |
|  |  |  | product into market |  |  |  |  |  |  |  |  |  |  |  |  | RF-30 | $Upgrade |  |  |  |  |  |
|  |  |  |  | -Reduced Sales next year |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Project Manager |  |  |  |  |  |  |  | Jessica Abrams |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | between payments |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Reduction inProjecttotalprojectedStartrevenueDate |  |  |  | -Track detailed cost changes throughout |  |  |  | May 1, 2016 |  |  |  |  |  |
|  |  |  |  | -Business case may | ot be as strong |  |  |  |  |  |  |  | October 1, 2018 |  | C |  |  | C |
|  |  |  | Customer seeks to renegotiate |  |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Planned Completion |  |  | Date |  |  |  |  |  |  |  |  |  |
|  | 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | - Seek funding for chang s to help absorb | G. DuBois |  |  | $33,050 | 50% | $16,525 |  | S |  | Sc |
|  |  |  |  | need to be reducedEstimated Completion |  | nonDate-recurring costs impacts |  |  |  | August 12, 2018 |  |  |  |  |  |
|  |  |  |  | -Cost reduction may be needed |  |  |  |  | Step 2: Define the | Impact |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Reporting Date |  |  |  |  | -Negotiate with customer to use 'industry |  |  | December 3, 2017 |  |  |  | R | R |
|  |  |  |  | -Purchase of additional software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Specialize software is needed |  |  |  |  |  | standard' software |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | necessary Project Status |  |  |  |  |  |  |  |  |  |  | On Track |  |  |  | O O |
|  | 3 |  | based on current project | -IfEmployeesthe |  |  |  |  | X | X | X |  | -Charge cust mer for added cost of special | R. N | lson |  |  | $77,000 | 25% | $19,250 |  |  |  |  |
|  |  |  | requirements |  |  | willriskneedtrainingbecame ‘real,’ how would it affect the project? |  |  |  |  |  |
|  |  |  |  | - Efficiency | loss due to learning curve |  |  |  |  | software under scope change clause. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Category |  |
|  |  |  | Produce Validation Testing | -Need to | identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Added cost f paying 3rd party |  |  |  |  | equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | must be performed by 3rd |  | X | X |  | X |  |  | C. Jenkins | $113,000 | 20% | $22,600 |  |  |  |  |
|  |  |  | • | More Time? |  |  |  |  | -Work with cust mer to see what | tests they |  |  |  |  |  |  |  |  |
|  |  |  | party | -Schedule impact due to logistics |  | Risk |  |  |  |  | Impact of Risk |  | C | S | R O |  |
|  |  |  |  | -•Recurring | Number |  |  |  | Description |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Added Cost? |  |  |  |  | can perform on our behalf |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Cost in excess of business |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -A |
|  |  |  | Product Parts List exceeds | case |  |  |  |  |  | X |  |  |  | -Negotiate component costs with | suppliers | M. Hart |  |  | $8,400 | 30% | $2,520 |  |  |  |  |
|  | 5 | estimated value by more than | Reduced profit margin if price |  |  |  |  | -Renegotiate contract price with | customer |  |  |  |  |  |  |  |  |  |  |
|  |  |  | -• | Require More |  | Resources? |  |  |  |  |  |  |  |  |  |  |  |  | cl |
|  |  |  | 10% | remains unchanged |  |  |  |  |  |  | based on customer-driven changes. | -Delay in investment recovery |  |  |  |  |  |
|  |  |  |  | -Potential loss on effort | Customer delays release of end |  |  |  |  |  |  |
|  |  |  |  | • | Change Pricing Strategy? |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | -Reduced Sales next year |  |  | X | X | -A |
|  |  |  |  | -Will need to convert formatsproduct into market |  |  |  |  |  | an |
|  |  |  | Customer IT system/formats | internally |  |  |  |  |  |  | -Test software export abilities within first |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 |  | cannot receive project |  | X | X |  |  |  |  | R. Nelson |  |  | $18,500 | 70% | $12,950 |  |  |  | be |
|  |  |  |  | software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | deliverables |  |  |  |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  | -Reduction in total projected revenue |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -T |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | $294,950 |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Customer seeks to renegotiate | -Business case may not be as strong |  |  |  | de |
|  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |  |  | X |  |
|  |  |  |  |  | 2 |  |  |  |  |  |  |  |  | -Sales contribution from project may | X | v1 |  |  |
| © All rights reserved. The Managers Resource Handbook by MHX Global LLP |  |  |  |  |  |  |  | www.ManagersResourceHandbook.com |  |  |  | -S |
|  |  |  |  |  |  |  |  |  | price based on final design | need to be reduced |  |  |  |  |  |  |

|  |  |  |  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  |  | Project Financial Summary: |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Customer |  |  |  |  |  | Watkins Smith Corporation |  |  |  |  |  |  |  |  | Initial ROS: |  |  |  |  |  |  |  | 42% |  |  |  |
|  | Project |  |  |  |  |  |  | RF-30 Upgrade |  |  |  |  |  |  | Risk Category Definition |  |  | Current ROS: |  |  |  |  | 41% |  |  |  |
|  | Project Manager |  |  |  |  |  | Jessica Abrams |  |  |  |  |  |  |  |  |  | Estimated Investment: |  |  |  | $2.351M |  |  |  |
|  | Project Start Date |  |  |  |  | May 1, 2016 |  |  |  |  |  |  |  |  |  | Current Investment: |  |  |  | $1.595M |  |  |  |
|  | Planned Completion Date |  |  |  | October 1, 2018 |  | C |  |  |  | Cost |  |  | % Budget Spend |  |  |  |  | 68% |  |  |  |
|  | Estimated Completion Date |  |  |  | August 12, 2018 |  |  | S |  |  | Schedule |  |  | Estimated % Complete: |  |  |  |  | 75% |  |  |  |
|  | Reporting Date |  |  |  |  |  | December 3, 2017 |  |  | R |  | Resources |  |  | Initial Risk Value: |  |  |  | $119,643 |  |  |  |
|  | Project Status |  |  |  |  |  | On Track |  |  |  |  | O | Other |  |  | Current Risk Value: |  |  |  | $100,845 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Category |  |  |  |  |  |  |  |  |  |  |  | Risk Values |  |  |  |  |  |  |  |  |
|  | Number |  |  | Risk Description |  | Impact of Risk |  | C | S | R | O |  | Mitigation Strategy |  | Risk Owner | Total Risk | Probability of | Predicted |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin |  |  | $45,000 | 60% |  |  |  | $27,000 |  |  |  |
|  |  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | and Design Acceptance to sh | rten time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Customer |  |  |  |  |  | between payments | Watkins | Smith | Corporation |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughoutRF-30 Upgrade |  |  |  |  |  |  |  |  |  |  |  |  | Risk Cat |
|  |  |  |  |  |  |  |  | Project-Businsscase may not be as strong |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 |  | Customer seeks to renegotiate | -Sales contribution from project may | X |  |  | X | design evolution to show cost adjustments | G. DuBois |  |  | $33,050 | 50% |  |  |  | $16,525 |  |  |  |
|  |  |  | price based on final design | Project Manager |  |  |  |  |  | -Seek funding for changes to help absorbJessica Abrams |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | need to be reduced |  |  | Step | non-recurring costs impacts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Project-CstductionStartmay beDateneeded |  |  |  |  | May 1, 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 3: Categorize the Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Specialize software is needed | -Purchase of additional sof ware |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | Cost |
|  |  |  |  | Planned Completion Date |  |  |  | standard' software |  | October 1, 2018 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 |  | based on current project | necessary |  |  | X | X | X | -Charge customer for added cost of special | R. Nelson |  |  | $77,000 | 25% |  |  | S | $19,250 |  | Schedule |
|  |  |  |  |  |  |  |  | Estimated Completion Date |  |  |  | August 12, 2018 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | requirements |  |  | -Employees will need training |  |  |  |  | software under scope change clause. |  |  |  |  |  |  |  |  | categorize the |
|  |  |  |  |  | For Communication-Efficiecylossduetolarningpurposes,crve |  | and to help sort information, |  |
|  |  |  |  |  |  |  |  | Reporting Date |  |  |  |  |  |  |  |  | December 3, 2017 |  |  |  |  | R |  |  |  | Resources |
|  |  |  | Produce Validation Testing | -N ed to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Project Status |  |  |  |  |  |  |  |  |  | On Track |  |  |  |  |  |  |  |  |  |  | O | Other |
|  |  |  |  |  | risk. Some ways you can categorize: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Added cost of paying 3rd party |  |  |  |  | equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | must be performed by 3rd |  |  | X X |  | X |  |  |  | C. Jenkins |  | $113,000 | 20% |  |  |  | $22,600 |  |  |  |
|  |  |  |  | -Schedule impact due to logistics |  |  |  | -Work with customer to see what tests they |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | party |  |  |  |  |  |  |  |  |  |  |  | can perform on our behalf |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Recurring Cost in ex ess of business |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Category |  |  |
|  |  |  |  |  | Parts List exceeds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Product | • | Types | of Impact |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | estimated value by more than | -Reduced profit margin if price | X |  |  |  | -Re egotiate contract price with customer | M. Hart | Risk | $8,400 |  |  | 30% |  | C | S | $2,520 |  |  |  |
|  |  |  | 10% |  | • |  |  | Number | Risk | Description |  | Impact of |  |  |  |  |  |  |  |  | R O |  |  |
|  |  |  |  |  |  |  |  | remains unchanged |  |  |  |  |  | based on customer-driven changes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Product Families |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | • |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -Add custom |
|  |  |  |  |  |  | Customer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Customer IT system/formats | internally |  |  |  |  |  |  | -Test software export abilities within first |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | clause of co |
|  |  |  |  | -M y require specialize co | version |  |  |  |  | 90 days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 |  | cannot | receive project |  |  | X X |  |  |  |  |  | R. N lson |  |  | $18,500 |  |  | 70% |  |  |  | $12,950 |  |  |
|  |  |  |  |  | • |  |  |  | Customer delays release of end -Delay in investment | recovery |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Regional Location |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | deliverables |  |  | software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  | X | -Add milesto |
|  |  |  |  |  |  | 1 |  |  |  |  |  |  | evaluate import capabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | -Schedule impact if formatting issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | product into market |  | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |  |  |  | and Design A |
|  |  |  |  |  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) |  |  |  |  |  |  |  | between pa |
|  |  |  |  |  | • NOTE: Risks may have more than one category |  |  |  |  |  |  |  |  | $294,950 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) |  |  | $100,845 |  |  |  |
| © All rights reserved. The Managers Resource Handbook by MHX Global LLP |  |  |  | -Reduction in total projectedwww.ManagersResourceHandbookrevenue |  |  | .com | v1 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -Track detai |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |  |  | Project Information |  |  |  |  |  |  |  |  |  |  |  | Project Financial Summary: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Customer |  |  |  |  |  | Watkins Smith Corporation |  |  |  |  |  |  |  |  |  | Initial ROS: |  |  |  | 42% |  |  |
|  |  |  | Project |  |  |  |  |  |  |  | RF-30 Upgrade |  |  |  |  | Risk Category Definition |  | Current ROS: |  |  |  | 41% |  |  |
|  |  |  | Project Manager |  |  |  |  |  | Jessica Abrams |  |  |  |  |  |  |  |  |  | Estimated Investment: |  |  | $2.351M |  |  |
|  |  |  | Project Start Date |  |  | May 1, 2016 |  |  |  |  |  |  |  |  |  | Current Investment: |  |  | $1.595M |  |  |
|  |  |  | Planned Completion Date |  |  | October 1, 2018 | C |  |  |  | Cost |  |  |  |  | % Budget Spend |  |  |  | 68% |  |  |
|  |  |  | Estimated Completion Date |  | August 12, 2018 |  | S |  |  | Schedule |  |  |  |  | Estimated % Complete: |  |  |  | 75% |  |  |
|  |  |  | Reporting Date |  |  |  |  |  | December 3, 2017 |  |  | R |  | Resources |  |  |  |  | Initial Risk Value: |  | $119,643 |  |  |
|  |  |  | Project Status |  |  |  |  |  | On Track |  |  |  | O | Other |  |  |  |  | Current Risk Value: |  | $100,845 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Category |  |  |  |  |  |  |  |  |  | Risk Values |  |  |  |  |  |
|  |  |  | Number |  |  | Risk Description |  | Impact of Risk | C | S | R | O | Mitigation Strategy |  | Risk Owner |  | Total Risk | Probability of |  | Predicted |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence |  | Risk Value |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  | Project | Financial | Summary: |  |  |  |  |  |
| orporation |  | 1 |  |  |  |  |  |  |  |  |  | X |  | X | clause of contract |  |  |  | ROS:T.Franklin |  |  | $45,000 | 60% |  | $27,000 |  | 42% |
|  |  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | -Add milestone payments for InitialInitialConcept |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | product into market | -Reduced Sales next year |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |  |  |  |  |  |  |  |
| rade |  |  |  |  |  |  |  |  | Risk | Category Definition |  |  |  |  |  |  | ROS: |  |  |  |  |  |  |  |  | 41% |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | between payments |  | Current |  |  |  |  |  |  |  |  |  |  |  |
| rams |  |  |  |  |  |  |  |  |  | -Reduction in total projected revenue |  |  |  |  |  |  |  | Estimated |  | Investment: |  |  |  |  |  |  | $2.351M |
| 016 |  |  |  |  |  |  |  |  |  | -Business case may not be as strong |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |  |  |  |  |  | $1.595M |
|  |  |  |  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | price basedSteponfinaldesign4: | Define Mitigation |  |  |  |  |  |  |  | Current Investment: |  |  |  |  |  |  |  |
|  |  |  | 2 |  |  |  | X |  |  | Strategies-Seekfundingfor changes to help absorb |  | G. DuBois |  |  | $33,050 | 50% |  | $16,525 |  |  |
|  |  |  |  |  |  |  |  |  |  | -Sales co tribution from project may |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2018 |  |  | C |  |  |  | Cost | need to be reduced |  |  |  |  | non-recurring costs impacts % Budget Spend |  |  |  |  |  |  |  |  | 68% |
|  |  |  |  |  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2018 | • |  |  | S |  |  |  | Schedule |  |  |  |  |  |  |  |  |  | Estimated % Complete: |  |  |  |  |  | 75% |
|  |  | WhatSpecanilizesoftwareyouis neededdo | -Purchase of additio al software |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |  |  |  |  |  |  |  |
| 3, 2017 |  |  | to influence the |  | outcomestandard'softwareofthe risks, |  |  |  |  |  |  |  |  |  | $119,643 |
|  |  |  |  |  |  | R | Resources |  |  |  |  |  |  |  |  | Initial Risk Value: |  |  |  |  |  |  |  |
|  |  |  | 3 |  | based on current project | n cessary | X | X | X | -Charge customer for added cost of special |  | R. Nelson |  | $77,000 | 25% |  | $19,250 |  |  |
| ck |  |  | or mitigateOtheirOther impact?-Efficiencylossdue to learning curve |  |  |  |  |  |  |  | Current Risk Value: |  |  |  |  |  |  | $100,845 |
|  |  |  |  |  | requirements |  | -Em loyees will need training |  |  |  |  | software under scope change clause. |  |  |  |  |  |  |  |  |  |  |  |
|  | • What can you do to protect the project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Produce Validati | n Testing | -Need to iden ify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | -Added cost of paying 3rd party |  |  |  |  | equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 4must be performed | by 3rd |  | X X |  | X |  |  |  |  |  | C. Jenkins |  | $113,000 | 20% | $22,600 |  |  |
|  |  |  |  | Category |  |  |  | -Schedule impact due to logistics |  |  |  |  | -Work with customer |  | to see what tests they |  |  |  |  | Risk Values |  |  |  |  |  |
|  |  |  |  |  | party |  |  |  |  |  |  |  |  |  |  | can perform on | our |  | behalf |  | Total Risk |  | Probability |  | of |  | Predicted |
| Risk |  |  |  |  | C S | R O |  | -Recurring Cost in excess of business |  |  |  |  |  | Risk Owner |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | exceeds | case | Mitigation Strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Product Parts List |  |  |  |  |  |  |  | -Negotiate component costs with suppliers |  | Value |  |  | Occurrence |  |  | Risk Value |
|  |  |  | 5 | estimated value by more than | -Reduced profit margin if price | X |  |  | -Renegotiate contract price with customer |  | M. Hart |  | $8,400 | 30% |  |  | $2,520 |  |  |
|  |  |  |  |  | 10% |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | remains unchanged |  |  |  |  | based on customer-driven changes. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | clause of contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| recovery |  |  |  |  |  |  |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Customer IT system/formats | internally |  |  |  |  | -Test software export abilities within first |  | $45,000 | 60% |  |  |  |  | $27,000 |
| ear |  |  | 6 |  | X | X | -Add milestone-Mayrequire spaymentsecializecoversionfor Initial Concept90days | T. Franklin |  |  |  |  | $12,950 |  |  |
|  |  |  |  |  | cannot receive project | software | X X |  |  | -Have customer provide list of formats to |  | R. Nelson |  | $18,500 | 70% |  |  |  |  |
|  |  |  |  |  | deliverables | and Design Acceptance to shorten time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | between payments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ojected revenue |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) |  | $294,950 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) |  | $100,845 |  |  |
|  |  |  |  |  |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  | www.ManagersResourceHandbook.com | v1 |
|  | © All ri hts reserved. The Managers Resource Handbook by MHX Global LLP |  |  |  |  |  |  |  |  |  |
| ot be as strong |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |  | Project Information |  |  |  |  |  |  |  |  | Project Financial Summary: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer |  | Watkins Smith Corporation |  |  |  |  |  | Initial ROS: |  | 42% |
| Project |  | RF-30 Upgrade |  |  |  |  |  | Risk Category Definition | Current ROS: |  | 41% |
| Project Manager | Jessica Abrams |  |  |  |  |  |  | Estimated Investment: |  | $2.351M |
| Project Start Date | May 1, 2016 |  |  |  |  |  |  | Current Investment: |  | $1.595M |
| Planned Completion Date | October 1, 2018 |  | C |  |  |  | Cost | % Budget Spend |  | 68% |
| Estimated Completion Date | August 12, 2018 |  |  | S |  |  | Schedule | Estimated % Complete: |  | 75% |
| Reporting Date | December 3, 2017 |  |  |  | R |  | Resources | Initial Risk Value: |  | $119,643 |
| Project Status | On Track |  |  |  |  | O | Other | Current Risk Value: |  | $100,845 |
|  |  |  |  |  |  | Category |  |  |  | Risk Values |  |
| Number |  | Risk Description | Impact of Risk |  | C | S | R | O | Mitigation Strategy | Risk Owner | Total Risk | Probability of | Predicted |
|  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |
|  |  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |
|  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |
| 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |
|  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | between payments |  |  |  |  |
|  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |
|  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |
|  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |
| 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | -Seek funding for changes to help absorb | G. DuBois | $33,050 | 50% | $16,525 |
|  |  |  | need to be reduced |  |  |  |  |  | non-recurring costs impacts |  |  |  |  |
|  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |
|  |  |  | -Purchase of additional software |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |
|  |  | Specialize software is needed |  |  |  |  |  | standard' software |  |  |  |  |
|  |  |  | necessary |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  | based on current project |  |  |  | X | X | X |  | -Charge customer for added cost of special | R. Nelson | $77,000 | 25% | $19,250 |
|  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |  |
|  |  | Step 5: |  | Owner |  |  |  |  |  |
|  |  |  | Identify- | the Risk |  | software under scope change clause. |  |  |  |  |
|  |  | requirements | Efficiency loss due to learning curve |  |  |  |  |  |  |  |  |  |
|  |  | Produce Validation Testing | -Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |
|  |  |  | -Added cost of paying 3rd party |  |  |  |  | equipment |  |  |  |  |
| 4 |  | must be performed by 3rd |  | X | X |  | X |  | C. Jenkins | $113,000 | 20% | $22,600 |
|  |  |  | -Schedule impact due to logistics |  |  |  |  | -Work wi h custom r to see what tests they |  |  |  |  |
| Ownership is a form of accountability.canListperformtheonourbehalf |  |  |  |  |
|  |  | party |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Product Parts List exceeds | - Recurring Cost | excess of business |  |  |  |  | -Negotiate component costs with suppliers |  |  |  |  |
|  |  |  | caseindividuals |  |  |  |  |  |  |  |  |  |  |
| name(s) of those |  |  | who are primarily |  |  |  |  |
| 5 |  | estimated value by more than | -Reduced profit margin if price | X |  |  |  | -Renegotiate contract price with customer | M. Hart | $8,400 | 30% | $2,520 |
| responsible for managing and mitigating the |  |  |  |  |
|  |  | 10% | remai s uncha | ged |  |  |  |  |  | based on customer-driven changes. |  |  |  |  |
|  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |
| risk item. | -Will need to convert formats |  |  |  |  |  |  |  |  |  |
|  |  | Customer IT system/formats | internally |  |  |  |  |  |  | -Test software export abilities within first |  |  |  |  |
|  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  |  |  |
| 6 |  | cannot receive project |  | X | X |  |  |  | R. Nelson | $18,500 | 70% | $12,950 |
|  |  |  | software |  |  |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |
|  |  | deliverables |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |
|  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | $294,950 |
|  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  |  |  |  |  | Project Information |  |  |  |  |  |  |  | Project Financial Summary: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Customer |  | Watkins Smith Corporation |  |  |  |  |  |  | Initial ROS: |  | 42% |  |
|  | Project |  |  |  | RF-30 Upgrade |  |  |  |  | Risk Category Definition | Current ROS: |  | 41% |  |
|  | Project Manager |  | Jessica Abrams |  |  |  |  |  |  | Estimated Investment: |  | $2.351M |  |
|  | Project Start Date |  | May 1, 2016 |  |  |  |  |  |  | Current Investment: |  | $1.595M |  |
|  | Planned Completion Date |  | October 1, 2018 | C |  |  |  | Cost |  | % Budget Spend |  | 68% |  |
|  | Estimated Completion Date |  | August 12, 2018 |  | S |  |  | Schedule |  | Estimated % Complete: |  | 75% |  |
|  | Reporting Date |  | December 3, 2017 |  |  | R |  | Resources |  | Initial Risk Value: |  | $119,643 |  |
|  | Project Status |  | On Track |  |  |  | O | Other |  | Current Risk Value: |  | $100,845 |  |
|  |  |  |  |  |  |  | Category |  |  |  |  | Risk Values |  |  |
|  | Number |  | Risk Description | Impact of Risk | C | S | R | O |  | Mitigation Strategy | Risk Owner | Total Risk | Probability of | Predicted |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |  |
|  |  |  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |  |
|  |  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |  |
|  |  | 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |  |
|  |  |  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | between payments |  |  |  |  |  |
|  |  |  |  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |  |
|  |  |  |  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |  |
|  |  | 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | -Seek funding for changes to help absorb | G. DuBois | $33,050 | 50% | $16,525 |  |
|  |  |  |  |  |  | need to be reduced |  |  |  |  | non-recurring costs impacts |  |  |  |  |  |
|  |  |  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | -Purchase of additional software |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |  |
|  |  |  |  | Specialize software is needed |  |  |  |  |  | standard' software |  |  |  |  |  |
|  |  |  |  |  | necessary |  |  |  |  |  |  |  |  |  |  |
|  |  | 3 |  | based on current project |  | X | X | X |  | -Charge customer for added cost of special | R. Nelson | $77,000 | 25% | $19,250 |  |
|  |  |  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Step |  |  | Total | Value of Each Risk |  |  |  |  |  |
|  |  |  |  | requirements |  | 6: Quantify the |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | -Efficiency loss due o learning curve |  |  |  |  | softw re | nd r sc pe change lause. |  |  |  |  |  |
|  |  |  |  | Produce Validation Testing | -Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |  |
|  |  |  |  |  | -Added cost of paying 3rd party |  |  |  |  | equipment |  |  |  |  |  |  |
|  |  | 4 | must be performed by 3rd |  | X | X |  | X |  |  | C. Jenkins | $113,000 | 20% | $22,600 |  |
|  |  |  |  | -Schedule impact due to ogistics |  |  |  |  | -Work with customer to see hat tests they |  |  |  |  |  |
|  | Calculate the total financial value |  | of | the risk, if it were to occur. This |  |  |  |
|  |  |  |  | party |  |  |  |  |  |  | can perform on our behalf |  |  |  |  |  |
|  |  |  |  |  |  | -Recurring Cost in excess of business | a new project. |  |  |  |  |  |
|  | is a similar exercise to estimating |  |  |  |  |  |  |
|  |  |  |  | Product Parts List exceeds | case |  |  |  |  | -Negotiate | mponent costs with suppliers |  |  |  |  |  |
|  |  | 5estimated value by more than | -Reduced profit margin if price | X |  |  |  | -Renegotiate contract price with customer | M. Hart | $8,400 | 30% | $2,520 |  |
|  |  |  | 10% |  | remains unchanged |  |  |  |  | based on customer-driven changes. |  |  |  |  |  |
|  |  |  |  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |  |
|  | • How much more time would | be needed? |  |  |  |  |  |
|  |  |  |  |  |  | -Will need to conv rt formats |  |  |  |  |  |  |  |  |  |  |  |
|  | • |  |  | Customer IT system/formats | internally |  |  |  |  | -Test software export abilities within first |  |  |  |  |  |
|  |  |  |  |  |  | required?-Havecustomer provide list of formats to |  |  |  |  |  |
|  |  |  | How many hourssoftware of effort are |  |  |  |  |  |  |
|  |  | 6 |  | cann t receive project | -May require sp cialize conversion | X | X |  |  | 90 days |  | R. Nelson | $18,500 | 70% | $12,950 |  |
|  |  |  |  | deliverables |  | -Schedu e impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |  |
|  | • What is the Hourly Rate? |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |  |  |
|  | • What additional expenses (travel, materials, supplies) | are there? |  | $294,950 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Tot l Pot n ial Risk (Unweighted) |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |  |
| © All rights reserved. The Managers Resource Handbook by MHX Global LLP |  |  |  |  | www.ManagersResourceHandbook.com v1 |

Step 6 (Continued): Keep The

Assumptions Nearby

Your assumptions may need to change as time goes by. Include these values in

your template off to the side, or on another tab of the spreadsheet. The “Total” value corresponds to the “Total Risk Value” in the Risk Assessment

Matrix. Things to include:

- Time (Hours)

- Hourly Rates

- Travel Costs

- Additional expenses (software, materials, supplies)

Cost Calculations

| Number | Hours | Rate | Travel | Other | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | ($/Hour) | ($2000/Trip) | Expenses |  |
| 1 | 300 | $30 | $16,000 | $20,000 | $45,000 |

| 2 | 490 | $45 | $6,000 | $5,000 | $33,050 |
| --- | --- | --- | --- | --- | --- |

| 3 | 600 | $45 | $0 | $50,000 | $77,000 |
| --- | --- | --- | --- | --- | --- |

| 4 | 500 | $30 | $8,000 | $90,000 | $113,000 |
| --- | --- | --- | --- | --- | --- |

| 5 | 240 | $35 | $0 | $0 | $8,400 |
| --- | --- | --- | --- | --- | --- |

| 6 | 100 | $35 | $0 | $15,000 | $18,500 |
| --- | --- | --- | --- | --- | --- |

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  |  | Project Information |  |  |  |  |  |  |  | Project Financial Summary: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer |  | Watkins Smith Corporation |  |  |  |  |  |  | Initial ROS: |  | 42% |
| Project |  |  | RF-30 Upgrade |  |  |  |  | Risk Category Definition | Current ROS: |  | 41% |
| Project Manager |  | Jessica Abrams |  |  |  |  |  |  | Estimated Investment: |  | $2.351M |
| Project Start Date |  | May 1, 2016 |  |  |  |  |  |  | Current Investment: |  | $1.595M |
| Planned Completion Date |  | October 1, 2018 | C |  |  |  | Cost |  | % Budget Spend |  | 68% |
| Estimated Completion Date |  | August 12, 2018 |  | S |  |  | Schedule |  | Estimated % Complete: |  | 75% |
| Reporting Date |  | December 3, 2017 |  |  | R |  | Resources |  | Initial Risk Value: |  | $119,643 |
| Project Status |  | On Track |  |  |  | O | Other |  | Current Risk Value: |  | $100,845 |
|  |  |  |  |  | Category |  |  |  |  | Risk Values |  |
| Number |  | Risk Description |  | Impact of Risk | C | S | R | O | Mitigation Strategy | Risk Owner | Total Risk | Probability of | Predicted |
|  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |
|  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |
|  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |
| 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |
|  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |
|  |  |  |  |  |  |  |  |  | between payments |  |  |  |  |
|  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |
|  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |
|  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |
| 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | -Seek funding for changes to help absorb | G. DuBois | $33,050 | 50% | $16,525 |
|  |  |  | need to be reduced |  |  |  |  | non-recurring costs impacts |  |  |  |  |
|  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |
|  |  |  | -Purchase of additional software |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |
|  |  | Specialize software is needed |  |  |  |  |  | standard' software |  |  |  |  |
|  |  |  | necessary |  |  |  |  |  |  |  |  |  |
| 3 |  | based on current project |  | X | X | X |  | -Charge customer for added cost of special | R. Nelson | $77,000 | 25% | $19,250 |
|  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |  |
|  |  | requirements |  |  |  |  |  | software under scope change clause. |  |  |  |  |
|  |  |  | -Efficiency loss due to learning curve |  |  |  |  |  |  |  |  |  |
|  | Step 7: Estimate- | Probability of |  |  | Occurrence |  |  |  |  |
|  |  | Produce Validation Testing | Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |
|  |  |  | -Added cost of paying 3rd party |  |  |  |  | equipment |  |  |  |  |  |
| 4 |  | must be performed by 3rd |  | X | X |  | X |  |  | C. Jenkins | $113,000 | 20% | $22,600 |
|  |  |  | -Schedule impact due to logistics |  |  |  |  | -Work with customer to see what tests they |  |  |  |  |
|  |  | party |  |  |  |  |  |  | can perform on our behalf |  |  |  |  |
| Estimate the probability that each |  |  | risk will |  |  |  |  |  |
|  |  |  | -Recurring Cost in excess of busin ss |  |  |  |  |  |  |  |  |  |  |
|  |  | Product Parts List exceeds | case |  |  |  |  |  | -Negotiate component costs with suppliers |  |  |  |  |
| occur. This estimate should be | revised over | M. Hart | $8,400 | 30% | $2,520 |
| 5 |  | estimated value by more than | -Reduc d profit margin if price | X |  |  |  | -Reneg tiate contract price with customer |  |  |  |  |
|  |  | 10% | remains unchanged |  |  |  |  | based on customer-driven changes. |  |  |  |  |
| time. If a risk becomes real, set | the probability |  |  |  |  |
|  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |  |
|  |  |  | -Will need to convert formats |  | as issues90days | and |  |  |  |  |
| to 100%. Reduce-Maytherequire specializeprobabilityconversion |  |  |  |  |  |  |
|  |  | Customer IT system/formats | internally |  |  |  |  | -Te t software export abilities within first |  |  |  |  |
| 6 |  | cannot receive project | software | X | X |  |  | -Have customer provide list of formats to | R. Nelson | $18,500 | 70% | $12,950 |
| risks are mitigated- | or eliminated. |  |  |  |  |  |  |  |  |  |
|  |  | deliver bles | Schedule impact f formatting issu s |  |  |  |  | evaluate import capabilities |  |  |  |  |
|  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | $294,950 |
|  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  |  |  | Project Information |  |  |  |  |  |  |  | Project Financial Summary: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Customer |  | Watkins Smith Corporation |  |  |  |  |  | Initial ROS: |  | 42% |
|  | Project |  | RF-30 Upgrade |  |  |  |  | Risk Category Definition | Current ROS: |  | 41% |
|  | Project Manager | Jessica Abrams |  |  |  |  |  | Estimated Investment: |  | $2.351M |
|  | Project Start Date | May 1, 2016 |  |  |  |  |  | Current Investment: |  | $1.595M |
|  | Planned Completion Date | October 1, 2018 | C |  |  |  | Cost | % Budget Spend |  | 68% |
|  | Estimated Completion Date | August 12, 2018 |  | S |  |  | Schedule | Estimated % Complete: |  | 75% |
|  | Reporting Date | December 3, 2017 |  |  | R |  | Resources | Initial Risk Value: |  | $119,643 |
|  | Project Status | On Track |  |  |  | O | Other | Current Risk Value: |  | $100,845 |
|  |  |  |  |  |  | Category |  |  |  | Risk Values |  |
|  | Number |  | Risk Description | Impact of Risk | C | S | R | O | Mitigation Strategy | Risk Owner | Total Risk | Probability of | Predicted |
|  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |
|  |  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |
|  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |
|  | 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |
|  |  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | between payments |  |  |  |  |
|  |  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |
|  |  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |
|  |  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |
|  | 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | -Seek funding for changes to help absorb | G. DuBois | $33,050 | 50% | $16,525 |
|  |  |  |  | need to be reduced |  |  |  |  | non-recurring costs impacts |  |  |  |  |
|  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |
|  | Step 8: Compute the Expected |  | Value-Negotiate with customer to use 'industry |  |  |  |  |
|  |  |  | Specialize software is needed | -Purchase of additional software |  |  |  |  | standard' software |  |  |  |  |
|  |  |  |  | necessary |  |  |  |  |  |  |  |  |  |  |
|  | 3 |  | based on current project |  |  | X | X | X | -Charge customer for added cost of special | R. Nelson | $77,000 | 25% | $19,250 |
|  |  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |
|  |  |  | requirements |  | 6) |  |  |  | software under scope change clause. |  |  |  |  |
|  |  |  |  | -Efficiency loss d to learning curve |  |  |  |  |  |  |  |  |  |
|  | Multiply the Total Risk Value (Step |  | by the |  |  |  |  |
|  |  |  | Produce Validation Testing | -Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |
|  |  |  |  | -Add d cost of paying 3rd arty |  |  |  |  | equipment |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | C. Jenkins | $113,000 | 20% | $22,600 |
|  | Probability4mustbeperformedof Occurrenceby3rd | (Step 7) toX | XestablishX |  |  |  |  |
|  |  |  | party | -Schedule impact due to logistics |  |  |  |  | -Work with customer to see what tests they |  |  |  |  |
| the Predicted Risk Value. | This is often | can perform on our behalf |  |  |  |  |
|  |  |  |  | -Recurring Cost in excess of business |  |  |  |  |  |  |  |  |  |
|  |  |  | Pro uct Parts List exceeds | case |  |  |  |  |  | -Negotiate component costs with suppliers |  |  |  |  |
| referred to as an expected value or a |  |  |  | -Renegotiate contract price with customer | M. Hart | $8,400 | 30% | $2,520 |
| 5 |  | estimated value by more than | -Reduced profit margin if price | X |  |  |  |  |  |  |  |  |
|  |  |  | 10% | remains unchanged |  |  |  |  | based on customer-driven changes. |  |  |  |  |
| weighted value. | -Potential loss on effort |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |
|  |  |  | Customer IT system/formats | internally |  |  |  |  |  | -Test software export abilities within first |  |  |  |  |
|  |  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  |  |  |
| 6 |  | cannot receive project |  | X | X |  |  |  | R. Nelson | $18,500 | 70% | $12,950 |
|  |  |  | software |  |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |
|  |  |  | deliverables |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |
|  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | $294,950 |
|  |  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  |  |  | Project Information |  |  |  |  |  |  | Project Financial Summary: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Customer |  | Watkins Smith Corporation |  |  |  |  |  | Initial ROS: |  | 42% |
|  | Project |  | RF-30 Upgrade |  |  |  |  | Risk Category Definition | Current ROS: |  | 41% |
|  | Project Manager | Jessica Abrams |  |  |  |  |  | Estimated Investment: |  | $2.351M |
|  | Project Start Date | May 1, 2016 |  |  |  |  |  | Current Investment: |  | $1.595M |
|  | Planned Completion Date | October 1, 2018 | C |  |  |  | Cost | % Budget Spend |  | 68% |
|  | Estimated Completion Date | August 12, 2018 |  | S |  |  | Schedule | Estimated % Complete: |  | 75% |
|  | Reporting Date | December 3, 2017 |  |  | R |  | Resources | Initial Risk Value: |  | $119,643 |
|  | Project Status | On Track |  |  |  | O | Other | Current Risk Value: |  | $100,845 |
|  |  |  |  |  | Category |  |  |  | Risk Values |  |
|  | Number |  | Risk Description | Impact of Risk | C | S | R | O | Mitigation Strategy | Risk Owner | Total Risk | Probability of | Predicted |
|  |  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |
|  |  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |
|  |  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |
|  | 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |
|  |  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |
|  |  |  |  |  |  |  |  |  | between payments |  |  |  |  |
|  |  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |
|  |  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |
|  |  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |
|  | 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | -Seek funding for changes to help absorb | G. DuBois | $33,050 | 50% | $16,525 |
|  |  |  |  | need to be reduced |  |  |  |  | non-recurring costs impacts |  |  |  |  |
|  |  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |
|  |  |  | Step 9: Sum the Total |  | Project-NegotiateRiskwithcustomer to use 'industry |  |  |  |  |
|  |  |  | Specialize software is needed | -Purchase of additional software |  |  |  |  | standard' software |  |  |  |  |
|  |  |  |  | necessary |  |  |  |  |  |  |  |  |  |
|  | 3 |  | based on current project |  | X | X | X | -Charge customer for added cost of special | R. Nelson | $77,000 | 25% | $19,250 |
|  |  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |
| To |  |  | requirements |  |  |  |  |  | software under scope change clause. |  |  |  |  |
|  |  |  |  | -Efficiency l ss due to learn ng curve |  |  |  |  |  |  |  |  |  |
|  | calculate the Total Project Risk, | sum all the values you |  |  |  |  |
|  |  |  | Produce Val dation Testing | -Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |
|  |  |  |  | -Added cost of paying 3rd rty |  |  |  |  | equipment |  |  |  |  |
|  |  |  |  |  | X X |  | X |  | C. Jenkins | $113,000 | 20% | $22,600 |
|  | calculated4mustbeperformedinStepby3rd 8. In this example: |  |  |  | -Work with customer to see what tests they |  |  |  |  |
|  |  |  | party | -Schedule impact due to logistics |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | can perform on our behalf |  |  |  |  |
|  |  |  |  | -Recurring Cost in excess of business |  |  |  |  |  |  |  |  |  |
|  |  |  | Product Parts List exceeds | case |  |  |  |  | -Nego iate component costs with suppliers |  |  |  |  |
| From Step 6: Total Potential Risk | (Unweighted): ~$295k | M. Hart | $8,400 | 30% | $2,520 |
| 5 |  | estimated value by more than | -Reduced profit margin if price | X |  |  | -Renegotiate contract price with customer |  |  |  |  |
|  |  |  | 10% | remains unch ng |  |  |  |  | based on customer-driven changes. |  |  |  |  |
| From Step 8: Total Estimated-Potentiallossoneffort Impact | (Weighted): ~101k |  |  |  |  |
|  |  |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |
|  |  |  | Customer IT system/formats | internally |  |  |  |  | -Test software export abilities within first |  |  |  |  |
|  |  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  |  |  |
| 6 |  | cannot receive project |  | X X |  |  |  | R. Nelson | $18,500 | 70% | $12,950 |
|  |  |  | software |  |  |  | -Have customer provide list of formats to |  |  |  |  |
|  |  |  | deliverables |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |
|  |  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Total Potential Risk (Unweighted) | $294,950 |
|  |  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

Final Tips for Creating a Risk Assessment Matrix

- Create the Matrix Before Project Starts To Fully Understand Risks

- Factor Costs Into Business Case / Financial Models

- Reevaluate Often with Project Team

–Have Any Risks Become Real?

–Are Risks Still Valid?

–Are Probabilities Still Accurate?

–Any New Items to Add?

- Change Probabilities and Assumptions As Needed to Continuously Understand Financial Values

For Step-By-Step Instructions and to Download The Template:

http://www.managersresourcehandbook.com/project-risk-matrix-template/

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

Final Tips for Creating a Risk Assessment Matrix

1.	Create it Before Project Starts To Fully Understand Risks

2.	Factor Costs Into Business Case / Financial Models

3.	Reevaluate Often with Project Team

–	Have Any Risks Become Real?

–	Are Risks Still Valid?

–	Are Probabilities Still Accurate?

–	Any New Items to Add?

Step 10: Review & Update Matrix Over Time

- Change Probabilities and AssumptionsReview AswithNeededProjectTeamtoCoftenntinuoustokeep ahead

Understand Financial Values	of changes in the project!

For Step-By-Step Instructions and to Download The Template:

http://www.managersresourcehandbook.com/project-risk-matrix-template/

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1

|  |  | Project Information |  |  |  |  |  |  | Project Financial Summary: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer |  | Watkins Smith Corporation |  |  |  |  |  | Initial ROS: |  | 42% |
| Project |  | RF-30 Upgrade |  |  |  |  | Risk Category Definition | Current ROS: |  | 41% |
| Project Manager | Jessica Abrams |  |  |  |  |  | Estimated Investment: |  | $2.351M |
| Project Start Date | May 1, 2016 |  |  |  |  |  | Current Investment: |  | $1.595M |
| Planned Completion Date | October 1, 2018 | C |  |  |  | Cost | % Budget Spend |  | 68% |
| Estimated Completion Date | August 12, 2018 |  | S |  |  | Schedule | Estimated % Complete: |  | 75% |
| Reporting Date | December 3, 2017 |  |  | R |  | Resources | Initial Risk Value: |  | $119,643 |
| Project Status | On Track |  |  |  | O | Other | Current Risk Value: |  | $100,845 |
|  |  |  |  | Category |  |  |  | Risk Values |  |
| Number |  | Risk Description | Impact of Risk | C | S | R | O | Mitigation Strategy | Risk Owner | Total Risk | Probability of | Predicted |
|  |  |  |  |  |  |  |  |  |  | Value | Occurrence | Risk Value |
|  |  |  |  |  |  |  |  | -Add customer-driven delays to penalties |  |  |  |  |
|  |  | Customer delays release of end | -Delay in investment recovery |  |  |  |  | clause of contract |  |  |  |  |
| 1 |  |  |  |  | X |  | X | -Add milestone payments for Initial Concept | T. Franklin | $45,000 | 60% | $27,000 |
|  |  | product into market | -Reduced Sales next year |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | and Design Acceptance to shorten time |  |  |  |  |
|  |  |  |  |  |  |  |  | between payments |  |  |  |  |
|  |  |  | -Reduction in total projected revenue |  |  |  |  | -Track detailed cost changes throughout |  |  |  |  |
|  |  |  | -Business case may not be as strong |  |  |  |  |  |  |  |  |  |
|  |  | Customer seeks to renegotiate |  |  |  |  |  | design evolution to show cost adjustments |  |  |  |  |
| 2 |  | price based on final design | -Sales contribution from project may | X |  |  | X | -Seek funding for changes to help absorb | G. DuBois | $33,050 | 50% | $16,525 |
|  |  |  | need to be reduced |  |  |  |  | non-recurring costs impacts |  |  |  |  |
|  |  |  | -Cost reduction may be needed |  |  |  |  |  |  |  |  |  |
|  |  |  | -Purchase of additional software |  |  |  |  | -Negotiate with customer to use 'industry |  |  |  |  |
|  |  | Specialize software is needed |  |  |  |  |  | standard' software |  |  |  |  |
|  |  |  | necessary |  |  |  |  |  |  |  |  |  |
| 3 |  | based on current project |  | X | X | X |  | -Charge customer for added cost of special | R. Nelson | $77,000 | 25% | $19,250 |
|  |  |  | -Employees will need training |  |  |  |  |  |  |  |  |  |
|  |  | requirements |  |  |  |  |  | software under scope change clause. |  |  |  |  |
|  |  |  | -Efficiency loss due to learning curve |  |  |  |  |  |  |  |  |  |
|  |  | Produce Validation Testing | -Need to identify potential suppliers |  |  |  |  | -Setup test program to use only internal |  |  |  |  |
|  |  |  | -Added cost of paying 3rd party |  |  |  |  | equipment |  |  |  |  |
| 4 |  | must be performed by 3rd |  | X | X |  | X |  | C. Jenkins | $113,000 | 20% | $22,600 |
|  |  |  | -Schedule impact due to logistics |  |  |  |  | -Work with customer to see what tests they |  |  |  |  |
|  |  | party |  |  |  |  |  | can perform on our behalf |  |  |  |  |
|  |  |  | -Recurring Cost in excess of business |  |  |  |  |  |  |  |  |  |
|  |  | Product Parts List exceeds | case |  |  |  |  | -Negotiate component costs with suppliers |  |  |  |  |
| 5 |  | estimated value by more than | -Reduced profit margin if price | X |  |  |  | -Renegotiate contract price with customer | M. Hart | $8,400 | 30% | $2,520 |
|  |  | 10% | remains unchanged |  |  |  |  | based on customer-driven changes. |  |  |  |  |
|  |  |  | -Potential loss on effort |  |  |  |  |  |  |  |  |  |
|  |  |  | -Will need to convert formats |  |  |  |  |  |  |  |  |  |
|  |  | Customer IT system/formats | internally |  |  |  |  | -Test software export abilities within first |  |  |  |  |
|  |  |  | -May require specialize conversion |  |  |  |  | 90 days |  |  |  |  |
| 6 |  | cannot receive project |  | X | X |  |  |  | R. Nelson | $18,500 | 70% | $12,950 |
|  |  |  | software |  |  |  |  | -Have customer provide list of formats to |  |  |  |  |
|  |  | deliverables |  |  |  |  |  |  |  |  |  |  |
|  |  |  | -Schedule impact if formatting issues |  |  |  |  | evaluate import capabilities |  |  |  |  |
|  |  |  | cannot be resolved |  |  |  |  |  |  |  |  |  |
| © All rights reserved. The Managers Resource Handbook by MHX Global LLP |  | Total Potential Risk (Unweighted) | $294,950 |
|  |  | www.ManagersResourc Handbook.com | v1 |
|  |  |  |  |  |  |  |  |  | Total Estimated Impact (Weighted) | $100,845 |

The Manager's Resource Handbook is an online source of tools, templates

and articles for managers and leaders in today’s business environment. Our

mission is the help managers and businesses succeed through the benefit of our experience.

You can contact us at:

http://www.ManagersResourceHandbook.com

Like us on Facebook!

Follow us on Twitter!

© All rights reserved. The Managers Resource Handbook by MHX Global LLP	www.ManagersResourceHandbook.com	v1