|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |
|  | **COMMERCIAL CONSTRUCTION SCHEDULE** | | | |  | **SCHEDULE VERSION** | |  |
|  |  | V2.1 (17/02/2022) | |  |
|  |  | **PAGE** | |  |
|  |  | #1 | |  |
|  |  |  |  |  |  |  |  |  |
|  | **PROJECT TITLE** | |  | **PROJECT MANAGER** | | | |  |
|  | COMMERCIAL CONSTRUCTION XPRESS | |  | JOHN DOE | | | |  |
|  | **LOCATION** | |  | **CLIENT** | | | |  |
|  | 35 MAIN BUILDING AVENUE, ROSEVELT | |  | BUILDING INVESTMENT HOLDING LTD | | | |  |
|  |  |  |  |  |  |  |  |  |
|  | **TASK NAME** | **STATUS** | **ASSIGNED TO** | | **START DATE** | **END DATE** | **DURATION** in days |  |
|  | **1.0 SITE PREPARATION** | Completed | Management | | 05/01 | 05/30 | 30 |  |
|  | 1.1 Implementation of drainage | Completed | Drainage LLC | | 05/01 | 05/08 | 8 |  |
|  | 1.2 Removal of vegetation | Completed | Machinery team | | 05/02 | 05/16 | 15 |  |
|  | 1.3 Inspection of structural lines | Completed | Engineering team | | 05/18 | 05/30 | 13 |  |
|  | **2.0 FOUNDATION** | Completed | Construction team 1 | | 06/01 | 06/10 | 10 |  |
|  | **3.0 FRAMING** | In Process | Construction team 2 | | 06/11 | 07/20 | 40 |  |
|  | **4.0 ROOFING, SIDING AND HVAC** | Pending | Construction team 3 | | 07/21 | 10/20 | 92 |  |
|  | 4.1 Roofing | Not Started | Construction team 3 | | 07/21 | 08/04 | 15 |  |
|  | 4.2 Siding | Not Started | Construction team 3 | | 07/21 | 09/10 | 52 |  |
|  | 4.3 HVAC | Not Started | Construction team 3 | | 09/10 | 10/20 | 41 |  |
|  | **5.0 INTERIOR** | Not Started | Construction team 4 | | 10/21 | 11/12 | 23 |  |
|  | 5.1 Hardwoods | Not Started | Construction team 4 | | 10/21 | 10/22 | 2 |  |
|  | 5.2 Tile | Not Started | Construction team 4 | | 10/22 | 10/25 | 4 |  |
|  | 5.3 Cabinets | Not Started | Construction team 4 | | 10/22 | 10/28 | 7 |  |
|  | 5.4 Plumbing -hang sinks | Not Started | Construction team 4 | | 10/26 | 11/01 | 7 |  |
|  | 5.5 Stone Counters | Not Started | Construction team 4 | | 11/01 | 11/07 | 7 |  |
|  | 5.6 Schedule Buffer | Not Started | Construction team 4 | | 11/01 | 11/08 | 8 |  |
|  | 5.7 Decks | Not Started | Construction team 4 | | 11/02 | 11/05 | 4 |  |
|  | 5.8 Laundry/furnace room flooring | Not Started | Construction team 4 | | 11/05 | 11/12 | 8 |  |
|  | **6.0 EXTERIOR** | Not Started | Special team 1 | | 11/12 | 12/15 | 34 |  |
|  | **7.0 UTILITIES** | Not Started | Electrical team | | 11/12 | 12/18 | 37 |  |
|  | **8.0 LANDSCAPING** | Not Started | Landscaping team | | 01/05 | 01/28 | 24 |  |
|  | **9.0 LOREM IPSUM** | Not Started | Person 1 | | 01/10 | 02/02 | 24 |  |
|  | 9.1 Subtask description | Not Started | Person 1 | | 01/10 | 01/28 | 19 |  |
|  | 9.2 Subtask description | Not Started | Person 1 | | 01/29 | 02/02 | 5 |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  | |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  | Global Building Corporation LLC ▪201 Norton Street, 23434 Belville ▪ (555) 1241 254541▪gbconlinewebsite.com | | | | | | |  |
|  |  |  |  |  | [© TemplateLab.com](https://templatelab.com/) | | |  |