|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|   |  |   |   |   |   |   |   |   |
|   | **COMMERCIAL CONSTRUCTIONSCHEDULE** |   | **SCHEDULE VERSION** |   |
|   |   | V2.1 (17/02/2022) |   |
|   |   | **PAGE** |   |
|   |   | #1 |   |
|   |  |   |   |   |   |   |   |   |
|   | **PROJECT TITLE** |  | **PROJECT MANAGER** |   |
|   | COMMERCIAL CONSTRUCTION XPRESS |   | JOHN DOE |   |
|   | **LOCATION** |  | **CLIENT** |   |
|   | 35 MAIN BUILDING AVENUE, ROSEVELT |   | BUILDING INVESTMENT HOLDING LTD |   |
|   |   |   |   |   |   |   |   |   |
|   | **TASK NAME** | **STATUS** | **ASSIGNED TO** | **START DATE** | **END DATE** | **DURATION** in days |   |
|   | **1.0 SITE PREPARATION** | Completed | Management | 05/01 | 05/30 | 30 |   |
|   |  1.1 Implementation of drainage  | Completed | Drainage LLC | 05/01 | 05/08 | 8 |   |
|   |  1.2 Removal of vegetation | Completed | Machinery team | 05/02 | 05/16 | 15 |   |
|   |  1.3 Inspection of structural lines | Completed | Engineering team | 05/18 | 05/30 | 13 |   |
|   | **2.0 FOUNDATION** | Completed | Construction team 1 | 06/01 | 06/10 | 10 |   |
|   | **3.0 FRAMING** | In Process | Construction team 2 | 06/11 | 07/20 | 40 |   |
|   | **4.0 ROOFING, SIDING AND HVAC** | Pending | Construction team 3 | 07/21 | 10/20 | 92 |   |
|   |  4.1 Roofing | Not Started | Construction team 3 | 07/21 | 08/04 | 15 |   |
|   |  4.2 Siding | Not Started | Construction team 3 | 07/21 | 09/10 | 52 |   |
|   |  4.3 HVAC | Not Started | Construction team 3 | 09/10 | 10/20 | 41 |   |
|   | **5.0 INTERIOR** | Not Started | Construction team 4 | 10/21 | 11/12 | 23 |   |
|   |  5.1 Hardwoods | Not Started | Construction team 4 | 10/21 | 10/22 | 2 |   |
|   |  5.2 Tile | Not Started | Construction team 4 | 10/22 | 10/25 | 4 |   |
|   |  5.3 Cabinets | Not Started | Construction team 4 | 10/22 | 10/28 | 7 |   |
|   |  5.4 Plumbing -hang sinks | Not Started | Construction team 4 | 10/26 | 11/01 | 7 |   |
|   |  5.5 Stone Counters | Not Started | Construction team 4 | 11/01 | 11/07 | 7 |   |
|   |  5.6 Schedule Buffer | Not Started | Construction team 4 | 11/01 | 11/08 | 8 |   |
|   |  5.7 Decks | Not Started | Construction team 4 | 11/02 | 11/05 | 4 |   |
|   |  5.8 Laundry/furnace room flooring | Not Started | Construction team 4 | 11/05 | 11/12 | 8 |   |
|   | **6.0 EXTERIOR** | Not Started | Special team 1 | 11/12 | 12/15 | 34 |   |
|   | **7.0 UTILITIES** | Not Started | Electrical team | 11/12 | 12/18 | 37 |   |
|   | **8.0 LANDSCAPING** | Not Started | Landscaping team | 01/05 | 01/28 | 24 |   |
|   | **9.0 LOREM IPSUM** | Not Started | Person 1 | 01/10 | 02/02 | 24 |   |
|   |  9.1 Subtask description | Not Started | Person 1 | 01/10 | 01/28 | 19 |   |
|   |  9.2 Subtask description | Not Started | Person 1 | 01/29 | 02/02 | 5 |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |  |  |  |  |  |  |   |
|   |   |   |   |   |   |   |   |   |
|   | Global Building Corporation LLC ▪201 Norton Street, 23434 Belville ▪ (555) 1241 254541▪gbconlinewebsite.com |   |
|   |   |   |   |   |  [© TemplateLab.com](https://templatelab.com/)    |   |