## Kitchen Construction Schedule
TEAR OUT & DEMOLITION | ROUGH-IN WORK | PROFESSIONAL INSPECTION | FINISHING THE WALLS
Clear old walls | Adding square footage | Calling the city | Hang drywall
Move old cabinetry | Framing | Scheduling appointment | Tape drywall
Deinstall fixtures | Moving plumbing fixtures | The approval | Finish drywall
Hauling debris away |  |  | Add a coat of primer
01/04 - 04/04 | 05/04 - 09/04 | 10/04 - 14/04 | 15/04 - 19/04
INSTALL DOORS & WINDOWS | CABINETS AND PLUMBING FIXTURES | BRING IN NEW APPLIENCES | INSTALL NEW FLOORING
Install Doors (2pcs) | Install new countertops | Instal microwave | Select colors and styles
Install windows (3pcs) | Install cabinets | Install stove | Prepare the substrate
Check insulation | Install sink | Install refrigerator | Insert ceramic tiles
Lorem Ipsum | Install faucet | Install wine chiller | Lorem Ipsum
| Position garbage bin | Install water cleaning system
22/04 - 23/04 | 28/04 - 02/05 | 05/05 - 07/05 | 10/05 - 14/05
1
2
3
4
5
6
7
8
  KITCHEN CONSTRUCTION SCHEDULE

## ©
© TemplateLab.com