|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|   |   |   |   |   |   |   |
|   | RENOVATION CONSTRUCTION |   |
|   | SCHEDULE |   |
|   |   |   |   |   |   |   |
|   |   |   |   |   |   |   |
|   | **STAGE** | ❶ |   |  |   |
|   |   |   | **Demolition preparations** | **JAN 24 ● FEB 02** |  |   |
|   |   |   | **Demolition** | **FEB 03 ● FEB 22** |  |   |
|   |   |   |   |  |  |   |
|   | **STAGE** | ❷ |  |  |   |
|   |   |   | **Excavation** | **FEB 24 ● MAR 10** |  |   |
|   |   |   | **Concrete** | **MAR 13 ● MAR 17** |  |   |
|   |   |   | **Pre backfill** | **MAR20 ● MAR 24** |  |   |
|   |   |   |   |  |  |   |
|   | **STAGE** | ❸ |  |  |   |
|   |   |   | **Framing** | **APR 01 ● MAY 23** |  |   |
|   |   |   | **Roof** | **MAY 24 ● JUN 02** |  |   |
|   |   |   | **Plumbing** | **MAY 24 ● JUN 06** |  |   |
|   |   |   | **Windows** | **MAY 26 ● JUN 07** |  |   |
|   |   |   | **HVAC** | **JUN 01 ● JUN 12** |  |   |
|   |   |   | **A/V** | **JUN 14 ● JUL 11** |  |   |
|   |   |   | **House wrap** | **JUL 01 ● JUL 15** |  |   |
|   |   |   | **Insulation** | **JUL 16 ● JUL 24** |  |   |
|   |   |   | **Drywall** | **JUL 26 ● AUG 02** |  |   |
|   |   |   |   |  |  |   |
|   | **STAGE** | ❹ |  |  |   |
|   |   |   | **Cabinets** | **AUG 10 ● AUG 13** |  |   |
|   |   |   | **Decks** | **AUG 15 ● AUG 16** |  |   |
|   |   |   | **Interior doors** | **AUG 19 ● AUG 21** |  |   |
|   |   |   | **Interior painting** | **AUG 22 ● AUG 30** |  |   |
|   |   |   | **Appliances** | **SEP 01 ● SEP 05** |  |   |
|   |   |   | **Plumbing** | **SEP 03 ● SEP 12** |  |   |
|   |   |   | **Electrical** | **SEP 03 ● SEP 18** |  |   |
|   |   |   | **Cleaning** | **SEP 30 ● SEP 31** |  |   |
|   |   |   |   | [**© TemplateLab.com**](https://templatelab.com/)   |