## Slide 1
 | RENOVATION CONSTRUCTION |  |  |  |  | 
 | SCHEDULE |  |  |  |  | 
 | STAGE |  | ❶ |  |  | 
 |  |  | Demolition preparations |  |  | 
 |  |  | Demolition |  |  | 
 | STAGE |  | ❷ |  |  | 
 |  |  | Excavation |  |  | 
 |  |  | Concrete |  |  | 
 |  |  | Pre backfill |  |  | 
 | STAGE |  | ❸ |  |  | 
 |  |  | Framing |  |  | 
 |  |  | Roof |  |  | 
 |  |  | Plumbing |  |  | 
 |  |  | Windows |  |  | 
 |  |  | HVAC |  |  | 
 |  |  | A/V |  |  | 
 |  |  | House wrap |  |  | 
 |  |  | Insulation |  |  | 
 |  |  | Drywall |  |  | 
 | STAGE |  | ❹ |  |  | 
 |  |  | Cabinets |  |  | 
 |  |  | Decks |  |  | 
 |  |  | Interior doors |  |  | 
 |  |  | Interior painting |  |  | 
 |  |  | Appliances |  |  | 
 |  |  | Plumbing |  |  | 
 |  |  | Electrical |  |  | 
 |  |  | Cleaning |  |  | 
FEB 03 ● FEB 22
FEB 24 ● MAR 10
MAR 13 ● MAR 17
MAR20 ● MAR 24
APR 01 ● MAY 23
MAY 24 ● JUN 02
MAY 24 ● JUN 06
MAY 26 ● JUN 07
JUN 01 ● JUN 12
JUN 14 ● JUL 11
JUL 01 ● JUL 15
JUL 16 ● JUL 24
JUL 26 ● AUG 02
AUG 10 ● AUG 13
AUG 15 ● AUG 16
AUG 19 ● AUG 21
AUG 22 ● AUG 30
SEP 01 ● SEP 05
SEP 03 ● SEP 12
SEP 03 ● SEP 18
SEP 30 ● SEP 31
JAN 24 ● FEB 02
© TemplateLab.com