|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |
|  | RENOVATION CONSTRUCTION | | | | |  |
|  | SCHEDULE | | | | |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  | **STAGE** | | ❶ |  |  |  |
|  |  |  | **Demolition preparations** | **JAN 24 ● FEB 02** |  |  |
|  |  |  | **Demolition** | **FEB 03 ● FEB 22** |  |  |
|  |  |  |  |  |  |  |
|  | **STAGE** | | ❷ |  |  |  |
|  |  |  | **Excavation** | **FEB 24 ● MAR 10** |  |  |
|  |  |  | **Concrete** | **MAR 13 ● MAR 17** |  |  |
|  |  |  | **Pre backfill** | **MAR20 ● MAR 24** |  |  |
|  |  |  |  |  |  |  |
|  | **STAGE** | | ❸ |  |  |  |
|  |  |  | **Framing** | **APR 01 ● MAY 23** |  |  |
|  |  |  | **Roof** | **MAY 24 ● JUN 02** |  |  |
|  |  |  | **Plumbing** | **MAY 24 ● JUN 06** |  |  |
|  |  |  | **Windows** | **MAY 26 ● JUN 07** |  |  |
|  |  |  | **HVAC** | **JUN 01 ● JUN 12** |  |  |
|  |  |  | **A/V** | **JUN 14 ● JUL 11** |  |  |
|  |  |  | **House wrap** | **JUL 01 ● JUL 15** |  |  |
|  |  |  | **Insulation** | **JUL 16 ● JUL 24** |  |  |
|  |  |  | **Drywall** | **JUL 26 ● AUG 02** |  |  |
|  |  |  |  |  |  |  |
|  | **STAGE** | | ❹ |  |  |  |
|  |  |  | **Cabinets** | **AUG 10 ● AUG 13** |  |  |
|  |  |  | **Decks** | **AUG 15 ● AUG 16** |  |  |
|  |  |  | **Interior doors** | **AUG 19 ● AUG 21** |  |  |
|  |  |  | **Interior painting** | **AUG 22 ● AUG 30** |  |  |
|  |  |  | **Appliances** | **SEP 01 ● SEP 05** |  |  |
|  |  |  | **Plumbing** | **SEP 03 ● SEP 12** |  |  |
|  |  |  | **Electrical** | **SEP 03 ● SEP 18** |  |  |
|  |  |  | **Cleaning** | **SEP 30 ● SEP 31** |  |  |
|  |  |  |  | [**© TemplateLab.com**](https://templatelab.com/) | | |