## Slide 1
 | RESIDENTIAL CONSTRUCTION SCHEDULE |  |  |  |  |  |  | PROJECT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | RESIDENT BUILDING B542 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | PROJECT MANAGER: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | John Doe |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Planned |  |  | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Task | Start Date | End Date | Duration | Start Date | End Date | Duration | Task Status | 01-May | 16-May | 31-May | 15-Jun | 30-Jun | 15-Jul | 30-Jul | 14-Aug | 29-Aug | 13-Sep | 28-Sep | 13-Oct | 28-Oct | 12-Nov | 27-Nov | 12-Dec | 27-Dec | 11-Jan | 26-Jan | 10-Feb | 25-Feb | 12-Mar | 27-Mar | 11-Apr | 26-Apr | 
 | Negotiate project costs | 01/May/2022 | 03/Jun/2022 | 25 | 01/May/2022 | 22/May/2022 | 15 | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Consult regulatory specialists | 13/May/2022 | 31/May/2022 | 12 | 25/May/2022 | 17/Jun/2022 | 18 | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Get permits to start work | 01/Jul/2022 | 29/Jul/2022 | 20 | 01/Jul/2022 | 20/Jul/2022 | 14 | In Progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Foundation | 01/Aug/2022 | 05/Sep/2022 | 25 |  |  |  | Pending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Lorem Ipsum #1 | 06/Sep/2022 | 18/Oct/2022 | 30 |  |  |  | Pending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Lorem Ipsum #2 | 20/Sep/2022 | 25/Oct/2022 | 25 |  |  |  | Pending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Item #7 | 01/Oct/2022 | 11/Nov/2022 | 30 |  |  |  | Pending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Item #8 | 01/Nov/2022 | 29/Nov/2022 | 20 |  |  |  | Pending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Item #9 | 01/Dec/2022 | 29/Dec/2022 | 20 |  |  |  | Pending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Item #10 | 20/Jan/2023 | 14/Apr/2023 | 60 |  |  |  | Pending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
© TemplateLab.com