|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **COMPANY NAME HERE** | | | | | | | | | | | | | | |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **Task** | **Owner** | **Start** | **Finish** | **% Complete** | **W1** | **W2** | **W3** | **W4** | **W5** | **W6** | **W7** | **W8** | **W9** | **W10** |  |
|  | **14/03/22** | **21/03/22** | **28/03/22** | **04/04/22** | **11/04/22** | **18/04/22** | **25/04/22** | **02/05/22** | **09/05/22** | **16/05/22** |  |
|  | **18/03/22** | **25/03/22** | **01/04/22** | **08/04/22** | **15/04/22** | **22/04/22** | **29/04/22** | **06/05/22** | **13/05/22** | **20/05/22** |  |
|  |  | | | | | | | | | | | | | | |  |
|  | **DESIGN** | **Design Corporation LTD** | **14/03/22** | **01/04/22** | **100%** |  |  |  |  |  |  |  |  |  |  |  |
|  | Instructions to a pool designer | Client & Project Manager | 14/03/22 | 15/03/22 | 100% |  |  |  |  |  |  |  |  |  |  |  |
|  | 3D Modelling | Allan Fox (Design Corporation) | 16/03/22 | 25/03/22 | 100% |  |  |  |  |  |  |  |  |  |  |  |
|  | Design rework and approval | Design Corporation & Client | 28/03/22 | 01/04/22 | 100% |  |  |  |  |  |  |  |  |  |  |  |
|  | **PERMITTING** | **Administration Dept.** | **04/04/22** | **15/04/55** | **75%** |  |  |  |  |  |  |  |  |  |  |  |
|  | Building permit forms | Garry Chrismas | 04/04/55 | 05/04/22 | 100% |  |  |  |  |  |  |  |  |  |  |  |
|  | Official permit approval process | Municipality officials | 06/04/22 | 15/04/22 | 60% |  |  |  |  |  |  |  |  |  |  |  |
|  | **EXCAVATION** | **Heavy Machinery Team** | **18/04/22** | **22/04/22** | **0%** |  |  |  |  |  |  |  |  |  |  |  |
|  | Digging | John Millman | 18/04/22 | 21/04/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Utilities protection | Mick Dixon | 20/04/22 | 22/04/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | **STEEL, PLUMBING, ELECTRICAL** | **Special Teams** | **25/04/22** | **06/05/22** | **0%** |  |  |  |  |  |  |  |  |  |  |  |
|  | Lay the steel route | Construction Team | 25/04/22 | 29/04/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Electrical installations | Electrical Team | 02/05/22 | 06/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Plumbing installations | Plumbing Team | 02/05/22 | 06/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | **VINYL POOL INSTALLATION** | **Installation Team** | **09/05/22** | **13/05/22** | **0%** |  |  |  |  |  |  |  |  |  |  |  |
|  | Pool shipping | Truckers Co. | 09/05/22 | 09/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Pool installation | Installation Team | 10/05/22 | 13/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | **DECK & LANDSCAPING** | **Special Teams** | **16/05/22** | **20/05/22** | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Landscaping | Landscaping Team | 16/05/22 | 19/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Water features | Plumbing Team | 16/05/22 | 20/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Deck customization | Outdoor Design Team | 16/05/22 | 18/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  | Custom lighting | Electrical Team | 17/05/22 | 18/05/22 | 0% |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SWIMMING POOL  CONSTRUCTION SCHEDULE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

[**© TemplateLab.com**](https://templatelab.com/)