## Slide 1
EXPLORING & PREPARING
PLANNING & RESOURCING
implementiNG
FULL IMPLEMENTATION
JAN 01 – FEB 22
Assessing needs and the evidence base for the intervention
Assessing fit, feasibility and appropriateness
Assessing implementation readiness
Developing leadership for implementation
Stakeholder engagement planning
Selecting or designing the intervention
Identifying outcomes
Developing a theory of change and logic model
mar 01 – apr 06
Assessing enablers and barriers for implementation
Developing an implementation plan
Establishing implementation team(s) and other structures to support implementation
Securing resources
Identifying champions to support implementation
Designing monitoring, evaluation and feedback systems
Determining and delivering staff training, capacity building and support requirements
Planning for sustainability.
apr 12 – jun 17
Maintaining ongoing communication with key stakeholders, explaining why the intervention is necessary and securing continued buy in
Providing ongoing professional development opportunities, coaching and mentoring for stakeholders implementing and delivering the intervention
Monitoring implementation, service and client outcomes
Using data and feedback to inform ongoing improvements
Adapting for local context where appropriate.
aug 01 – aug 30
Maintaining skilful practice
Developing more efficient and effective structures
Evaluating implementation, service and client outcomes
Engaging in continuous improvement cycles.
IMPLEMENTATION TIMELINE
© TemplateLab.com