## Internship Work Plan Template
INTERN NAME: |  | John Doe |  |  | START DATE: | 2023-01-20
MAIN MENTHOR: |  |  | Benjamin Brooks |  | END DATE: | 2023-03-17
INTERNSHIP GOAL: |  |  |  | Getting base knowledge of court practice and preparing commercial propoosals
SECTOR/TRAINING: |  |  |  | HR/ Standard Operating Procedures
ID | Task |  |  |  | Trainer/ Supervisor |  | Expected Time | Deadline
1.1 | Reading SOPs for dress code and time evidence |  |  |  | J. Reese |  | 2 work days | 2023-01-24
1.2 | Training and test for SOPs for data loss prevention |  |  |  | J. Reese |  | 3 work days | 2023-01-27
SECTOR/TRAINING: |  |  |  | ADVOCACY / Court Practice
ID | Task |  |  |  | Trainer/ Supervisor |  | Expected Time | Deadline
2.1 | General company rules regarding confidentiality |  |  |  | D. Barton |  | 10 work days | 2023-02-10
2.2 | Client relationship, case studying practice |  |  |  | D. Nicholson |  | 10 work days | 2023-02-24
2.3 | Legal case paperwork and court room appearance |  |  |  | C.Harper |  | 8 work days | 08/03/203
SECTOR/TRAINING: |  |  |  | FINANCE / Commercial proposals
ID | Task |  |  |  | Trainer/ Supervisor |  | Expected Time | Deadline
3.1 | ERP solution and training for entering customers |  |  |  | N. McDonald |  | 2 work days | 2023-03-10
3.2 | Demo of creating commercial proposals |  |  |  | J. Bray |  | 5 work days | 2023-03-17
INTERNSHIP REVIEW | [6 empty] | Grade: | 9 / 10
John Doe already feels lika a part of the team, having the opportunity to offer colleagues his ideas and to implement them on his own. He got the opportunity to be engaged in projects and a variety of tasks (from researching court practice to preparing a commercial proposal for a client). He had his own area of responsibility, which, in my opinion, is very important for getting used to starting from the lowest positions.

## ©
© TemplateLab.com