## Team Work Plan Template
Identification
| Cost Benefit Analysis | Bobby Porter
2023-02-02
| Risk Assessment | Maddox Rose
2023-02-18
| Develop Project Proposal | Tia Workman
2023-02-28
Planning
| Kick-off meeting with client | Morgan Sutton
2023-03-17
| Define scope of work and write URS | Denny Burris
2023-03-31
| Identify and Record Project Risks | Alfie Wilkinson
2023-04-11
Execution and Control
| Project Communications Management | Nickolas Sullivan
2023-04-18
| Manage Project Procurement | John Doe
2023-05-21
| Track and Manage Project Risks and Issues | Zaid Shaw
2023-06-01
| Conduct Project Change Management | Tia Workman
2023-06-17
Closeout
| Conduct Closeout Meetings | Nickolas Sullivan
2023-07-10
| Develop Lessons Learned | Adonis Dickson
2023-07-11
| Develop Closeout Report | Leslie Palmer
2023-07-16
| Archive Project Documents and Conduct Transitioning Activities | Mel Jackson
2023-07-31
T E A M
WORK PLAN
APPROVED
$450,000
OUT FOR APPROVAL
IN PROGRESS
RESEARCH
ESCALATION

## ©
© TemplateLab.com