## Slide 1
PHASES
BUSINESS ACQUISITION
Work Breakdown Structure
TASK DEADLINE RESPONSIBLE
Plan an acquisition strategy
Set up goal
Benefits listed
Define acquisition type
Jan 09, 2023
Jan 14, 2023
Jan 22, 2023
S.Dilbert
B. Elora
S. Dilbert
Establish the search criteria for the opportunity
Management can be improved
Lack of treasury to be covered
International expansion opportunity
Feb 05, 2023
Feb 08, 2023
Feb 22, 2023
M. Willson
M. Willson
Y. Hammer
Search for potential targets
Analyse objectives condition
Opportunities offered by banks
Professional references
Feb 27, 2023
Mar 02, 2023
Mar 04, 2023
M. Willson
M. Willson
Y. Hammer
Planning the transaction
Contacting companies
Assess the potential companies
NDA agreements handling
Mar 15, 2023
Mar 31, 2023
Apr 10, 2023
N. Pikachu
G. Beavis
D. Castiel
Analysis of the company
Ask for additional information
Evaluate the potential acquisition
Financial statements examination
Apr 20, 2023
Apr 30, 2023
May 06, 2023
A. Fester
A. Fester
Y. Hammer
LOI (Letter of Intent) and Negotiations
First offer (non-binding)
More detailed negotiations
Binding offer
May 11, 2023
May 25, 2023
May 31, 2023
T. Dagwood
R. Yoda
Z. Merida
Due Diligence
Confirm or correct the evaluation
Due diligence report creation
Offer corrections (Final offer)
Jun 04, 2023
Jun 20, 2023
Jun 25, 2023
U. Challa
B. Harris
L. Loyd
Drafting of contracts and other transaction documents
Payment method and guarantees
Power sharing definition
How to retain key people
Jul 08, 2023
Jul 12, 2023
Jul 18, 2023
J. Nakashima
W. Johnson
S. Paris
Finance for the operation
Stable cash flow management
Investment program definition
Amount of funds needed defined
Jul 25, 2023
Jul 30, 2023
Aug 10, 2023
F. Sonic
A. Wednesday
M. Poup
Closing and integration for the acquisition
Signing of the commercial operation
The effective integration
Internal protocols revisions
Aug 28, 2023
Sep 10, 2023
Sep 30, 2023
H. Morris
V.Gage
B. Barton
01
02
03
04
05
06
07
08
09
10
© TemplateLab.com