## Slide 1
 |  |  |  |  | PROJECT ACTION PLAN |  |  |  |  |  | 
 | CLAUDIA WARREN |  |  |  |  |  |  |  |  |  | 
 |  | Project Manager |  |  |  | WEBSITE FOR MARKETING PURPOSES |  |  |  |  | 
 |  | E: claudia.warren@mycompanyname.com |  |  |  | For our web design project, the requirements include designing a new website for a pet shop that allows consumers to purchase products online and to contact the pet shop in an online format. Colour scheme - grey, magenta, blue. |  |  |  |  | 
 |  | P: (555) 1000 256 5521 |  |  |  |  |  |  |  |  | 
 | GOAL #1: MARKET RESEARCH |  |  |  | TIMELINE |  |  | RESOURCES |  |  | 
 | Action Item | Phase | Responsible | Progress | Start | End | Planned Hrs | Department | Materials | Cost | 
 | Hire marketing guru | Completed | Sarah H. & Gloria G. | 100% | 01/01/2023 | 10/01/2023 | 30 hrs | HR | LinkedIn Research | $350.00 | 
 | Gather statistic data | Completed | Hannah B. | 100% | 15/01/2023 | 30/01/2023 | 80 hrs | Marketing | Web services | $1,540.00 | 
 | Marketing segmentation | Execution | Jurgen M. | 75% | 01/02/2023 | 28/02/2023 | 120 hrs | Marketing | Online marketing tools | $3,200.00 | 
 | Final strategy definition | Execution | Vera S. & John G. | 60% | 20/02/2023 | 15/03/2023 | 60 hrs | Marketing |  |  | 
 | GOAL #2: WEBSITE DESIGN |  |  |  | TIMELINE |  |  | RESOURCES |  |  | 
 | Action Item | Phase | Responsible | Progress | Start | End | Planned Hrs | Department | Materials | Cost | 
 | Website architecture | Planning | Mike N. | 10% | 01/04/2023 | 25/04/2023 | 100 hrs | IT Development |  |  | 
 | Develop user interface | Planning | Gilbert F. | 10% | 01/04/2023 | 30/04/2023 | 50 hrs | Web Development | Icon library | $300.00 | 
 | GOAL #3: WEBSITE LAUNCH |  |  |  | TIMELINE |  |  | RESOURCES |  |  | 
 | Action Item | Phase | Responsible | Progress | Start | End | Planned Hrs | Department | Materials | Cost | 
 | Internal testing | Not Started | John J. | 0% | 01/05/2023 | 05/05/2023 | 24 hrs | IT Development | Cloud | $1,500.00 | 
 | SEO work | Not Started | Vera S. | 0% | 01/05/2023 | 10/05/2023 | 40 hrs | Marketing |  |  | 
 | Go Live | Not Started | Vera S. & John G. | 0% | 11/05/2023 | 11/05/2023 | 8 hrs | Marketing |  |  | 
© TemplateLab.com