## IT Project Staffing Plan
IT PROJECT STAFFING
Project Name: Project Phoenix |  |  | Project Description:
Company Name: Tech Innovators, Inc. |  |  | Project Phoenix aims to develop a cutting-edge e-commerce platform that revolutionizes online shopping. The platform will provide seamless user experiences, personalized recommendations, and efficient order processing.
Project Manager: Alexandra Carter
Start Date: April 15, 2024
Activity | Role | Project Responsibility |  | Skills Required |  | Number of Staff Req. | Estimated Start Date | Duration Required
Coding | Java Developer | Develop core modules |  | Java, Spring, Hibernate |  | 2 | 2024-04-15 | 9 months
Testing | QA Analyst | Test core modules | Test core modules | Automation, Selenium | Automation, Selenium | 3 | 2024-04-30 | 8 months
Deployment | DevOps Engineer | Deploy applications on production | Deploy applications on production | Jenkins, Docker, AWS | Jenkins, Docker, AWS | 5 | 2024-05-15 | 5 months
Design | UX Designer | Create user interfaces | Create user interfaces | UI/UX design, Sketch | UI/UX design, Sketch | 2 | 2024-04-20 | 5 months
Documentation | Technical Writer | Document application features | Document application features | Technical writing | Technical writing | 1 | 2024-11-01 | 2 months
Role | Name | Requested FTE | Acquired FTE | Rate Unit | Source
|  | (FY24-25) | (FY24-25)
Java Developer | John Doe | 1 | 1 | $80/hr | Hourly (Internal)
Java Developer | Jane Smith | 1 | 1 | $80/hr | Hourly (Internal) | Hourly (Internal) | Hourly (Internal) | Hourly (Internal)
QA Analyst | Mark Brown | 0.8 | 1 | $60/hr | Hourly (ABC Corp) | Hourly (ABC Corp) | Hourly (ABC Corp) | Hourly (ABC Corp)
QA Analyst | Emily White | 0.8 | 0.5 | $60/hr | Hourly (ABC Corp) | Hourly (ABC Corp) | Hourly (ABC Corp) | Hourly (ABC Corp)
DevOps Engineer | Michael Clark | 0.5 | 0.5 | $90/hr | Hourly (Internal) | Hourly (Internal) | Hourly (Internal) | Hourly (Internal)
DevOps Engineer | Laura Adams | 0.5 | 0.5 | $90/hr | Hourly (Internal) | Hourly (Internal) | Hourly (Internal) | Hourly (Internal)
DevOps Engineer | William Brown | 0.5 | 0.5 | $90/hr | Hourly (External - RockIT) | Hourly (External - DesignCo) | Hourly (External - DesignCo) | Hourly (External - DesignCo)
DevOps Engineer | Daniel Lee | 0.5 | 0.2 | $90/hr | Hourly (External - RockIT) | Hourly (External - DesignCo) | Hourly (External - DesignCo) | Hourly (External - DesignCo)
DevOps Engineer | Olivia Smith | 0.5 | 0.2 | $90/hr | Hourly (External - RockIT) | Hourly (External - DesignCo) | Hourly (External - DesignCo) | Hourly (External - DesignCo)
UX Designer | Ava Johnson | 0.4 | 0.4 | $70/hr | Hourly (External - DesignCo) | Hourly (External - DesignCo) | Hourly (External - DesignCo) | Hourly (External - DesignCo)
UX Designer | Ethan White | 0.5 | 0.5 | $70/hr | Hourly (External - DesignCo) | Hourly (External - DesignCo) | Hourly (External - DesignCo) | Hourly (External - DesignCo)
Technical Writer | Noah Adams | 0.2 | 0.2 | $50/hr | Hourly Contract (Writer Services) | Hourly Contract (Writer Services) | Hourly Contract (Writer Services) | Hourly Contract (Writer Services)

## ©
© TemplateLab.com