## Project Staffing Plan Template
Project Name: | IT Infrastructure Installation Project |  | Project Description:
Project Manager: | John Smith |  | The IT Infrastructure Installation Project aims to upgrade our organization’s network, servers, and hardware components to enhance efficiency, security, and scalability.
Budget: | 500000
Starting Date: | April 1, 2024
Activity | Role | Project Responsibility | Skills Required | Number of Staff | Start Date | Duration Expected
Network Assessment | Network Engineer | Evaluate existing network infrastructure, identify weaknesses, and propose improvements. | Cisco networking, subnetting, security protocols | 1 | 2024-04-01 | 2 weeks
Server Deployment | System Administrator | Install and configure servers, ensuring optimal performance and security. | Windows/Linux server administration, virtualization | 2 | 2024-04-15 | 4 weeks
Hardware Procurement | Procurement Specialist | Source and purchase required hardware components within budget constraints. | Vendor management, negotiation skills | 1 | 2024-04-01 | 1 week
Cable Installation | Cable Technician | Physically install network cables, patch panels, and switches. | Structured cabling, cable termination | 2 | 2024-04-08 | 3 weeks
Firewall Setup | Security Specialist | Configure firewalls and security appliances to protect the network. | Firewall rules, intrusion detection | 1 | 2024-04-22 | 2 weeks
Backup Implementation | Backup Administrator | Set up data backup solutions for servers and critical systems. | Backup software, disaster recovery planning | 1 | 2024-04-29 | 1 week
Testing and QA | QA Analyst | Test network functionality, identify issues, and ensure compliance. | Test scripts, documentation | 1 | 2024-05-06 | 2 weeks
Documentation | Technical Writer | Create user manuals, system documentation, and standard operating procedures. | Technical writing, communication skills | 1 | 2024-05-20 | 1 week
STAFFING REQUIREMENTS GUIDELINES:
Based on the staffing requirements, we can conclude that this project demands a diverse team with specialized skills. Effective collaboration among these roles will ensure successful IT infrastructure installation and smooth project execution.
PROJECT STAFFING PLAN

## ©
© TemplateLab.com