Lessons Learned: University Hospitals of Morecambe Bay NHS Trust

Project: Care Management Code:

UHMB NHS Foundation Trust SHA:

NWSHA

The CSC Alliance

Working with NHS Connecting for Health

to deliver the National Programme for IT

| CSC Alliance Proprietary Information | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| --- | --- |
| Version 1.0 | 22/02/2011 | Page 2 of 50 |

| Content: |  | University Hospitals of Morecambe Bay NHS Foundation Trust Lessons Learnt |
| --- | --- | --- |
|  |  | Document |
| Originator: |  | Dave Mackay and Keith Bentham |
| Owner: |  | Aiden Griffin / Steve Fairclough |
| Version: |  | 1.0 |
| Date: |  | 22/02/2011 |
| Confidentiality: |  | CSC Alliance Proprietary Information |
| Configuration |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Reference: |  |  |
| Date Approved |  | 18 February 2011 |
| by CSCA: |  |  |
| CSCA Approver: |  | Dave Mackay |
| Date Sent for |  | 14 February 2011 |
| Authority |  |  |
| Approval: |  |  |
| Date Approved |  | 18 February 2011 |
| by Authority: |  |  |

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 3 of 50

Foreword

This document is delivered pursuant to the ICRS LSP Project Agreement for the North West SHA between The Secretary of State for Health and CSC Computer Sciences Limited (the Project Agreement) dated 2nd April 2009.

Confidentiality

All Information contained in this document is confidential to the NHS National Programme for Information Technology (NPfIT) or any other member of the NHS North Midlands and Eastern Programme for Information Technology (NMEPfIT), and CSC Computer Sciences Limited and is intended only for use within the NHS Care Record Local Service Provider (LSP) Programme.

|  | Distribution |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Role |  | Name |  | Organisation |  | Location |  | Copies |  |
|  | CSC Alliances |  | All CSCA NHS |  | CSC Alliance |  | NHS CSC |  | 1 electronic |  |
|  | Alliance |  | Project Staff |  |  |  | Alliance |  |  |  |
|  |  |  |  |  |  |  | Programme |  |  |  |
|  |  |  |  |  |  |  | Portal Centre |  |  |  |
|  | NHS |  |  |  | NHS |  | SHA |  | 1 electronic |  |
|  | Programme |  |  |  |  |  | Warrington |  |  |  |
|  | Office |  |  |  |  |  |  |  |  |  |
|  | Director of |  | Patrick |  | UHMB |  | Furness |  | 1 electronic |  |
|  | Service and |  | McGahon |  |  |  | General |  |  |  |
|  | Commercial |  |  |  |  |  | Hospital |  |  |  |
|  | Development |  |  |  |  |  |  |  |  |  |
|  | Head of |  | Steve |  | UHMB |  | Furness |  | 1 electronic |  |
|  | Health |  | Fairclough |  |  |  | General |  |  |  |
|  | Informatics |  |  |  |  |  | Hospital |  |  |  |
|  | UHMB |  | Keith Bentham |  | UHMB |  | Furness |  | 1 electronic |  |
|  | Programme |  |  |  |  |  | General |  |  |  |
|  | Manager |  |  |  |  |  | Hospital |  |  |  |
|  | Deputy Chief |  | Debbie |  | NHS |  | SHA |  | 1 electronic |  |
|  | Information |  | Bywater |  | Northwest |  | Warrington |  |  |  |
|  | Officer, NHS |  |  |  |  |  |  |  |  |  |
|  | Northwest |  |  |  |  |  |  |  |  |  |
|  | CSCA NW |  | Aiden Griffin |  | CSCA |  | CSCA Chorley |  | 1 electronic |  |
|  | Acct Exec |  |  |  |  |  |  |  |  |  |
|  | CSCA Project |  | Dave Mackay |  | CSCA |  | CSCA |  | 1 electronic |  |
|  | Manager |  |  |  |  |  | Knowsley |  |  |  |

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 4 of 50

Amendment Record

|  | Issue Status |  |  | Version |  |  | Date | Actioned By |  | Description |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Draft |  |  |  | V0.1 |  |  |  | 06/12/10 |  | Keith Bentham |  |  | First rough draft to |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | establish |
|  | Draft |  |  |  | V0.2 |  |  |  | 12/01/10 |  | Darren Thomas |  |  | Updated to include |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | CSCA content |
|  | Draft |  |  |  | V0.3 |  |  |  | 12/01/10 |  | Darren Thomas |  |  | Revised formatting and |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | added content to |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | section 6 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Reviewed and own |
|  | Version |  |  |  | V0.4 |  |  |  | 13/01/10 |  | Dave Mackay |  |  | comments added – |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | kept at draft pending |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Review |
|  |  |  |  |  | V0.5 |  |  |  | 14/02/10 |  | Darren Thomas |  |  | Updated with content |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | from Barrow lessons |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | learned meeting |

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 5 of 50

|  | Glossary |  |  |
| --- | --- | --- | --- |
|  | Abbreviation |  | Description |  |
|  | ADR |  | Adverse Drug Reaction |  |
|  | ATP |  | Authority To Proceed |  |
|  | BAU |  | Business As Usual |  |
|  | CDC |  | Clinical Data Capture |  |
|  | CFH |  | Connecting For Health |  |
|  | CRT |  | Community Rehabilitation & Therapy |  |
|  | CSCA |  | Computer Sciences Corporation Alliance |  |
|  | DVP |  | Deployment Verification Period |  |
|  | EUT |  | End User Training |  |
|  | iPM |  | iSoft Patient Manager |  |
|  | LAN |  | Local Area Network |  |
|  | LRC |  | Lorenzo Regional Care |  |
|  | LRD |  | Local Reference Data |  |
|  | MPI |  | Master Patient Index |  |
|  | NSD |  | National Service Desk |  |
|  | PDS |  | Patient Demographic Service |  |
|  | PID |  | Project Initiation Document |  |
|  | QA |  | Quality Assessment |  |
|  | RBAC |  | Role Based Access Control |  |
|  | SDRC |  | Standard Deployment Readiness Criteria |  |
|  | SHA |  | Strategic Health Authority |  |

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 6 of 50

Table of Contents

| Table of Contents | 6 |
| --- | --- |
| 1 | Management Summary | 8 |
| 1.1. | Background | 8 |
| 1.2. | Key themes | 8 |
| 1.3. | Key recommendations | 9 |
| 2 | Introduction | 12 |
| 3 | Roles and Responsibilities | 13 |
| 3.1. | CSCA Responsibilities: | 13 |
| 3.2. | NHS Responsibilities: | 13 |
| 4 | Key Points | 15 |
| 5 | Lessons Learnt | 16 |
| 5.1. | Project Governance | 16 |
| 5.2. | Project Initiation | 18 |
| 5.3. | Project Management | 18 |
| 5.4. | Training | 20 |
| 5.5. | Business Change | 23 |
| 5.6. | Stakeholder Engagement and Comms | 25 |
| 5.7. | Benefits Planning and Realisation | 26 |
| 5.8. | Design | 27 |
| 5.9. | Solution Localisation | 29 |
| 5.10. | Interfaces | 31 |
| 5.11. | Data Migration | 32 |
| 5.12. | Deployment Testing | 34 |

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| --- | --- |
| Version 1.0 |  | 22/02/2011 | Page 7 of 50 |
| 5.13. | RBAC / SSO |  | 38 |
| 5.14. | Cut-over |  | 38 |
| 5.15. | Post Go-Live Deployment Issues | 40 |
| 5.16. | Service Delivery |  | 41 |
| 5.17. | Infrastructure |  | 41 |
| 5.18. | Unforeseen Events |  | 44 |
| 5.19. | Tools and Methods |  | 45 |
| 5.20. | Trust Culture |  | 45 |
| 5.21. | Other |  | 46 |
| 6 | Conclusions & Recommendations | 47 |

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 8 of 50

1	Management Summary

1.1. Background

The National Programme for Information Technology (NPfIT) is a key part of reform of the NHS and will help make the NHS a more responsive service that provides patients with more choice. To help patients make these vital choices they will need access to more information about the NHS and their own personal health and care history than ever before.

The overall goal as part of the National Programme is to modernise the delivery of patient care in accordance with the NPfIT strategy, and achieve interoperability across key care settings. The key objectives of the NPfIT include:

Improving the health of the population Improving the quality of care

Improving the patient experience Reducing waiting times

Delivering NHS service and modernisation priorities

Producing better financial and management information.

This Project was been established to deliver clinical benefit to the healthcare population of UHMB within the NW Strategic Health Authority. The project scope was designed to deliver UHMB with the NHS care record service (NCRS), i.e. to make patient treatment information available across the UHMB. This project replaced the i.PM PAS and will ultimately replace the i.PM A&E system currently used by UHMB.

1.2. Key themes

The 20 key themes identified in the project lessons learned are:

| Section |  | Theme |
| --- | --- | --- |
| 5.1 |  | Project Governance |
| 5.2 |  | Project Initiation |
| 5.3 |  | Project Management |
| 5.4 |  | Training |
| 5.5 |  | Stakeholder Engagement and Comms |
| 5.6 |  | Benefits Planning and Realisation |
| 5.7 |  | Design |

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 9 of 50

5.8	Solution Localisation

5.9	Interfaces

5.10	Data Migration

5.11	Deployment Testing

5.12	RBAC / SSO

5.13	Cutover

5.14	Post Go Live Deployment Issues

5.15	Service Delivery

5.16	Infrastructure

5.17	Unforeseen Events

5.18	Tools and Methods

5.19	Trust Culture

5.20	Other

1.3. Key recommendations

The key recommendations from the deployment are as follows:

| Lesson | Recommendation |
| --- | --- |
| ID |  |

- With the additional communications support aspects of being an Early Adopter make arrangements for co-ordination/vetting of information requests.

- Put resource requests in early for additional project team members.

- Use lessons from other sites.

- Use less detailed job plans. The job plans should include a start and end date of each activity to allow better monitoring.

- The training single instance model is sufficient for a steady state business usual but not for the Early Adopter model. An alternative training solution is required to support the EA’s

- Do not train until you are sure you have a Project that is 95% sure that it is going live.

- If using GURU, implement on the lead up to the go-live to get staff into the habit of

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 10 of 50

using GURU on the lead up rather than during the noise immediately post go-live.

17	Ensure trainers/training workstream is embedded as part of project team

- Training should include a section for operational reports and the trust should agree as part of their organisational procedures which reports are most useful for which areas (outpatients, inpatients etc)

- Future state Business Processes need to be established early on in the project as part of a readiness assessment

- Future state Business Processes need to be established early on in the project verified and owned by the Operational Managers to ensure compliance.

- Ensure the scope of any service improvement/capacity and demand work is thoroughly documented and all involved parties have a clear understanding of what is to be undertaken including the delivery dates.

- That Trust’s acknowledge the scale and importance of this major change project and endorse full support from the information department to provide vital data at an operational level

- To ensure all parties involved are organised and hold the correct information to be able to deliver.

- Engage with a good cross section of employees from managers to those on the shop floor

- Contact all involved parties prior to business change events/workshops to ensure they hold the most correct and up to date information.

- Ensure projects have a full time Communications lead.

- Use clinical and project leads to validate the development and agreement of benefits – this will help support achievement of relevant benefits

33	The project has a full-time Benefits lead.

- Make sure stakeholders are involved with benefits work from the very start of the project. Regular updates from the benefits manager to improvement groups is important and an active role for stakeholders with benefits work should be encouraged

- Anonymous opinion questionnaires have allowed staff to express their thoughts directly to those who will listen which in turn reduces negative ‘gossip’ within departments and assures staff that they are being listened to and that their opinion is valid and valued.

- The parallel runs were good in that they were able to emphasise usability issues however these need to be taken onto the next level by better replication of real system use i.e. interruptions to their work. For example users experiencing phone calls whilst booking patients.

40	We had a core team of people whom you could rely on to do the key complex tasks

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 11 of 50

and then a larger number of inexperienced staff who came in during the latter stages of the project, did add some value eventually but it took a disproportionate amount of time to get these people productive e.g. To help with the creation of letter templates. Lesson is to try and get these staff involved in the project as early as possible.

41	Tools needed earlier to transfer config between builds

- All of the issues encountered post go-live need to be fed back to the DM team to ensure that they do not happen at the next cutover

- Prior to deployment testing starting, consideration must be given to the business processes – when will reports be used by the trust in the functional areas and this should be built into the test plan. The ‘true users’ should also conduct this testing. They will have greater understanding of the different scenarios the reports will be used in. Example: If an outpatient receptionist runs a clinic list in iPM for a consultant every Tuesday prior to clinic then it is reasonable to expect that user to test the equivalent report in Lorenzo in the same way.

- Get iPM setup in same environment as DEPLOR526.

- Make the test environments mimic the PROD environment more accurately.

- Recognition of common/understood aims/objectives at the outset

- Co-locate all of the testing activities

- Discipline of having a daily wash-up before /after each testing day

- CSCA need to prove their ability to fix issues in dress rehearsal so that Projects can have the assurance that during actual cut over issues will be fixed in a timely manner

- If adopting ‘Vocera’ technology ensure that all the communication black spots are identified.

- Ensure operational report testing is included in the cut over plan as part of each functional area.

- Make a room available for developers/data migration staff to quickly turn issues around on site.

- Ensure that issues are owned by Issues Resolution Team and Chennai team are there only to assist.

- The Environments should be tested prior to the Trust taking delivery. Joint Touch testing between CSCA and the Trust for each environment

94	In adverse weather conditions make better use of phone and video conferencing

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 12 of 50

2	Introduction

This report has been compiled jointly between UHMB and CSCA project teams. This is a living document and will be added to as and when applicable lessons learnt are submitted.

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 13 of 50

3	Roles and Responsibilities

Both parties hold a joint responsibility for the completion of lessons learned and planned actions arising from such lessons for inclusion in the Deployment Verification Report. Lessons learned must be submitted to nhs.deployment.verification@csc.com prior to the final verification day. The responsibilities of each party will include the following as a minimum:

3.1. CSCA Responsibilities:

Plan and agree timelines with the NHS Project Manager that supports the delivery of lessons learned to enable the planned completion of DVP.

Collate, from the CSCA Deployment team, the lessons learned from the Deployment.

Notify the NHS Project Manager within a reasonable time frame that they should provide the NHS lessons learned to CSCA (in an agreed format) prior to the completion of DVP, in order that CSCA can receive, compile and combine such lessons learned with CSCA’s lessons learned into one document for review by the parties.

Should the NHS Project Manager not provide the lessons learned within a reasonable time frame prior to the completion of the DVP, escalate to the SHA for resolution (Note: CSCA is not responsible for any failure of the NHS to provide lessons learnt feedback) .

Liaise with the NHS Project Manager (whether by conference call or meeting, whichever is most appropriate), to discuss and agree the lessons learned and any actions that need to be taken by the parties. Where a party states that no lessons have been learned, this position should be agreed by both parties (such agreement not to be unreasonably withheld).

Inclusion of the final lessons learned and planned actions arising from such lessons in the final Deployment Verification Report.

3.2. NHS Responsibilities:

Collate from the NHS Location / Deployment team, the lessons learned with regards that Deployment at that relevant Location.

Communicate such lessons learned to the CSCA Deployment Manager within a reasonable timeframe to support the planned completion of the DVP.

Meet with the CSCA Deployment Manager (whether by conference call or by meeting, whichever is most appropriate) to discuss and agree the lessons learned and any actions that need to be taken by the parties.

Where a lack of lessons learnt feedback is identified and escalated to the SHA, use reasonable endeavors to resolve such escalation within timescales that support the planned completion of the DVP.

Where a party states that no lessons have been learned, this position should be agreed by both parties (such agreement not to be unreasonably withheld).

A failure by CSCA to fulfill their responsibilities outlined above may result in rejection of, or delay in authorising, the final Deployment Verification Report by the designated NHS approver until such time as CSCA’s responsibilities have been fulfilled.

If the NHS Project Manager’s responsibilities have not been fulfilled in timescales which support the planned completion of the DVP and CSCA has complied with its responsibilities for lessons learned, CSCA may submit the Deployment Verification Report with CSCA lessons learned data only (where applicable) and this will not delay approval of the Deployment

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 14 of 50

Verification Report. Details of requests for NHS input will be included in the Deployment Verification Report for information.

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0

22/02/2011

Page 15 of 50

4	Key Points

The following table details a list of the key observation points identified from the main lessons learned content in section 5:

Observation Areas

Stage Gate Crash

Additional Communications/SHA Reviews

Ramp up of resources

Lessons learned from other projects

Job Plans

Risk Management

Workstreams

End User Training

Go-live date delay

Guru/Wiki

Trainer involvement

Specific training to Trust ‘service leads’

Future state business processes

Change management issues

Capacity and demand work

Information department and business change process

Change Workshops

Communications Lead

Communication of Benefits

Benefits Lead

Benefits Tracker

Software Delivery

Usability

Resourcing

Configuration/Configuration Transfer

Data Migration aspects

Cycle Testing and parallel runs

RBAC Versions

Cutover resources, activities and planning

Service and Issue Management

Environments and performance

Weather

This document is subject to the conditions in the Foreword © CSC

Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 16 of 50 |

5	Lessons Learnt

The process for completing this lessons learned report was that an initial set of lessons were noted by the Trust and CSCA Project Managers whilst the project was running. Once the project went live further requests were made to the project team to consider any further lessons and the document was then compiled from that input for submission as part of the Deployment Verification Report.

5.1. Project Governance

| Id |  | Observations |  | Consequences |  | Lesson Learnt |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | (what went well/ what went badly/ what was |  | (what was achieved/ was not achieved because of |  |  |
|  |  | missing) |  | this) |  |  |

- Stage Gate Crash – Triangle 6 As part of the project management Avoid Stage Gate Crash stage gate was crashed in strategy, UHMB placed a number of

January in an attempt to hit the  ‘Review Gates’ into the plan.  Due to

March 2010 date.	unforeseen circumstances and outside

influences, the first gate date ultimately

wasn’t hit and the project went live at

the end of May but in the meantime

this lead to activities being done either

in	a	rush	or	at	the	last	possible

moment.

Due to time constraints, there were

also a number of config areas that

were  not  fully  explored  which  have

meant that the users and Trust have

lost	some	potential	features,	time

savings and benefits that the product

could deliver.	E.g. Access Planning

config such as Linking Access plans to

Preferred Clinics/Wards to help stream

Owner

CSCA /

Trust PMs

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 17 of 50

line the process.

- Additional Communications/SHA Review Overhead.

- Senior management involvement.

The attention by senior management while welcome was not consistent.

A project of this nature unfortunately attracts an additional overhead for comms and assurance.

The additional effort required to support the SHA Review, deliverables and in particular the Triangle 7 and 6 reviews had had a big impact on delivery at a key stage in the project.

In addition, the demand for information and ‘reports by Close of play’ that frequently landed in an ad-hoc nature from ‘left field’ were also very frustrating at best and a real distraction and drain on delivery at worse and their effect on a number of levels should not be under estimated or forgotten.

When senior CSCA managers were involved this provided focus and good customer relations. However when the interest was not there it left a level of confusion and a vacuum. There was ample project management attention but inconstant senior attention created a disjointed customer experience

Better Co-ordination/Vetting of Information Requests.

More consistent attention from the CSCA higher management would be beneficial.

SHA

CSCA

Programme

Managment

| 4. |  | Daily focus around the T0 (and |  | The plans had a familiar look and feel. |  | Regularly reviewed T0 plan, 10 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | similar versions) of the plan |  | They allowed a rolling horizon of |  | day rolling plan and high level |

CSCA

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 18 of 50

|  |  | worked well. |  | planning and for all parties to be fully |
| --- | --- | --- | --- | --- |
|  |  |  |  | up to speed on a daily basis without |
|  |  |  |  | the over head of a detailed MS project |
|  |  |  |  | plan |

cutover plan worked very well. These should be adopted as standard practice

| 5.2. |  | Project Initiation |  |  |
| --- | --- | --- | --- | --- |
| Id |  | Observations |  | Consequences |
|  |  | (what went well/ what went badly/ what was |  | (what was achieved/ was not achieved because of |
|  |  | missing) |  | this) |

Lesson Learnt

Owner

- Project initiation was relatively smooth but ramp up of resources was slow

- Unrealistic expectations of timescales. The original dates at initiation were a very aggressive and unrealistic at the time of writing the PID

Put additional pressure on existing staff. Some workstreams did not fully engage in the initial stages. The effect of this was that in the latter stages of the project some of the workstreams were behind with specific activities and as a result certain areas did not have the necessary concentrated effort.

This lead to planning assumptions being erroneous

Put resource requests in early to avoid difficulty with resources internally and commitments on day to day activities.

Realistic expectations should be discussed and agreed with senior management on all sides given the evidence available early in the project

Trust

CSCA

CSCA

Programme

managment

5.3. Project Management

Id	Observations

(what went well/ what went badly/ what was missing)

- Good planning – lessons learned

– other projects / Barts. (Stage

|  | Consequences |  |  |  | Lesson Learnt |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | (what was achieved/ was not achieved because of this) |  |  |  |  |  |
|  | During the planning stage, the Project |  |  |  | Use lessons from other |  |

Owner

Trust /

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 19 of 50

Gates/AHP’s/Dual Keying)

- Job Plans

- Risk Management

10.	Workstreams

Management Team went to a great deal of effort to learn the lessons from other Projects that had happened at the trust and other deployments that had taken place elsewhere in the National Programme and built those measures into the plan for UHMB.

Good structured method of being able to monitor progress being made by staff. Perhaps overcomplicated compared to what staff were used to using.

It was effective in bringing different workstreams together.

Was time consuming from a workstream manager point of view.

Needed to come in earlier in the planning stage

There was a distinct change in how the Trust managed the risk and issues within the project. These were logged by the workstream leads in the first instance through the job plans. They were then managed by the Project Managers

The Risk log was then sent to CFH to hold within their TDB to be managed.

The set up of the workstream with a lead in each area spawned an enthusiasm for them to work in a fashion

| comparable sites to UHMB i.e. |  | CSCA |
| --- | --- | --- |
| Care Trusts; Acute Trusts etc. |  | PMs |
| Compare apples with apples. |  |  |

| Less detailed job plans but |  | Trust |
| --- | --- | --- |
| continue to use. The job plans |  |  |
| should include a start and end |  |  |
| date of each activity to allow |  |  |
| better monitoring. |  |  |
| Communications down needs to |  |  |
| be better to include others not at |  |  |
| meetings. |  |  |

Clinical Risk assessment needs Trust to be done from the beginning

Logging of issues needs to be clearer

Need to have a good triage

process

Need to have a good process in place for clinical risk

| Clear focussed ownership of |  | Trust |
| --- | --- | --- |
| worksteams is effective |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 20 of 50

|  |  |  |  |  |  |  |  | where decisions in one area could then |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | be assessed by the other leads, so that |
|  |  |  |  |  |  |  |  | they were not working in silos. |
|  | 11. |  |  |  | CSCA project planning | and |  |  | Project had to adopt a very fast moving. |  |
|  |  |  |  |  | reporting |  |  |  | CSCA Project governance needed to be |  |
|  |  |  |  |  |  |  |  |  | a lighter touch. For example, MS project |  |
|  |  |  |  |  |  |  |  |  | plans were too large for fast moving |  |
|  |  |  |  |  |  |  |  |  | environment The plans for delivery |  |
|  |  |  |  |  |  |  |  |  | changed on a daily basis and very often |  |
|  |  |  |  |  |  |  |  |  | these changes were significant. The |  |
|  |  |  |  |  |  |  |  |  | reporting and planning | requirements |  |
|  |  |  |  |  |  |  |  |  | were considerable. In addition there |  |
|  |  |  |  |  |  |  |  |  | was | repetition | of | information |  |
|  |  |  |  |  |  |  |  |  | requirements and ad hoc requests. The |  |
|  |  |  |  |  |  |  |  |  | result was a full additional PM was |  |
|  |  |  |  |  |  |  |  |  | required just to manage this for the |  |
|  |  |  |  |  |  |  |  |  | project |  |  |  |  |
|  | 12. |  |  |  | Daily 0800 calls |  |  | Daily 8 AM calls were established with |
|  |  |  |  |  |  |  |  | all stakeholders (SHA, CfH, CSCA & |
|  |  |  |  |  |  |  |  | Trust). Senior managers from all |

organisations had invitations. This

allowed everyone to be fully up to speed

and issues to be dealt with. T0 10 day

rolling plan was the collateral.

Simplify reporting to one single route / format. PMO resources more connected and informed about on- site challenges. Plans simplified to cope with rapid change and not linked to other plans automatically.

Very effective to have daily calls for all parties for EA projects

Trust

Trust /

CSCA

5.4. Training

|  | Id |  |  | Observations |  | Consequences |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (what went well/ what went badly/ what was |  | (what was achieved/ was not achieved because of this) |  |
|  |  |  |  | missing) |  |  |  |
|  | 13. |  |  | The biggest impact of the Stage |  | The changes in build over time also |  |
|  |  |  |  | Gate crash in January 2010 was |  | subsequently changed the processes. |  |

| Lesson Learnt |  | Owner |
| --- | --- | --- |
| The single instance model is |  | CSCA |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 21 of 50 |

with End User Training. The Trust had 3500 staff to train in 10 weeks. This was delivered on a build that for the vast majority of the training was several versions out of date.

- In addition the delay in the go-live date meant that refresher training needed to take place and not all staff attended this training and hence the gap between training and go live for a considerable number of staff was several weeks.

- The Trust adopted Guru as a means to ensure that the most up to date processes were used by end users

- The Trust use of a ‘Wiki’ to store

the content of known workarounds –

A lot of the noise and confusion post go - live regarding how to use the system is attributable to the fact that the training plan that was put together could not be delivered due to the infrastructure and changes in plan.

Post go-live, GURU was made available to supplement the training that staff had received on the lead up to go-live. Guru is a fantastic product that contains the standard UHMB way to use the system. It was also a good way to ensure that end users got consistent messages from floorwalkers. However, post go-live the system has not really been fully utilised, this was mainly because of the stress of go-live, and end users were intent on doing their day to day job and using Guru impacted on this valuable time.

Floorwalkers did not stop the calls coming in to helpdesk

Used as a repository for workarounds pre-post go-live. Not widely, fully used by Project staff/Floorwalkers. Although

sufficient for a steady state business usual but not for the Early Adopter model. An alternative training solution is required to support the EA’s

| Do not train until you are sure |  | CSCA / |
| --- | --- | --- |
| you have a Project that is 95% |  | Trust |
| sure that it is going live. |  |  |
| Consider all workstreams: |  |  |
| Issues raised by trainers were |  |  |
| sometimes ignored. |  |  |
| Implement GURU on the lead |  | Trust |
| up to the go-live to get staff into |  |  |
| the habit of using GURU on the |  |  |
| lead up rather than during the |  |  |
| noise immediately post go-live. |  |  |
| Better engagement with |  |  |
| floorwalkers at the start. |  |  |
| Minimum criteria for floorwalkers |  |  |
| Get floorwalkers to get involved |  |  |
| in the actual areas beforehand |  |  |
| Rolling training programme |  |  |
| being adopted by the Trust to |  |  |
| pick up areas of bad practice |  |  |
| Perhaps implemented too late in |  | Trust |
| the day. Wider use earlier in the |  |  |
| project. |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 22 of 50

- Trainers – part of project team.

- Trainers as part of testing

- Specific training to Trust ‘service leads’ and users should have been made available for Lorenzo Operational Reporting.

- Strategic vs. Tactical Training environments

initially this proved useful in determining what workarounds were in place, as the project progressed post –go-live, this proved to be very time consuming

Good that the trainers were embedded in the project team. Aware of changes in each build, implications of changes in process on training, etc.

The trainers became part of the testing cycle and as such were flushing out issues that were different from other testing resources.

This brought a great deal of experience into the testing and visa versa allowed trainers to learn a great deal in addition to TtT

Users (outpatient clerks for example) were not aware of the choices available to them in the Lorenzo reports and what selection would be fit for their business purposed.

As a result they often chose a report not best suited for their needs and thought it ‘broken’ when they did not get results they expected. This meant service desk calls were raised.

The strategic training environment whilst effective for a BAU situation. Was not agile enough to stay up to date with the rapidly changing software.

Recommend that this is done for other projects.

Avoid trainers being embedded in project team too late

Trainers to be involved in testing for EA projects

Training should include a section for operational reports and the trust should agree as part of their organisational procedures which reports are most useful for which areas (outpatients, inpatients etc)

Early adopters need to have tactical training environments available and the ability to upgrade these rapidly.

CSCA /

Trust

CSCA /

Trust

Trust

PM/Trust

Training

Lead

CSCA

Training

lead

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 23 of 50

Tactical environments were required to

be delivered to allow the trust to test on

builds close to the go-live or production

builds

5.5. Business Change

Id	Observations	Consequences	Lesson Learnt	Owner

(what went well/ what went badly/ what was missing)

(what was achieved/ was not achieved because of

this)

| 21. |  | Future | state | Business |  | Changes were still being made too far | Future state Business | Trust/CSCA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Processes | were | developed |  | into the implementation | Processes need to be |  |
|  |  | along the way and changed |  |  | established early on in the |  |
|  |  | along the way |  |  |  | project as part of a readiness |  |
|  |  |  |  |  |  |  | assessment |  |

| 22. |  | Change management issues |  | Remedial change management | work | Future state Business |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | were still being identified up to |  | was required in relation to Access | Processes need to be |
|  |  | and even post go-live |  | Plans, Referral Management, | clinic | established early on in the |
|  |  |  |  | templates and horizons |  | project verified and owned by |
|  |  |  |  |  |  | the Operational Managers to |
|  |  |  |  |  |  | ensure compliance. |

Trust

Change

Lead

|  | 23. |  |  |  | The Business Change Team for |  |  | The Trust asked CFH to provide a | CfH assistance for | future | Trust/CfH |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | UHMB |  |  | team of individuals to assist in the | similar work on EAs |  |  |
|  |  |  |  |  |  |  |  | Management of Change within the |  |  |  |
|  |  |  |  |  |  |  |  | project. This team did a sterling piece |  |  |  |
|  |  |  |  |  |  |  |  | of work, preparing future state maps |  |  |  |
|  |  |  |  |  |  |  |  | and | also | Standard | Operating |  |  |  |
|  |  |  |  |  |  |  |  | Procedures. |  |  |  |  |  |
|  | 24. |  |  |  | Capacity and demand work |  |  | This requires buy in from all levels of | Ensure the scope of Capacity | Trust |
|  |  |  |  |  |  |  |  | the organisation. Little support from | and Demand (or any additional | Service |
|  |  |  |  |  |  |  |  | managerial | leads was detrimental to | service improvement | type |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 24 of 50 |

|  |  |  |  |  |  |  |  |  |  |  | the achievement of effective capacity |  | activities) work | is | thoroughly | Improvement |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  | and demand planning |  | documented | and | all | involved | Lead(s) |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | parties | have |  | a |  | clear |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | understanding of what is to be |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | undertaken | including | the |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | delivery dates (this work may |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | need to be done outside of |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | project timescales). |  |  |  |  |  |
|  | 25. |  |  |  | The value | of | information |  |  |  | The information department were an |  | That Trust’s | acknowledge the | Trust PM |  |
|  |  |  |  |  | departments | to | the business |  |  |  | overstretched resource, this lead to |  | scale and importance of this |  |  |
|  |  |  |  |  | change process |  |  |  |  | high priority project data being |  | major | change | project | and |  |  |
|  |  |  |  |  |  |  |  |  |  |  | regarded as low priority for the |  | endorse full support from the |  |  |
|  |  |  |  |  |  |  |  |  |  |  | information department |  | information | department | to |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | provide vital data at an |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | operational level |  |  |  |  |  |  |
|  | 26. |  |  |  | Change Workshops |  |  | On several occasions there was lack of | To ensure all parties involved | Trust/CSCA |  |
|  |  |  |  |  |  |  |  |  |  | commitment from other involved | are organised and hold the |  |  |
|  |  |  |  |  |  |  |  |  |  | parties which made objectives difficult | correct information to be able |  |  |
|  |  |  |  |  |  |  |  |  |  | to achieve | to deliver. |  |  |  |  |  |  |  |
|  | 27. |  |  |  | Change Workshops |  |  |  | On occasions we did not engage a |  | Engage with a good cross | Trust |  |
|  |  |  |  |  |  |  |  |  |  |  | good cross section of people |  | section | of | employees | from |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | managers to those on the shop |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | floor |  |  |  |  |  |  |  |  |
|  | 28. |  |  |  | Change Workshops |  |  |  | On the whole the workshops were very |  | Contact | all | involved | parties | Trust/CSCA |  |
|  |  |  |  |  |  |  |  |  |  |  | well organised and delivered to a high |  | prior to event ensuring they |  |  |
|  |  |  |  |  |  |  |  |  |  |  | level this in turn allowed us to develop |  | hold the most correct and up to |  |  |
|  |  |  |  |  |  |  |  |  |  |  | future state |  | date information. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | CSC staff at workshops need |  |  |

to be knowledgeable in their

field to assist effectively in the

workshops.

Change  Team  in  for  longer

following go-live.

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 25 of 50

5.6. Stakeholder Engagement and Comms

| Id |  | Observations |  | Consequences |
| --- | --- | --- | --- | --- |
|  |  | (what went well/ what went badly/ what was |  | (what was achieved/ was not achieved because of |
|  |  | missing) |  | this) |
| 29. |  | Comms Lead for the project |  | The project got an individual to take on |
|  |  |  |  | the communication role. Although this |
|  |  |  |  | was further down the line of the project |
|  |  |  |  | it provided a valuable resource to help |
|  |  |  |  | in the general comms of the project. |
|  |  |  |  | This was more professional and |
|  |  |  |  | provided a better corporate image to |
|  |  |  |  | the project. |

Lesson Learnt

That the project has a full time communications lead.

Owner

Trust PM

- Good focus upon benefits to the patient, the organisation and LHC partners (GP’s)

- Engagement from other parties

Good development across the team of what the key benefits were, this helped achieve buy in from owners, good development of a benefits tracker

Engagement from clinicians was often ignored

Clinicians and admin staff involved with project expressed a view that the time spent on providing expertise to the project has often been ignored or over-ruled as their advice is not reflected in the usability and intuitive behaviour of the application.

Needed to be greater engagement from Admin and clerical staff and

Use clinical and project leads to validate the development and agreement of benefits – this will help support achievement of relevant benefits

Review development process.

Closer relationships between organisations is improving.

Trust

Benefits

Lead

Trust/CSCA

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 26 of 50 |

|  |  |  |  | developers. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 32. |  | CSCA account wide briefings |  | Briefings on the plan to | all | CSCA |  | Recommend this is done for all |  |  |
|  |  |  |  | internal parties proved to be very |  | EA cut-over plans on a regular |  |  |
|  |  |  |  | effective. | This was | particularly |  | basis and is essential for all |  |  |
|  |  |  |  | effective for cut over plan and they |  | stakeholders |  |  |  |  |  |
|  |  |  |  | were very widely attended. |  |  |  |  |  |  |  |  |  |
| 33. |  | Parallel runs |  | A Full business run though against the |  | Recommend | this is | repeated |  |  |
|  |  |  |  | latest build | and migrated | data. | This |  | elsewhere. | However | the |  |  |
|  |  |  |  | allowed very detailed proving of the |  | customer reaction | to | “beta” |  |  |
|  |  |  |  | application and for the customer to |  | software needs to be very |  |  |
|  |  |  |  | rehearse all business process in a |  | carefully managed. |  |  |  |  |
|  |  |  |  | realistic environment. |  |  |  |  |  |  |  |  |  |

5.7. Benefits Planning and Realisation

Id	Observations	Consequences	Lesson Learnt	Owner

(what went well/ what went badly/ what was missing)

(what was achieved/ was not achieved because of

this)

| 34. |  |  | Benefits Lead for the project |  |  | The Trust employed a specific | That the project has a full-time |  | Trust PM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | individual to this post. They worked | Benefits lead. |  |  |
|  |  |  |  |  |  | closely with CFH (Emily Lahey) and |  |  |  |
|  |  |  |  |  |  | also with the SHA (Barbara Smith |  |  |  |
|  |  |  |  |  |  | and Jeremy Wilkinson). |  |  |  |
| 35. |  |  | Benefits Tracker |  |  | This small team were able to evaluate | Suggest focus on top 10 |  | Trust Benefits |
|  |  |  |  |  |  | the project and its benefits to focus | benefits |  | Lead |

on the “top ten” issues. These were

then tracked along the project

This team helped align the project to

the wider benefits realisation of the

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 27 of 50 |

|  |  |  |  |  |  | programme |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 36. |  | Enthusiastic | engagement of |  | Unsteady improvement groups | and | Make | sure stakeholders | are |  | Trust |
|  |  | key stakeholders at an early |  | misalignment of stakeholders | with | involved | with | benefits | work |  | Benefits/Comms |
|  |  | stage is vital to ensure smooth |  | benefits work. Potential to impact | from the very start of the |  | Lead |
|  |  | collection of baseline data |  | upon key go-live measures and will | project. Regular updates from |  |  |
|  |  |  |  |  |  | have an effect on benefits realisation | the | benefits | manager | to |  |  |
|  |  |  |  |  |  |  |  | improvement | groups | is |  |  |
|  |  |  |  |  |  |  |  | important and an active role |  |  |
|  |  |  |  |  |  |  |  | for stakeholders with benefits |  |  |
|  |  |  |  |  |  |  |  | work should be encouraged |  |  |
| 37. |  | Putting measures in place for |  | Those affected by the changes | Anonymous | opinion |  | Trust |
|  |  | staff to | express | opinions |  | should always have an outlet for their | questionnaires | have allowed |  | Benefits/Comms |
|  |  | regarding | the | changes |  | views. This will boost morale. If | staff to express their thoughts |  | Lead |
|  |  | provides an outlet for both |  | possible, these views should be | directly to those who will listen |  |  |
|  |  | negative and positive feedback |  | made public in forum so users can | which in turn reduces negative |  |  |
|  |  |  |  |  |  | see other users opinions |  | ‘gossip’ | within | departments |  |  |
|  |  |  |  |  |  |  |  | and assures staff that they are |  |  |
|  |  |  |  |  |  |  |  | being listened to and that their |  |  |
|  |  |  |  |  |  |  |  | opinion is valid and valued. |  |  |

| 5.8. | Design |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Id |  |  | Observations |  | Consequences |  |  |  | Lesson Learnt |  |  |  | Owner |  |
|  |  |  | (what went well/ what went badly/ what was |  | (what was achieved/ was not achieved because of this) |  |  |  |  |  |  |  |  |  |
|  |  |  | missing) |  |  |  |  |  |  |  |  |  |  |  |

- Software Delivery and design. RTT was promised in 620, then 620.1, Recommend more realistic and The term ‘Jam Tomorrow’ was Then 621, then 621.1, then 622. This accurate predicting of when used many times within the became 622 SP3 but some more is issues will be resolved Project to describe the design coming in 625.

and delivery of the software.

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 28 of 50

39.	Usability

- Design and Development Leads on EA customer site

Make it impossible to plan/test...do anything really. Most work streams were affected by this in the run up to go-live.

The system needs to be more user friendly or intuitive. In certain circumstances the number of clicks has increased either to complete a process or to find the information you are looking for.

A common complaint is that if you don’t find what you are looking for first time, it is very difficult to find what you want within Lorenzo. If you do find something, staff are not confident that what they are seeing is correct.

A number of the med secs are also now using word and copying and pasting into Lorenzo rather than use TXText within Lorenzo.

Design and Development leads for Lorenzo attended on site at key times like Parallel runs and dress rehearsal. This worked well and allowed very clear understanding of issues, suitable prioritisation and urgency from development and fast turnaround of design changes.

The parallel runs were good in that they were able to emphasise usability issues however these need to be taken onto the next level by better replication of real system use. i.e. interruptions to their work. For example users experiencing phone calls whilst booking patients.

Recommend this level of engagement from senior design and development staff for other EAs

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 29 of 50 |

5.9. Solution Localisation

|  | Id |  |  | Observations |  | Consequences |  |  |  | Lesson Learnt |  |  |  |  | Owner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (what went well/ what went badly/ what was |  | (what was achieved/ was not achieved because of this) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | missing) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 41. |  |  |  | Resourcing – This really relates |  | Compounded by time pressure but the |  | We had a core team of people |  |  | Trust PM |  |
|  |  |  |  |  | to access to expert/key resource |  | expert/Key resource for both sites had |  | whom you could rely on to do |  |  |  |  |
|  |  |  |  |  | for both Trust and CSC. |  | to work excessive hours for several |  | the key complex tasks and then |  |  |  |  |
|  |  |  |  |  |  |  | months to keep the project afloat |  | a | larger | number | of |  |  |  |  |
|  |  |  |  |  |  |  | because basically they had too much to |  | inexperienced staff who came in |  |  |  |  |
|  |  |  |  |  |  |  | do. |  | during the latter stages of the |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | project, did add some value |  |  |  |  |
|  |  |  |  |  |  |  | This time pressure came from an |  | eventually but it took a |  |  |  |  |
|  |  |  |  |  |  |  | aggressive/unrealistic time frame and |  | disproportionate amount of time |  |  |  |  |
|  |  |  |  |  |  |  | the fact that in certain areas, the |  | to get these people productive. |  |  |  |  |
|  |  |  |  |  |  |  | configuration of Lorenzo is extremely |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | complex and hence far more time |  | E.g. To help with the creation of |  |  |  |  |
|  |  |  |  |  |  |  | consuming than the equivalent task |  | letter templates. |  |  |  |  |  |  |
|  |  |  |  |  |  |  | would take in Lorenzo. |  |  |  |  |  |  |  |  |  |  |

Lesson is to try and get these

In addition, the software was unreliable	staff involved in the project as

and that caused delay caused by non-	early as possible.

system availability or late delivery. This

was compounded by the fact that certain

‘fixes’  to  letters  and  letter  config  for

example broke some letter templates

that  had  been  finished  and  lead  to

rework on several occasions.

42.	No mechanism to transfer local	This meant that the config team had to	Tools needed earlier to transfer	CSCA

configuration between builds	rebuild all the structure in each new config between builds build which consumed time and

resource.

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

Possible approach would be to build config/Clinics from scratch, take the hit and would book all future appointments – AS PER B WOMENS

guide A Configuration Workbook was not Recommend a config workbook made available to the Trust until very concept is establish early in late into the project. This meant that every EA project

there was no consistency in the approach to managing configuration items and also the knowledge of which items were primary, secondary or tertiary.

Some of the merge fields still not Prioritise letter templates early populating correctly. Still have issues in the project

with transport letters and telephone numbers. Some letters still don’t work as a result.

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 30 of 50 |

| 43. |  | Either in a rush or at the last | This meant that the users and trust have |  | In house script writing is |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | possible moment; due to time | lost some potential features, time |  | essential to build a series of |  |  |
|  |  | constraints, there were also a | savings and benefits that the product |  | scripts that are fit for purpose |  |  |
|  |  | number of config areas that were | could deliver. |  | and work along with the |  |  |
|  |  | not fully explored |  |  | business process. |  |  |  |
|  |  |  | E.g. Access Planning Config such as |  | Better | release | notes | are |  |  |
|  |  |  | Linking Access plans to Preferred |  |  |  |  |  |  |  |
|  |  |  | Clinics/Wards to help stream line the |  | required for each build. |  |  |  |
|  |  |  | process. |  | Where | key | changes | are |  |  |
|  |  |  |  |  | implemented it would be useful |  |  |
|  |  |  |  |  | for someone to sit down and |  |  |
|  |  |  |  |  | explain functionality. |  |  |  |
|  |  |  |  |  | Local TCN triage on a weekly |  |  |
|  |  |  |  |  | basis before being presented to |  |  |
|  |  |  |  |  | IMG. |  |  |  |  |  |

44.	Poor knowledge – config UHMB despite boot camp

45.	Not adequate time allowed building and testing letter templates.

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 31 of 50

- Temporary Locations needed to be added manually go live

- Ward Attender sessions had to be build manually at go live

- Mange referrals – tried to manually add all users into this profile

- Location hierarchy from IPM did not work correctly

- Access Plan Data Capture Sheets

|  | Cutover time |  |  |  | Solution required to avoid this |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cutover time |  |  |  | Solution required to avoid this |  |  |  |
|  | Not all users could accept referrals at go |  |  |  | Solution required to avoid this |  |  |  |
|  | live |  |  |  |  |  |  |  |
| Numerous Location migrated over with |  |  | Solution required to avoid this |  |  |  |
| the same name |  |  |  |  |  |  |
|  | Access Plan Profiles assigned to wrong |  |  |  | Solution required to avoid this |  |  |  |
|  | care providers. Access Plan Owner |  |  |  |  |  |  |  |
|  | Lorenzo In-tray kept crashing as too |  |  |  |  |  |  |  |
|  | many messages in the Inbox |  |  |  |  |  |  |  |

5.10. Interfaces

|  | Id |  |  |  | Observations |  |  | Consequences |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | (what went well/ what went badly/ what was |  |  | (what was achieved/ was not achieved because of this) |  |
|  |  |  |  |  | missing) |  |  |  |  |
|  | 51. |  |  |  | Full suite of departmental for test |  | All departmental were available for key |
|  |  |  |  |  |  |  | testing. This was sometimes |
|  |  |  |  |  |  |  | inconsistent but was essential for |
|  |  |  |  |  |  |  | effective end to end testing |
|  | 52. |  |  |  | Arrival Booths could have been |  | Arrival Booths were to be utilised at |
|  |  |  |  |  | utilised better at the time of go- |  | UHMB from go-live, this would have |

Lesson Learnt	Owner

Ensure departmental available on test / DRH environment. Ensure access and make testing of interfaces public.

Recommend arrival booth

strategy to de-risk

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 32 of 50

live

- CAB Messaging not tested on dual tower architecture

been particularly useful in reducing queues mainly in outpatient areas and would have reduced the stress to reception staff. As a result of some technical issues relating to the interface it was decided not to use them until after until after go-live

Wholesale failure CAB booking after go live

implementation issues causing operational difficulties

CAB to be tested in 2 tower

approach

5.11. Data Migration

|  | Id |  |  |  | Observations |  |  | Consequences |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | (what went well/ what went badly/ what was |  |  | (what was achieved/ was not achieved because of this) |  |
|  |  |  |  |  | missing) |  |  |  |  |

| Lesson Learnt |  | Owner |
| --- | --- | --- |

- Data Migration - The original plan was predicated on getting Data migration stable before Cycle testing commenced.

- New vs. Migrated records

- Validation within iPM

This failed dismally as it was Cycle 1 before we got out first full data load. (Data migration was late and of poor quality throughout all the data loads).

Lorenzo performs far better when you are using a brand new record against brand new config. A number of the issues being encountered in production are due to the fact the way that the Data Migration is colliding with the config.

With regards to 18ww, iPM allowed staff to put data in with little or no validation. Lorenzo has far more validation but the

| DM solution required for this. |  | DM |
| --- | --- | --- |
| Needs to be reviewed against |  | Lead(s) |
| new provider |  |  |
| DM solution required for this. |  | DM |
| Needs to be reviewed against |  | Lead(s) |
| new provider |  |  |
| DM solution required for this. |  | CSCA |
| Needs to be reviewed against |  | Design |
| new provider |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 33 of 50 |

|  |  |  |  |  |  |  |  | combination of change and mapping |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | has caused problems for the end users. |  |  |  |  |  |  |  |  |  |
|  | 57. |  |  |  | DM loads slow and poor quality |  |  | Data migration times were also |  |  |  | DM solution required for this. |  |  |  | DM |  |
|  |  |  |  |  |  |  |  | extremely slow, the migration tools |  |  |  | Needs to be reviewed against |  |  |  | Lead(s) |  |
|  |  |  |  |  |  |  |  | lagged behind our current build, were |  |  |  | new provider |  |  |  |  |  |
|  |  |  |  |  |  |  |  | poor quality when delivered and poorly |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | documented. |  |  |  |  |  |  |  |  |  |
|  | 58. |  |  | UHMB had a plan post go-live – |  | Trust Data Issues – CSC Application |  |  |  | DM process needs to continue |  |  |  | DM |  |
|  |  |  |  | Deliver software fixes, room data |  | issues. |  |  |  | post go-live to resolve / script |  |  |  | Lead(s) |  |
|  |  |  |  | fixes – this did not happen |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | issues |  |  |  |  |  |
|  | 59. |  |  |  | CFH resources supporting Data |  | The resources supplied by CFH in |  |  | Recommend experienced |  |  |  | DM |  |
|  |  |  |  |  | Migration |  | supporting Migration were excellent, |  |  | resource sourced for this activity |  |  |  | Lead(s) |  |
|  |  |  |  |  |  |  | particularly Mujaid Khan and Mike |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Turner. |  |  |  |  |  |  |  |  |
|  | 60. |  |  |  | Logging Migration Issues |  |  | These were initially logged in Quality |  |  |  | Recommend better collaborative |  |  |  | DM |  |
|  |  |  |  |  |  |  |  | centre, so that they had some visibility, |  |  |  | work between Dev & DM |  |  |  | Lead(s) |  |
|  |  |  |  |  |  |  |  | from the Trust perspective, however |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | they were not given the focus they |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | deserved from a CSC perspective. |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Issues were lost between CSCS |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Development and CSCA DM |  |  |  |  |  |  |  |  |  |
|  | 61. |  |  |  | The vast majority of issues |  |  | Large number of issues that could |  |  |  | All of the issues encountered |  |  |  | DM |  |
|  |  |  |  |  | encountered post go-live have |  |  | possibly be avoided |  |  |  | post go-live need to be fed back |  |  |  | Lead(s) |  |
|  |  |  |  |  | been down to data migration. |  |  |  |  |  |  | to the DM team to ensure that |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | they do not happen at the next |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | cutover. |  |  |  |  |  |
|  | 62. |  |  |  | Data Migration team and Product |  |  | Took a long time to agree what type of |  |  |  | Recommend better collaborative |  |  |  | DM |  |
|  |  |  |  |  |  |  |  |  |  |  |  | work between Dev & DM |  |  |  | Lead(s) |  |
|  |  |  |  |  | Specialists need to work more |  |  | issue it was |  |  |  |  |  |  |  |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 34 of 50 |

closely with each other. These 2 teams are key to a successful deployment – there was too much blame between what was a DM issue and what was an Application Issue

- Data Migration of Clinics should have been tested more thoroughly within Dress Rehearsals.

- Choose and Book service ID’s not migrated correctly

- Data Migrated with no referral attached

Problems with Physio clinics within trust. Unable to restructure numerous clinics

Not al slots available within Choose and Book

RTT issues – unable to create follow up bookings

DM solution required for this. Needs to be reviewed against new provider

DM solution required for this. Needs to be reviewed against new provider

DM solution required for this. Needs to be reviewed against new provider

DM

Lead(s)

DM

Lead(s)

DM

Lead(s)

5.12. Deployment Testing

|  | Id |  |  |  | Observations |  |  |  | Consequences |  |  |  | Lesson Learnt |  |  |  | Owner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | (what went well/ what went badly/ what was |  |  |  | (what was achieved/ was not achieved because of |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | missing) |  |  |  | this) |  |  |  |  |  |  |  |  |  |  |
|  | 66. |  |  |  | Proving to Cycle Testing to |  |  |  | Parallel Runs excellent/rapid method |  |  |  | The trust went live with a |  |  | CSCA |  |
|  |  |  |  |  | Parallel Runs to full Dress |  |  |  | of identifying bugs |  |  |  | number | of | temporary |  |  | Programme |  |
|  |  |  |  |  | rehearsal; |  |  |  |  |  |  |  | workarounds | that | had been |  |  | Management |  |
|  |  |  |  |  |  |  |  |  | Parallel Runs – The Parallel runs were |  |  |  | agreed with | the organisation, |  |  |  |  |
|  |  |  |  |  |  |  |  |  | extremely valuable in pointing out |  |  |  | on the proviso that fixes were |  |  |  |  |
|  |  |  |  |  |  |  |  |  | areas of the system that needed |  |  |  | delivered at 2w, 6w, 12w and |  |  |  |  |
|  |  |  |  |  |  |  |  |  | improvement – far better than any |  |  |  | 16w. By the time the 6 weeks |  |  |  |  |
|  |  |  |  |  |  |  |  |  | laboratory type testing. However, a |  |  |  | fixes were delivered, this would |  |  |  |  |
|  |  |  |  |  |  |  |  |  | degree of pressure was placed on the |  |  |  | have delivered a clean and |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Trust staff to score a pass mark for |  |  |  | stable process. |  |  |  |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 35 of 50

- During cycle testing actual users from hospital departments were used to assist Health Informatics

- During the parallel run testing consideration was only given to a number of operational reports that would be tested and not WHO would conduct this testing.

(There was one Trust resource leading on Operational reports testing and they were expected to cover all areas of functionality.)

their area (7/10) with the proviso that certain fixes would be delivered later.

Having actual users helping to test during the test cycles meant that the Trust were able to verify test scripts and validate understanding of business process as they went along

The trust resource worked in Health Informatics and they did not have detailed knowledge of outpatient procedures, coding and grouping etc. This meant they could not realistically comment on a report being fit for purpose, content accuracy etc.

Issues were missed and picked up much later in the project so operational

We are currently at 6 months plus and the trust have not had all their 2 week fixes delivered with the latest plan promising delivery of these 2w fixes at 16 weeks.

These known issues with the product are impacting usability, performance and undermining user confidence and with hindsight this approach was a high risk strategy assuming that the software supplier and LSP would deliver.

Recommend real users involved in testing

Prior to deployment testing starting consideration must be given to the business processes – when will reports be used by the trust in the functional areas and this should be built into the test plan.

The ‘true users’ should also

Trust PMs

Trust

PM/CSC PM

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 36 of 50 |

In addition to this testing of operational reports was done in isolation and was not fully integrated into testing of different functional/business areas e.g. inpatients.

reports were not fit for use in some areas.

Example: Waiting list clerks discovered on day 1 of ‘live’ that the access planning reports were not fit for purpose as they included irrelevant information yet did not include information vital to managing a waiting list. Had they been involved in early deployment testing this would have been highlighted.

conduct this testing. They will have greater understanding of the different scenarios the reports will be used in. Example: If an outpatient receptionist runs a clinic list in iPM for a consultant every Tuesday prior to clinic then it is reasonable to expect that user to test the equivalent report in Lorenzo in the same way.

| 69. |  | Need to have CAB, iPM and |  | It is not ideal to have to use PROD for |
| --- | --- | --- | --- | --- |
|  |  | Lorenzo available in the same |  | this sort of testing. |
|  |  | Spine environment. The team at |  |  |
|  |  | UHMB managed to arrange 2 |  |  |
|  |  | sets of cutover testing using |  |  |
|  |  | PROD! |  |  |

Get iPM setup in same environment as DEPLOR526.

Trust

PM/CSC PM

- CAB testing

- MHS Testing

The Trust spent a great deal of time testing Lorenzo / CAB functionality. Since the go-live we have only identified one code issue.

On the cutover weekend a large percentage of CAB bookings were not reaching the booked state. It was discovered that this was down to having 2 MHSs in PROD.

Recommend thorough CAB testing

Make the test environments mimic the PROD environment more accurately.

Trust

PM/CSC PM

CSCA

programme

Management

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 37 of 50 |

| 72. | ‘One team’ approach worked well | Less conflict and recognition of all |
| --- | --- | --- |
|  | i.e. CSCA/UHMB | and CfH |  |
|  | working in tandem | to achieve | parties to work to same objectives |

same goal

| Recognition of |  |  | Trust |  |
| --- | --- | --- | --- | --- |
|  |  |  | PM/CSC PM |  |
| common/understood |  |  |  |  |
| aims/objectives at the outset |  |  |  |  |

- Testing carried out over 2 sites over a wide geographical area

- Irregular daily (commence/completion)wash-ups

Difficult to manage daily testing activities and in particular the resources when often we didn’t know until short notice which site staff would be required. Created confusion and complexity in the overall management

It was not always clear what activities needed to be performed on a particular day nor what the state of progress was at any given time

|  | Co-locate all of the testing |  |  |  | Trust |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | activities |  |  |  | PM/CSC PM |  |
|  | Discipline of having a daily |  |  |  | Trust |  |
|  | wash-op before /after each |  |  |  | PM/CSC PM |  |
|  | testing day |  |  |  | (Test |  |
|  |  |  |  |  | Managers) |  |

| 75. |  | Trust staff not always available to |  | Delays to schedule and/or CfH |
| --- | --- | --- | --- | --- |
|  |  | support due to numerous |  | providing substitutes which often still |
|  |  | commitments |  | resulted in repeating of testing |

| Better availability of staff to |  |  | Trust |  |
| --- | --- | --- | --- | --- |
| support |  |  | PM/CSC PM |  |

- At Go live we found issues with trying to transact data on migrated data

- Scanning testing

When completing dress rehearsals – although we had migrated data on the environment – we tested on newly created Patients/Clinics/Access Plans/Wards.

Scanning not tested within parallel runs

|  | Should have completed activity |  |  |  | Trust |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | on Migrated Patients / Clinics / |  |  |  | PM/CSC PM |  |
|  | Wards |  |  |  |  |  |
|  | Test scanning |  |  |  | Trust |  |
|  |  |  |  |  | PM/CSC PM |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 38 of 50 |

5.13.RBAC / SSO

|  | Id |  |  | Observations | Consequences |  |  | Lesson Learnt |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (what went well/ what went badly/ what was | (what was achieved/ was not achieved because of |  |  |  |  |
|  |  |  |  | missing) | this) |  |  |  |  |

Owner

- RBACbuild  inconsistent  with  each

- Need RBAC knowledge at project level

- Need wider involvement of users in RBAC discussions (and earlier in project)

RBAC worked differently with each build. It was hard to establish source of the issue

We would have vastly benefited from a CSC Product Specialist on hand who knew and understood RBAC. We had support from Kerandeep who only knew RBAC and the Product Specialists who only knew the system

Dedicated RBAC reps on EA site

Dedicated RBAC reps on EA site

Inclusion of

departmental/service

managers when creating the

RBAC matrix

More involvement with end users at an earlier stage

CSCA

Programme

Management

CSCA

Programme

Management

Trust

5.14. Cut-over

| Id |  | Observations |  |  | Consequences |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | (what went well/ what went badly/ what was |  |  | (what was achieved/ was not achieved because of |  |
|  |  | missing) |  |  | this) |  |
| 81. |  | Full E2E dress rehearsal was |  |  | This proved very useful in order to |  |
|  |  | good –; |  |  | determine exact timings of activities |  |
|  |  |  |  |  | over the actual cutover period. It also |  |
|  |  |  |  |  | identified whether the resources were |  |

|  | Lesson Learnt |  |  |  | Owner |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | CSC need to prove their ability |  |  |  | CSCA |  |
|  | to fix issues in dress rehearsal |  |  |  | Programme |  |
|  | so that Projects can have the |  |  |  | Management |  |
|  | assurance that during actual |  |  |  |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 39 of 50 |

|  |  |  |  |  |  |  |  |  | adequate for activities |  |  |  | cut over issues will be fixed in a |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  | timely manner. |  |  |  |  |  |  |  |
|  | 82. |  |  |  | The Trust and CSC had some |  |  |  | The parallel runs allowed the Trust to |  |  |  | Establish cut-over as a |  |  |  |  | CSCA |  |
|  |  |  |  |  | excellent resources to assist with |  |  |  | get some very accurate timings |  |  |  | dedicated discipline in |  |  |  |  | Programme |  |
|  |  |  |  |  | the planning of activities for the |  |  |  | required for activities during the |  |  |  | deployment |  |  |  |  |  |  | Management |  |
|  |  |  |  |  | actual cutover. |  |  |  | cutover. The work provided by Mandy |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Williams and Matt Webster was |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | exemplary. CSC also had good |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | individuals in Stacie Hughes and Nick |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Allen and together they provided a |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | good cutover team. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 83. |  |  |  | As part of floorwalking activities |  |  | Vocera badges proved a very useful |  |  | If adopting this technology |  |  |  | Trust |  |
|  |  |  |  |  | the Trust made good use of |  |  | communications medium. It allowed |  |  | ensure | that | all | the |  |  |  |  |  |
|  |  |  |  |  | Vocera Badges. |  |  | the Control Rooms to communicate |  |  | communication black spots are |  |  |  |  |  |
|  |  |  |  |  |  |  |  | effectively with floorwalkers and to |  |  | identified. |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | provide new information to them |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | quickly. |  |  |  |  |  |  |  |  |  |  |  |
|  | 84. |  |  |  | Operational reports were not fully |  |  | It was assumed on Day 1 of ‘live’ that |  |  | Ensure operational report |  |  |  |  | Trust |  |
|  |  |  |  |  | tested as part of business |  |  | all operational reports would be fully |  |  | testing is included in the cut |  |  |  |  | PM/CSC PM |  |
|  |  |  |  |  | process and there was not a |  |  | working and content correct. |  |  | over plan as part of each |  |  |  |  |  |  |
|  |  |  |  |  | named resource made available |  |  | Although 80% of reports were |  |  | functional area. |  |  |  |  |  |  |  |
|  |  |  |  |  | by the trust to test them in |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | isolation either. |  |  | populated users quickly raised issues |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | around format and content and as |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | such the trust made the decision to |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | cease using Lorenzo reports entirely. |  |  |  |  |  |  |  |  |  |  |  |
|  | 85. |  |  |  | The cutover plan was very |  |  |  | We have seen issues in the past with |  |  |  | Detailed cut-over plan and |  |  |  |  | CSCA |  |
|  |  |  |  |  | detailed and accurate. |  |  |  | such things as batch DoS migration. |  |  |  | dedicated manager |  |  |  |  |  | Programme |  |
|  |  |  |  |  |  |  |  |  | No such issues were encountered at |  |  |  |  |  |  |  |  |  |  | managment |  |
|  |  |  |  |  |  |  |  |  | UHMB. |  |  |  |  |  |  |  |  |  |  |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 40 of 50 |

5.15. Post Go-Live Deployment Issues

Id	Observations

(what went well/ what went badly/ what was missing)

86.	Issue Management.

- Chennai support needed

- Coding and grouping – several files – e.g. Gender Validation – where not there on Lorenzo Build

| Consequences | Lesson Learnt | Owner |
| --- | --- | --- |
| (what was achieved/ was not achieved because of this) |  |  |

| There are too many people in the loop |  | Have one system for issues |  |  |  | EA Trust |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| and hence too many parts of the end to | management of at least a single |  |  |  | & CSCA |  |
| end journey/people involved in getting | version of the truth |  |  |  |  |  |
| something fixed that mean that the |  |  |  |  |  |  |
| overall issue management process is |  |  |  |  |  |  |
| broken. |  |  |  |  |  |  |

Focus list that wasn’t in focus.

Despite all this effort put in by all parties,

the trust still don’t have 100% clarity on

precisely	what	issues	have	been

delivered	when	they	receive	builds,

service packs and hot fixes. E.g. During

the upgrade to 633.1.6 in August, the

Trust	had	no	clear	release

notes/documentation from CSC as to

what they had delivered.

| There was too much reliance on the | Issues are owned by Issues | SDM |
| --- | --- | --- |
| Chennai team for early live support | Resolution and Chennai team |  |
|  | should be there to assist. |  |
| Unable to test Coding and Grouping to | Ensure C&G fully set up for test | CSCA |
|  |  | PM |
| full extent |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 41 of 50 |

5.16. Service Delivery

|  | Id |  | Observations |  |  | Consequences |  |  |  | Lesson Learnt |  |  |  | Owner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (what went well/ what went badly/ what was |  |  | (what was achieved/ was not achieved because of this) |  |  |  |  |  |  |  |  |
|  |  |  | missing) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 89. |  |  | Service Management Approach |  |  |  | Standard | Service | Management |  |  | Room available for |  |  |  | SDM |  |
|  |  |  |  |  |  |  |  | approach is not suitable for an Early |  |  | developers/data migration staff |  |  |  |  |  |
|  |  |  |  |  |  |  |  | adopter. |  |  |  |  | to quickly turn issues around on |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | site. |  |  |  |  |  |
|  | 90. |  |  | Scripts stop running |  |  | In addition to scripts running on a daily |  |  | Ensure scripts run for agreed |  |  |  | SDM |  |
|  |  |  |  |  |  |  | basis to fix gaps in both Application and |  |  | duration |  |  |  |  |  |
|  |  |  |  |  |  |  | CDS. Post | the 633.1.6 | upgrade in |  |  |  |  |  |  |  |  |

August, it transpired that a number of

scripts that CSC were running in the

background	to	help	support	the

production system (i.e. to help address

conflicts in different views of the app)

stopped running and took a number of

days before they were resurrected.

5.17. Infrastructure

|  | Id |  |  | Observations | Consequences |  |  | Lesson Learnt |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (what went well/ what went badly/ what was | (what was achieved/ was not achieved because of |  |  |  |  |
|  |  |  |  | missing) | this) |  |  |  |  |
|  | 91. |  |  |  | The standard and timeliness of |  |  | They generally arrived late and when |  |  |  | The Environments should be |  |
|  |  |  |  |  | Deployment Environments. |  |  | the Trust took deliver, they were |  |  |  | tested prior to the Trust taking |  |
|  |  |  |  |  |  |  |  | unstable with things not working. E.g. |  |  |  | delivery |  |
|  |  |  |  |  |  |  |  | ‘Things that worked yesterday don’t |  |  |  | Joint Touch testing between |  |
|  |  |  |  |  |  |  |  | work today’ following remedial work. |  |  |  |  |  |

Owner

Trust /

CSCA PM

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 42 of 50 |

|  |  |  |  |  | E.g. after a training instance upgrade, |  |  | CSC and the Trust of each |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | PDS no longer worked. The training |  |  | environment |  |  |  |  |  |
|  |  |  |  |  | instance also encountered people |  |  |  |  |  |  |  |  |
|  |  |  |  |  | being randomly booted out for no |  |  |  |  |  |  |  |  |
|  |  |  |  |  | apparent reason. |  |  |  |  |  |  |  |  |
|  |  |  | Communications re Environment |  |  |  |  |  |  |  |  |  |  |
| 92. |  |  |  |  |  | The Trust were consistently losing time |  |  |  | Better comms on Environments |  |  |  | CSCA |  |
|  |  |  | readiness. - |  |  | (especially just pre the Bury Go-Live) |  |  |  |  |  |  |  | Programme |  |
|  |  |  |  |  |  | where the instance was taken away by |  |  |  |  |  |  |  | Management |  |
|  |  |  |  |  |  | CSC and taken down with little or no |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | notice. |  |  |  |  |  |  |  |  |  |

- Upgrades - CSC seem to find it  The upgrade to 633.1.6 in August is a  As a result of the above, no-  CSCA

very difficult to manage reliable prime example that was extremely one could see the good that Programme software upgrades to a plan damaging. The sign off was scheduled the upgrade had introduced Management which don’t cause regression for 14:00 Sunday and took place at because of the bad way in

| issues. | 22:30 on | Monday | to | give | CSC | which the environment and the |
| --- | --- | --- | --- | --- | --- | --- |
|  | additional time to sort out the | final | build was delivered by CSC. |
|  | regression issues. |  |  |  | The upgrade was seen as a big |
|  |  |  |  |  |  | back ward step. |
|  | Due to an error within the application |  |
|  | server config that was applied post |  |
|  | sign off, on the morning of Tuesday |  |
|  | 3rd August, a number of issues were |  |
|  | seen at the Trust with inconsistent |  |
|  | application | behaviour | and | error |  |
|  | messages appearing. | These affected |  |
|  | the vast proportion of the end users |  |
|  | and prevented effective use of the |  |
|  | system for almost the whole day. |  |  |

This	build	also	contained	‘new

undocumented	features’	such	as

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

CSC Alliance Proprietary Information

NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned

Version 1.0	22/02/2011	Page 43 of 50

changing the way that the wild card

worked  and  limiting  the  number  of

rows on the outpatient pegboard that

caused operational mayhem and has

significantly added to the backlog that

the trust was seeking to address.

Post this upgrade, it transpired that a

number	of	scripts	that	CSC	were

running  in  the  background  to  help

support the production system (i.e. to

help address conflicts in different views

of the app) stopped running and took a

number	of	days	before	they	were

resurrected.

|  | 94. |  |  |  | System performance |  | This has been the biggest area that |  |  |  | Recommend | performance |  |  |  | CSCA |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | has affected the project post go-live. |  |  |  | review (In additions it previous |  |  |  | Programme |  |
|  |  |  |  |  |  |  | The fact that iPM allowed staff to have |  |  |  | and on-going work) |  |  |  | Management |  |
|  |  |  |  |  |  |  | multiple | sessions | open | whereas |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Lorenzo does not has been the biggest |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | single | issue. (Not | picked | up in |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | advance of go-live). This means that |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | staff are less efficient as they now |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | have to stop in the middle of what they |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | are doing in the event that they have to |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | deal with telephone enquiries, etc. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | because they can’t multi task. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Progress has been slow in terms of |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | improving performance. |  |  |  |  |  |  |  |  |  |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 44 of 50 |

- System Performance 2.

- During the early stages of the project it was not possible to transfer local config from one Build to another as there was no

mechanism to transfer electronically.

During recent upgrade some of the anticipated performance improvements have not materialised.

Performance is also variable, in that, within the same area of the system you can get different results on different PC’s and also contrasting performance

between different deployment environments. E.g. opening a CDC form in deployment took 3 secs and in prod 27…then on a different day 14...then 3…then 14.

It was very time consuming for the Trust staff to build the configuration into each of the builds. This was an inherent fault of the Builds and it was not until Build 620 that CSC were able to transfer data when upgrading the build.

|  | Recommend | performance |  |  |  | CSCA |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | review (In additions it previous |  |  |  | Programme |  |
|  | and on-going work) |  |  |  | Management |  |

| Tools should be made |  | CSCA |
| --- | --- | --- |
| available so that future Sites do |  | Programme |
| not experience this issue. |  | Management |

5.18. Unforeseen Events

|  | Id |  | Observations |  |  |  | Consequences |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (what went well/ what went badly/ what was |  |  |  | (what was achieved/ was not achieved because of this) |  |
|  |  |  | missing) |  |  |  |  |  |
|  | 97. |  | Weather: |  |  |  | Difficulties in staff attending meetings |  |
|  |  |  | Floods and Snow |  |  |  | due to adverse conditions. |  |

| Lesson Learnt | Owner |  |
| --- | --- | --- |
| Make better use of phone and | Trust | / |
| video conferencing | CSCA |  |
|  | PMs |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 45 of 50 |

5.19. Tools and Methods

|  | Id |  | Observations |  |  | Consequences |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (what went well/ what went badly/ what was |  |  | (what was achieved/ was not achieved because of this) |  |
|  |  |  | missing) |  |  |  |  |

Lesson Learnt	Owner

98.	Use of Camtasia;

5.20. Trust Culture

Id	Observations

(what went well/ what went badly/ what was missing)

This proved valuable in identifying the differences between Lorenzo and iPM in terms of performance and usability and to emphasise to the wider world why changes to functionality were needed.

It also illustrated why different groups of fixes were required.

Consequences

(what was achieved/ was not achieved because of this)

| Use Camastra |  | Trust |
| --- | --- | --- |

Lesson Learnt	Owner

99.	Engagement	of	Divisional	/	The Service Managers and Divisional

Service Managers on the project	Managers had the opportunity months

and months to sort out Clinic Templates

and	were	even	given	training	and

toolkits by the Change Team to help

them sort out their capacity and demand

and chose not to do so.

| Better engagement with Service |  | Trust |
| --- | --- | --- |
| / Divisional Managers to ensure |  |  |
| that they are more engaged pre |  |  |
| and post go-live. |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 46 of 50 |

5.21. Other

|  | Id |  | Observations |  |  | Consequences |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (what went well/ what went badly/ what was |  |  | (what was achieved/ was not achieved because of this) |
|  |  |  | missing) |  |  |  |  |  |
|  | 100 | . | Summary observations |  |  | A number of additional staff are still |
|  |  |  |  |  |  | supporting the stabilisation of the |
|  |  |  |  |  |  | product within the organisation because |
|  |  |  |  |  |  | they are struggling or unable to perform |
|  |  |  |  |  |  | a day’s work in a day without working |
|  |  |  |  |  |  | additional hours. |  |
|  |  |  |  |  |  | The performance of Lorenzo has also |
|  |  |  |  |  |  | highlighted | some | non-standard |
|  |  |  |  |  |  | operational | processes | that were |
|  |  |  |  |  |  | absorbed and lived with when iPM was |
|  |  |  |  |  |  | being used but cannot be carried with |
|  |  |  |  |  |  | Lorenzo. |  |  |

| Lesson Learnt | Owner |  |
| --- | --- | --- |
| Continue to support optimisation | CSCA | / |
| initiative | Trust |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 47 of 50 |

6	Conclusions & Recommendations

In conclusion, there are a number of key observations within this report that will need cascading across organisations both internally and externally to the UHMB Team to ensure lessons are passed on. All agreed owners are to ensure the recommendations are progressed to avoid similar issues within future projects.

The following key points have already been identified as recommendations for future implementations and these were discussed at the lessons learned review workshop held at the end of January 2011.

| Lesson | Recommendation |  | Responsibility |
| --- | --- | --- | --- |
| ID |  |  |  |
| 2 | With the additional communications support aspects of being an Early Adopter make |  | SHA |
|  | arrangements for co-ordination/vetting of information requests. |  |  |
| 5 | Put resource requests in early for additional project team members. |  | Trust/CSCA |
| 7 | Use lessons from other sites. |  | Trust/CSCA |
| 8 | Use less detailed job plans. The job plans should include a start and end date of each activity |  | Trust |
|  | to allow better monitoring. |  |  |
| 13 | The training single instance model is sufficient for a steady state business usual but not for |  | CSCA |
|  | the Early Adopter model. An alternative training solution is required to support the EA’s |  |  |
| 14 | Do not train until you are sure you have a Project that is 95% sure that it is going live. |  | Trust/CSCA |
| 15 | If using GURU, implement on the lead up to the go-live to get staff into the habit of using |  | Trust |
|  | GURU on the lead up rather than during the noise immediately post go-live. |  |  |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 48 of 50 |

| 17 | Ensure trainers/training workstream is embedded as part of project team |  | Trust/CSCA |
| --- | --- | --- | --- |
| 19 | Training should include a section for operational reports and the trust should agree as part of |  | Trust PM/Training Lead |
|  | their organisational procedures which reports are most useful for which areas (outpatients, |  |  |
|  | inpatients etc) |  |  |
| 21 | Future state Business Processes need to be established early on in the project as part of a |  | Trust/CSCA |
|  | readiness assessment |  |  |
| 22 | Future state Business Processes need to be established early on in the project verified and |  | Trust Change Lead |
|  | owned by the Operational Managers to ensure compliance. |  |  |
| 24 | Ensure the scope of any service improvement/capacity and demand work is thoroughly |  | Service Improvement Lead(s) |
|  | documented and all involved parties have a clear understanding of what is to be undertaken |  |  |
|  | including the delivery dates. |  |  |
| 25 | That Trust’s acknowledge the scale and importance of this major change project and endorse |  | Trust PM |
|  | full support from the information department to provide vital data at an operational level |  |  |
| 26 | To ensure all parties involved are organised and hold the correct information to be able to |  | Trust/CSCA |
|  | deliver. |  |  |
| 27 | Engage with a good cross section of employees from managers to those on the shop floor |  | Trust |
| 28 | Contact all involved parties prior to business change events/workshops to ensure they hold |  | Trust/CSCA |
|  | the most correct and up to date information. |  |  |
| 29 | Ensure projects have a full time Communications lead. |  | Trust PM |
| 30 | Use clinical and project leads to validate the development and agreement of benefits – this |  | Trust Benefits Lead |
|  | will help support achievement of relevant benefits |  |  |
| 33 | The project has a full-time Benefits lead. |  | Trust PM |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 49 of 50 |

| 35 | Make sure stakeholders are involved with benefits work from the very start of the project. |  | Trust Benefits/Comms Lead |
| --- | --- | --- | --- |
|  | Regular updates from the benefits manager to improvement groups is important and an active |  |  |
|  | role for stakeholders with benefits work should be encouraged |  |  |
| 36 | Anonymous opinion questionnaires have allowed staff to express their thoughts directly to |  | Trust Benefits/Comms Lead |
|  | those who will listen which in turn reduces negative ‘gossip’ within departments and assures |  |  |
|  | staff that they are being listened to and that their opinion is valid and valued. |  |  |
| 38 | The parallel runs were good in that they were able to emphasise usability issues however |  | Testing Leads |
|  | these need to be taken onto the next level by better replication of real system use i.e. |  |  |
|  | interruptions to their work. For example users experiencing phone calls whilst booking |  |  |
|  | patients. |  |  |
| 40 | We had a core team of people whom you could rely on to do the key complex tasks and then |  | Trust PM |
|  | a larger number of inexperienced staff who came in during the latter stages of the project, did |  |  |
|  | add some value eventually but it took a disproportionate amount of time to get these people |  |  |
|  | productive e.g. To help with the creation of letter templates. Lesson is to try and get these |  |  |
|  | staff involved in the project as early as possible. |  |  |
| 41 | Tools needed earlier to transfer config between builds |  | CSCA |
| 60 | All of the issues encountered post go-live need to be fed back to the DM team to ensure that |  | DM Leads |
|  | they do not happen at the next cutover |  |  |
| 67 | Prior to deployment testing starting, consideration must be given to the business processes – |  | Trust/CSCA PM |
|  | when will reports be used by the trust in the functional areas and this should be built into the |  |  |
|  | test plan. The ‘true users’ should also conduct this testing. They will have greater |  |  |
|  | understanding of the different scenarios the reports will be used in. Example: If an outpatient |  |  |
|  | receptionist runs a clinic list in iPM for a consultant every Tuesday prior to clinic then it is |  |  |
|  | reasonable to expect that user to test the equivalent report in Lorenzo in the same way. |  |  |
| 68 | Get iPM setup in same environment as DEPLOR526. |  | Trust/CSCA PM |
| 70 | Make the test environments mimic the PROD environment more accurately. |  | CSCA Pogramme Management |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information

| CSC Alliance Proprietary Information |  |  |
| --- | --- | --- |
|  |  | NHS-LOR1.9-DAP-30000-001-UHMB Deployment Lessons Learned |
| Version 1.0 | 22/02/2011 | Page 50 of 50 |

| 71 | Recognition of common/understood aims/objectives at the outset |  | Trust/CSCA PM |
| --- | --- | --- | --- |
| 72 | Co-locate all of the testing activities |  | Trust/CSCA PM |
| 73 | Discipline of having a daily wash-up before /after each testing day |  | Trust/CSCA PM |
| 78 | CSCA need to prove their ability to fix issues in dress rehearsal so that Projects can have the |  | CSCA Programme Management |
|  | assurance that during actual cut over issues will be fixed in a timely manner |  |  |
| 80 | If adopting ‘Vocera’ technology ensure that all the communication black spots are identified. |  | Trust |
| 81 | Ensure operational report testing is included in the cut over plan as part of each functional |  | Trust/CSCA PM |
|  | area. |  |  |
| 84 | Ensure that issues are owned by Issues Resolution Team and Chennai team are there only to |  | SDM |
|  | assist. |  |  |
| 86 | Make a room available for developers/data migration staff to quickly turn issues around on |  | SDM |
|  | site. |  |  |
| 88 | The Environments should be tested prior to the Trust taking delivery. Joint Touch testing |  | Trust/CSCA PM |
|  | between CSCA and the Trust for each environment |  |  |
| 94 | In adverse weather conditions make better use of phone and video conferencing |  | Trust/CSCA PM |

This document is subject to the conditions in the Foreword © CSC Computer Sciences Limited. All Rights Reserved.

CSC Alliance Proprietary Information