## Gantt planification
Marketing Plan
[Name]
2018-09-14 11:02
|  | August 2018 | [29 empty] | October 2018 | [22 empty] | November 2018
 | time axis 2018-08-20 to 2018-12-28
Project activities | Status | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Meeting | done
EnterviewS28 | done
Market Study | doing ok | bar: 2018-08-30 to 2018-09-14
Design Objetives | done
Congress | done | bar: 2018-09-27
Analysis of Direct Competition | done
Design Context | todo | bar: 2018-10-03 to 2018-10-08
Analysis of indirect competition | done
Report Design | done | bar: 2018-10-05 to 2018-10-12
Presentation | done
Target | done | bar: 2018-10-10 to 2018-10-11
Proposal Draft | todo
Design Social Strategy | done | bar: 2018-10-19 to 2018-10-25
Delivery | done
Presentation for the team | todo | bar: 2018-10-31
Design review | done
Meeting2 | done
Finish agency proposal | todo
Presentation 2 | todo | bar: 2018-11-08 to 2018-11-14
Choose agency | todo
Congress NY | done | bar: 2018-11-15 to 2018-11-21
Presentation 3 | todo

## Project overview
Marketing Plan
[Name]
2018-09-14 11:02
Project team | Role
Teresa | Project owner
Richard | Team member
Diego | Team member
Activity | Involved |  | Goals |  | Subtasks | Assigned to | Date | Time
Meeting
22 Aug 2018 - 22 Aug 2018 (1 days) |  |  | No goals |  | No subtasks
EnterviewS28
23 Aug 2018 - 29 Aug 2018 (5 days) | Teresa |  | No goals |  | No subtasks
Market Study
30 Aug 2018 - 14 Sep 2018 (12 days) |  |  | No goals |  | No subtasks
Design Objetives (20% Completed)
17 Sep 2018 - 2 Oct 2018 (12 days) | Diego | ✓ | Review the plan | ✓ | Determine the goal | Richard
| Richard | - | Analysis of data | - | Determine the subject | Diego
|  |  |  | - | Meeting | Richard | 13 Jan 2018 | 01:00
|  |  |  | - | Draft | Teresa
Richard
Congress
27 Sep 2018 - 27 Sep 2018 (1 days) |  |  | No goals |  | No subtasks
Analysis of Direct Competition
28 Sep 2018 - 4 Oct 2018 (5 days) | Teresa |  | No goals |  | No subtasks
Design Context (100% Completed)
3 Oct 2018 - 8 Oct 2018 (4 days) | Teresa | - | Test 01 | ✓ | Analysis 1
|  | - | Overview | ✓ | Success Case
|  | ✓ | First Draft | ✓ | Subtask |  | 4 Jan 2018 | 01:30
|  |  |  | ✓ | Analysis 2 | Teresa |  | 02:00
|  |  |  | ✓ | Suppliers | Teresa | 16 Jan 2018
Analysis of indirect competition (0% Completed)
3 Oct 2018 - 4 Oct 2018 (2 days) |  |  | No goals | - | Drafts
Report Design (33% Completed)
5 Oct 2018 - 12 Oct 2018 (6 days) | Teresa |  | No goals | ✓ | Draft | Richard
| Richard |  |  | - | Subtask 02 | Teresa
|  |  |  | - | Subtask 03 |  | 30 Aug 2018 | 10:00
Presentation
9 Oct 2018 - 9 Oct 2018 (1 days) |  | ✓ | Results test |  | No subtasks
|  | - | Make a decision
Target
10 Oct 2018 - 11 Oct 2018 (2 days) |  |  | No goals |  | No subtasks
Proposal Draft
12 Oct 2018 - 18 Oct 2018 (5 days) | Teresa |  | No goals |  | No subtasks
Design Social Strategy
19 Oct 2018 - 25 Oct 2018 (5 days) | Richard |  | No goals |  | No subtasks
Delivery (100% Completed)
29 Oct 2018 - 30 Oct 2018 (2 days) |  |  | No goals | ✓ | Analysis
|  |  |  | ✓ | Draft
|  |  |  | ✓ | Plan
Presentation for the team (50% Completed)
31 Oct 2018 - 31 Oct 2018 (1 days) |  |  | No goals | ✓ | Ppt
|  |  |  | - | Communication
Design review
31 Oct 2018 - 2 Nov 2018 (3 days) |  |  | No goals |  | No subtasks
Meeting2
31 Oct 2018 - 1 Nov 2018 (2 days) |  |  | No goals |  | No subtasks
Finish agency proposal
1 Nov 2018 - 7 Nov 2018 (5 days) | Teresa |  | No goals |  | No subtasks
Richard
Presentation 2
8 Nov 2018 - 14 Nov 2018 (5 days) | Teresa |  | No goals |  | No subtasks
Choose agency
8 Nov 2018 - 16 Nov 2018 (7 days) |  |  | No goals |  | No subtasks
Congress NY
15 Nov 2018 - 21 Nov 2018 (5 days) |  |  | No goals |  | No subtasks
Presentation 3
10 Dec 2018 - 14 Dec 2018 (5 days) | Teresa |  | No goals |  | No subtasks