## ABC
ADOT ABC Decision Making Matrix
| Category | Decision-Making Item | Possible Points | Points Allocated | Scoring Guidance
| Railroad | Railroad/ Rail Transit under Bridge? | 4 |  | 0 No track under bridge
2 Minor track under bridge
4 Major track(s) under bridge
| Construction Impacts | ADT (Combined ADT on and under bridge) | 10
1 ADT under 10,000
3 ADT 10,000 to 25,000
5 ADT 25,000 to 50,000
6 ADT 50,000 to 75,000
7 ADT 75,000 to 100,000
10 ADT 100,000+
|  | Allowable Lane Closure (Roadway on Bridge) | 4 |  | 0 Long Term Lane Reduction Allowed During Construction
4 No Long Term Lane Reduction Allowed During Construction
|  | Allowable Lane Closure (Roadway under Bridge) | 4 |  | 0 Long Term Lane Reduction Allowed During Construction
4 No Long Term Lane Reduction Allowed During Construction
|  | Allowable Bridge Closure (Roadway on Bridge) | 6 |  | 0 Bridge Can closed - Viable Detour Available
6 Bridge Cannot be Closed
|  | Allowable Roadway Closure (Roadway under bridge) | 4 |  | 0 Roadway under can be closed
4 Roadway under cannot be closed
|  | Permanent Align Shift w/ single phase an option | 3 |  | 0 A permanent alignment shift is achievable to facilitate construction
3 A permanent alignment shift is achievable, but undesirable.
|  | Is phased construction with widening an option? | 8 |  | 0 Widening will fit updated standards or future roadway improvements
6 Widening achievable, but undesireable due to unused investment
8 No alternatives available for widening
|  | Impact to Local Access (Local business access, Local resident access etc.) | 6 |  | 0 Minor or no impact to access
3 Moderate impact to access
6 Major impact to access
| Project Duration | Impacts Critical Path of the Total Project? | 8 |  | 0 Minor or no impact to critical path of total project
4 Moderate impact to critical path of the total project
8 Major impact to critical path of the total project
|  | Restricted Construction Time (Environmental schedules, Economic Impact-e.g. local business access, special events, etc.) | 10 |  | 0 No construction time restrictions
3 Minor construction time restrictions
6 Moderate construction time restrictions
10 Major construction time restrictions
|  | Seasonal Limitations for conventional construction? | 4 |  | 0 No seasonal limitations for conventional construction
4 Seasonal limitations for conventional construction
| Environment | Does ABC mitigate a critical environmental impact or sensitive environmental issue? | 5 |  | 0 ABC does not mitigate an environmental issue
2 ABC mitigates a minor environmental issue
3 ABC mitigates several minor environmental issues
4 ABC mitigates a major environmental issue
5 ABC mitigates several major environmental issues
| Safety | Safety (Workers Concerns) | 8 |  | 0 Short duration impact
4 Normal duration impact
8 Extended duration impact
|  | Safety (Traveling Public Concerns) | 8 |  | 0 Short duration impact
4 Normal duration impact
8 Extended duration impact
| Economy of Scale | Bridge Economy of Scale (repetition of components in a bridge or bridges in a project) (Total spans=sum of all spans on all bridges on the project) | 4 |  | 0 1 total span
1 2 total spans
2 3 total spans
3 4 total spans
4 5+ total spans
| Risk Management | Does ABC allow management of a particular risk? | 4 |  | 0-4 Use judgement to determine if risks can be managed through ABC that arent covered in other topics
|  | Total Possible | 100
|  |  | Sum of Points: | 0