## Holidays (Input)
SpreadsheetML.com Critical Path Method Project
Holiday every |  | Y/N*
| Sunday | Y
| Monday | N
| Tuesday | N
| Wednesday | N
| Thursday | N
| Friday | N
| Saturday | Y
Holiday on |  | Date (maximum of 40 dates)*
|  | 2009-12-25 | Christmas Day
|  | 2010-01-01 | New Year's Day
|  | 2010-01-18 | Martin Luther King Day
|  | 2010-02-15 | Presidents Day
|  | 2010-05-31 | Memorial Day
|  | 2010-07-04 | Independence Day
|  | 2010-09-06 | Labor Day
|  | 2010-10-11 | Columbus Day
|  | 2010-11-11 | Veterans' Day
|  | 2010-11-25 | Thanksgiving Day
|  | 2010-12-25 | Christmas Day

## Month 1 (Input)
SpreadsheetML.com Critical Path Method Project
Project Start Date* |  | 2009-12-01 | [10 empty] | 2009-12-01
ID* | Items* | DY* | DID1* | DID2* | DID3* | DID4* | DID5* | Early Start Date | Early End Date | Late Start Date | Late End Date | SL | tu | we | th | fr | sa | su | mo | tu | we | th | fr | sa | su | mo | tu | we | th | fr | sa | su | mo | tu | we | th | fr | sa | su | mo | tu | we | th
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Activity A | 5 | [5 empty] | 2009-12-01 | 2009-12-07 | 2009-12-01 | 2009-12-07 | 0 | bar: 2009-12-01 tu 1 to 2009-12-01 mo 7; 2009-12-01 sa 12 to 2009-12-01 su 13; 2009-12-01 sa 19 to 2009-12-01 su 20; 2009-12-01 fr 25 to 2009-12-01 su 27
2 | Activity B | 3 | 1 |  |  |  |  | 2009-12-08 | 2009-12-10 | 2009-12-08 | 2009-12-10 | 0 | bar: 2009-12-01 sa 5 to 2009-12-01 su 6; 2009-12-01 tu 8 to 2009-12-01 th 10; 2009-12-01 sa 12 to 2009-12-01 su 13; 2009-12-01 sa 19 to 2009-12-01 su 20; 2009-12-01 fr 25 to 2009-12-01 su 27
3 | Activity C | 3 | 2 |  |  |  |  | 2009-12-11 | 2009-12-15 | 2009-12-11 | 2009-12-15 | 0 | bar: 2009-12-01 sa 5 to 2009-12-01 su 6; 2009-12-01 fr 11 to 2009-12-01 tu 15; 2009-12-01 sa 19 to 2009-12-01 su 20; 2009-12-01 fr 25 to 2009-12-01 su 27
4 | Activity D | 3 | 2 |  |  |  |  | 2009-12-11 | 2009-12-15 | 2009-12-23 | 2009-12-28 | 8 | bar: 2009-12-01 sa 5 to 2009-12-01 su 6; 2009-12-01 fr 11 to 2009-12-01 mo 28
5 | Activity E | 7 | 4 |  |  |  |  | 2009-12-16 | 2009-12-24 | 2009-12-29 | 2010-01-07 | 8 | bar: 2009-12-01 sa 5 to 2009-12-01 su 6; 2009-12-01 sa 12 to 2009-12-01 su 13; 2009-12-01 we 16 to 2009-12-01 th 31
6 | Activity F | 15 | 3 |  |  |  |  | 2009-12-16 | 2010-01-07 | 2009-12-16 | 2010-01-07 | 0 | bar: 2009-12-01 sa 5 to 2009-12-01 su 6; 2009-12-01 sa 12 to 2009-12-01 su 13; 2009-12-01 we 16 to 2009-12-01 th 31
7
8
| Project Completion Date | [7 empty] | 2010-01-07 |  |  | Legend
[13 empty] | DY - Duration in Days | [7 empty] | DIDx - Predecessors' ID | [8 empty] | SL - Slack
[14 empty] | - Critical Path | [6 empty] | - Non Critical Path | [6 empty] | x | - Holiday