- TAppendix one

Project plan/Critical path/Task list template for an event

<Event name>

<Event location>, <Event date and time>

| Task | Responsibilities: | Started Finished Date |  |
| --- | --- | --- | --- |

KEY MILESTONES

Expression of interest deadline

Marketing print deadline

Event date

TASKS COMPLETED

Establish date for event

Steering committee set-up and allocation of sub-committees (set

parameters and methodology of communication)

Venue contract reviewed and signed

Finalise title and theme

Seven to 10 months prior

Design and print

Arrange the design of logo

Finance

Prepare preliminary budget and have signed off

Confirm booking procedure (if tickets are involved)

Research funding grants to apply for

Ensure public liability insurance covers all event activities

Management

Draft critical path for review

Establish future committee meeting dates

Finalise committee responsibilities

Hold community and public consultation

Write event management plan

Marketing

Establish marketing and communications plan

Update regional tourism websites with event details

Program

Research ideas for entertainers/ performers/ activities

Sponsorship

Obtain information on demographics and the key benefits of

involvement from commercial perspective for inclusion in the

sponsorship flier

Sponsorship packages to be determined (levels, packages, inclusions

and entitlements)

Send sponsorship flier to print

Distribute sponsorship flier and make pitches

Review and enter sponsorship contact databases into database

Six months prior

Emergency services

Request first aid service service

Management

Confirm performers entitlements (travel, accommodation and meals)

Committee meeting

Program

Programme grid developed with performer time allocations

Discuss ideas for entertainers/performers/activities with committee

Research welcome to country

Five months prior

Community participation - expression of interest

Introduction of project to community through marketing, call for

expression of interest from individuals/groups interested in planning,

performing, volunteering

Food stalls

Research appropriate food stalls/vendors and update database

Send information to potential food stalls/vendors

Entertainment

Source performers as appropriate and update database

Confirm with committee with performers (and check against budget)

Update master spreadsheet for for entertainments

Send contracts to all performers/activites (outlining deadlines,

requesting photos, biographies and confirming entitlements)

Management

Committee meeting

Marketing

Put expression of interest detials on website

Sponsorship

Plan a schedule to follow up regularly with potential sponsors

Produce contract for sponsors, process invoices, and request logos as

sponsorship bookings come in

Venue

Evacuation plan

Four months prior

Design and print

Set program draft and brief

Finance

Appendix one

Project plan/Critical path/Task list template for an event

<Event name>

<Event location>, <Event date and time>

| Task | Responsibilities: | Started | Finished | Date |  |
| --- | --- | --- | --- | --- | --- |
| Review 2012 budget |  |  |  |  |  |
| Food vendors |  |  |  |  |  |
| Compile draft contracts and forms |  |  |  |  |  |
| Raise invoices for food vendors |  |  |  |  |  |
| Entertainment |  |  |  |  |  |
| Confirm with committee with performers (and check against budget) |  |  |  |  |  |
| Update master spreadsheet with entertainment contact details |  |  |  |  |  |
| Review contracts (checking that risk management form is complete |  |  |  |  |  |
| and that insurance is current) |  |  |  |  |  |
| Management |  |  |  |  |  |
| Committee meeting |  |  |  |  |  |
| Wet weather contingency plan |  |  |  |  |  |
| Marketing |  |  |  |  |  |
| Engage in social media for event |  |  |  |  |  |
| Three months prior |  |  |  |  |  |
| Food Vendors |  |  |  |  |  |
| Send contracts to all food vendors (outlining deadlines and confirming |  |  |  |  |  |
| entitlements) |  |  |  |  |  |
| Check current food registration with the council |  |  |  |  |  |
| Infrastucture |  |  |  |  |  |
| Book infrastructre as per performers requirements |  |  |  |  |  |
| Confirm standard requirements for stages |  |  |  |  |  |
| Request quote from audio visual supplier |  |  |  |  |  |
| Entertainment |  |  |  |  |  |
| Book accommodation for performers where required |  |  |  |  |  |
| Management |  |  |  |  |  |
| Committee meeting |  |  |  |  |  |
| Marketing |  |  |  |  |  |
| Flier design and production |  |  |  |  |  |
| Poster design and production |  |  |  |  |  |
| Operations |  |  |  |  |  |
| Draft security brief |  |  |  |  |  |
| Get security quotes |  |  |  |  |  |
| Book security |  |  |  |  |  |
| Arrange parking staff for venue |  |  |  |  |  |
| Organise any permits for event |  |  |  |  |  |
| Organise any licences for event |  |  |  |  |  |
| Traffic management plan |  |  |  |  |  |
| Risk management plan |  |  |  |  |  |
| Sponsorship |  |  |  |  |  |
| Confirm sponsors' entitlements (acknowledgements, logos, |  |  |  |  |  |
| advertisements) and request materials as appropriate (advising that |  |  |  |  |  |
| full payment of sponsor package is required prior to print deadline for |  |  |  |  |  |
| the sponsor's information to be included) |  |  |  |  |  |
| Ensure all entitlements are adhered to |  |  |  |  |  |
| Volunteers |  |  |  |  |  |
| Meet with KM and VB about volunteer requirements |  |  |  |  |  |
| Send expression of interest to previous year's volunteers |  |  |  |  |  |
| Waste management |  |  |  |  |  |
| Organise requirements |  |  |  |  |  |
| Send out contract |  |  |  |  |  |
| Two months prior |  |  |  |  |  |
| Audio visual |  |  |  |  |  |
| Confirm AV and send contract |  |  |  |  |  |
| Design and print |  |  |  |  |  |
| Ascertain what material will be required for final program |  |  |  |  |  |
| Draft evaluation form and send to committee for review |  |  |  |  |  |
| Draft final program |  |  |  |  |  |
| Final proof of the program approved |  |  |  |  |  |
| Send program to print |  |  |  |  |  |
| Finance |  |  |  |  |  |
| Obtain performers travel itineraries and organise reimbursements as |  |  |  |  |  |
| applicable |  |  |  |  |  |
| Food stalls |  |  |  |  |  |
| Review contract (checking all elements of risk and that insurance is |  |  |  |  |  |
| current) |  |  |  |  |  |
| Ensure all appropriate paper work has been submitted including |  |  |  |  |  |
| registration, insurance and food safety program |  |  |  |  |  |
| Confirm power sources and update master spreadsheet |  |  |  |  |  |
| Identify water requirements and update master spreadsheet |  |  |  |  |  |
| Collate information with all final event details for information pack |  |  |  |  |  |

Appendix one

Project plan/Critical path/Task list template for an event

<Event name>

<Event location>, <Event date and time>

| Task | Responsibilities: | Started | Finished | Date |  |
| --- | --- | --- | --- | --- | --- |
| Infrastructure |  |  |  |  |  |
| Plan information area requirements (including furniture and signage) |  |  |  |  |  |
| and place orders as required |  |  |  |  |  |
| Book toilet cleaning |  |  |  |  |  |
| Organise general venue cleaning prior and post-event |  |  |  |  |  |
| Check if generator back up is required |  |  |  |  |  |
| Ensure SunSmart considerations are implemented |  |  |  |  |  |
| Organise keys for venue |  |  |  |  |  |
| Confirm event staff work hours for event |  |  |  |  |  |
| Organise water for green rooms, staff, event patrons and volunteers |  |  |  |  |  |
| Management |  |  |  |  |  |
| Draft runsheet |  |  |  |  |  |
| Undertake committee site visit |  |  |  |  |  |
| Confirm committee responsibilities during the event |  |  |  |  |  |
| Plan staff and confirm rosters for information desk, MCs, directional |  |  |  |  |  |
| staff and general duties |  |  |  |  |  |
| Committee meeting |  |  |  |  |  |
| Entertainment |  |  |  |  |  |
| Confirm technical requirements - add to master spreadsheet |  |  |  |  |  |
| Book Mayor/councillors to event |  |  |  |  |  |
| Organise Mayor's speech requirements |  |  |  |  |  |
| Chase invoices |  |  |  |  |  |
| Marketing |  |  |  |  |  |
| Banner (for Elgin Blvd) design and printed |  |  |  |  |  |
| Send event details to Out & About |  |  |  |  |  |
| Newspaper adverts designed |  |  |  |  |  |
| Draft text for final program and send to committee for review |  |  |  |  |  |
| Prepare signage brief (sponsor corflutes) |  |  |  |  |  |
| Send program text to graphic designer |  |  |  |  |  |
| Put posters in noticeboards |  |  |  |  |  |
| Book photographer |  |  |  |  |  |
| Security |  |  |  |  |  |
| Determine whether additional venue security is required and organise |  |  |  |  |  |
| booking if needed |  |  |  |  |  |
| Sponsorship |  |  |  |  |  |
| Confirm sponsor involvement in official opening |  |  |  |  |  |
| Volunteers |  |  |  |  |  |
| Update volunteer application form |  |  |  |  |  |
| Source external volunteers |  |  |  |  |  |
| Volunteers registered |  |  |  |  |  |
| Volunteers position descrption and roster prepared |  |  |  |  |  |
| Month prior |  |  |  |  |  |
| Catering |  |  |  |  |  |
| Staff/volunteer meal vouchers |  |  |  |  |  |
| Emergency services |  |  |  |  |  |
| Place first aid on site map |  |  |  |  |  |
| Finance |  |  |  |  |  |
| Update budget |  |  |  |  |  |
| Finalise cash float for onsite |  |  |  |  |  |
| Food stalls |  |  |  |  |  |
| Information packs send to food vendors |  |  |  |  |  |
| Send gas sheet information to relevant stallholders |  |  |  |  |  |
| Map out site plan |  |  |  |  |  |
| Follow-up phone call to ALL food vendor to ensure everything is fine |  |  |  |  |  |
| Infrastructure |  |  |  |  |  |
| Confirm all infrastructure |  |  |  |  |  |
| Send site plan to all suppliers |  |  |  |  |  |
| Pack-up list |  |  |  |  |  |
| Collate all signage |  |  |  |  |  |
| Review equipment list and do shopping list (if necessary) |  |  |  |  |  |
| Mark up site map for OH and S inspection |  |  |  |  |  |
| Brief parking staff |  |  |  |  |  |
| Inform emergency services of event |  |  |  |  |  |
| Map power outlets and wattage |  |  |  |  |  |
| Green room |  |  |  |  |  |
| Order food/ beverages for performers |  |  |  |  |  |
| Main stage |  |  |  |  |  |
| Confirm technical requirements |  |  |  |  |  |
| Review and finalise main stage confirmation to all performers with |  |  |  |  |  |
| onsite briefing notes (remember to confirm stage size within breifing |  |  |  |  |  |
| Distribute performer biographies and briefing notes to stage MCs |  |  |  |  |  |

Appendix one

Project plan/Critical path/Task list template for an event

<Event name>

<Event location>, <Event date and time>

| Task | Responsibilities: | Started | Finished | Date |  |
| --- | --- | --- | --- | --- | --- |
| Set-up housekeeping notes for onsite folder for MCs |  |  |  |  |  |
| Organise MC breifing |  |  |  |  |  |
| Management |  |  |  |  |  |
| Committee meeting |  |  |  |  |  |
| Confirm onsite staff roster |  |  |  |  |  |
| Print running sheets, program and site plan and distribute to all |  |  |  |  |  |
| involved |  |  |  |  |  |
| Prepare onsite contact list (including performer list) |  |  |  |  |  |
| Prepare event handbooks for staff/volunteers |  |  |  |  |  |
| Prepare onsite folders (including master folders) |  |  |  |  |  |
| Prepare stage manager folders |  |  |  |  |  |
| Marketing |  |  |  |  |  |
| Corflute production |  |  |  |  |  |
| Print program (with map) |  |  |  |  |  |
| Brief to photographer and film crew |  |  |  |  |  |
| Sponsorship |  |  |  |  |  |
| Set-up meetings with sponsors |  |  |  |  |  |
| Review and finalise sponsor onsite briefing notes |  |  |  |  |  |
| Volunteers |  |  |  |  |  |
| Volunteer training |  |  |  |  |  |
| Follow-up external volunteers |  |  |  |  |  |
| Volunteer position descriptions |  |  |  |  |  |
| Runsheet of volunteers and job allocation |  |  |  |  |  |
| Volunteer information packs |  |  |  |  |  |
| Collate all information for information tent |  |  |  |  |  |
| Week of event |  |  |  |  |  |
| Venue |  |  |  |  |  |
| Ensure keys from venue are obtained |  |  |  |  |  |
| Volunteers |  |  |  |  |  |
| Volunteer info evening |  |  |  |  |  |
| Management |  |  |  |  |  |
| Team breifing |  |  |  |  |  |
| Bump-in |  |  |  |  |  |
| Onsite (refer to individual run sheet for day) |  |  |  |  |  |
| Dismantle |  |  |  |  |  |
| Post event |  |  |  |  |  |
| Management |  |  |  |  |  |
| Send thank you letter to volunteers |  |  |  |  |  |
| Send thank you letter to performers, activities and market stallholders |  |  |  |  |  |
| Committee debrief |  |  |  |  |  |
| Sponsors meeting and debreif (and return any signage) |  |  |  |  |  |
| Analyse evaluation results |  |  |  |  |  |
| Review media coverage |  |  |  |  |  |
| Update budget |  |  |  |  |  |
| Finalise accounts |  |  |  |  |  |
| Prepare final report |  |  |  |  |  |

Appendix two

Event budget template

|  |  |  | Proposed (exc |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Component | Particulars | GST) | Working | Actual | Notes |
|  | Income |  |  |  |  |  |
|  |  | Ticket sales |  |  |  |  |
|  |  | Sponsorship |  |  |  |  |
|  |  | Grants |  |  |  |  |
|  |  | Raffles and fundraising |  |  |  |  |
|  |  | Stall or other fees |  |  |  |  |
|  | Total income |  | $ | $ | $ |  |
|  | Expenses |  |  |  |  |  |
|  | Venue hire | Hire fee |  |  |  |  |
|  | Infrastructure | Equipment hire |  |  |  |  |
|  |  | Audio visual (lighting and sound) |  |  |  |  |
|  |  | Traffic management |  |  |  |  |
|  |  | First aid |  |  |  |  |
|  |  | Toilets |  |  |  |  |
|  |  | Power |  |  |  |  |
|  |  | Security |  |  |  |  |
|  |  | Waste management |  |  |  |  |
|  | Program | Entertainment |  |  |  |  |
|  |  | Travel and accommodation |  |  |  |  |
|  | Catering | Food for staff/ volunteers |  |  |  |  |
|  |  | Food for performers |  |  |  |  |
|  | Marketing | Design |  |  |  |  |
|  |  | Print advertising |  |  |  |  |
|  |  | TV |  |  |  |  |
|  |  | Radio |  |  |  |  |
|  |  | Program |  |  |  |  |
|  |  | Flyer |  |  |  |  |
|  |  | Distribution/ postage |  |  |  |  |
|  |  | Signage |  |  |  |  |
|  |  | Photography |  |  |  |  |
|  |  | Media launch |  |  |  |  |
|  | Administration | Permit fees |  |  |  |  |
|  |  | Salaries and fees |  |  |  |  |
|  |  | Stationary |  |  |  |  |
|  |  | Decorations |  |  |  |  |
|  |  | Prizes |  |  |  |  |
|  |  | Insurance |  |  |  |  |
|  |  | Contingency |  |  |  |  |
|  | Total expenses |  | $ | $ | $ |  |
|  | Total |  | $ | $ | $ |  |

Appendix three

Event marketing plan template

ACTIVITY

Event name

Advertising

Television:

Print:

Radio:

Signage:

Social media:

Website

Facebook

Twitter

Printed materials distribution

Flyers - size, quantity

Brochures - size, quantity

Posters - size, quantity

Other