Event Planning Guide

Purpose

This document is to be used as a general guide for any FBC ministry or outside group that is hosting a large event at FBC. While it may be too detailed for smaller events, it should be reviewed for guidelines for all sized events.

Prayer

Please don’t attempt anything for the Lord without first seeking His direction. Before you contact the first speaker, you need to pray for God’s guidance. Jesus said it best: “Ask and it will be given to you; seek, and you will find; knock and the door will be opened to you.” (Matthew 7:7)

Primary Contact Information

Roy Madden	ext. 202 roy.madden@firstbaptistnet.com	Director of Administrative Services

Contract / Service Agreements

Per FBC Bylaws and Job Descriptions, only the Senior Pastor, Director of Administrative Services and/or the Trustees are authorized to sign contracts or service agreements on behalf of FBC.

For ministry events (guest speakers, conferences, etc), the employee and/or lay-leader overseeing a specific ministry event should co-sign the contract and/or service agreement prior to finalizing any arrangements.

Prior to signing most contracts or service agreements, the document is forwarded to our Church Attorney for review.

Planning

Check with Roy Madden for event availability on the church calendar.

Seating capacity on the floor of the Sanctuary is 900. One row of chairs in the balcony will seat 40-50. The choir loft seats 80-100.

One to Two Years Before the Event

Decide event purpose.

Set the tentative date for the event and check the church calendar (you may want to inquire as to a back-up date as well). Contact Roy Madden to confirm the date. If the date is available it will be tentatively reserved pending submission of the attached Building / Facility Use Application form. Remember to schedule ALL areas that will be used – not just the main meeting location (include kitchen, break-out rooms, registration area, childcare rooms, etc.) If any additional setup days are required in certain rooms prior to the event, these also need to be reserved on the church calendar. Be sure you have the event set for a time when there are no conflicts with church events. You may also want to check school and community calendars and sporting events schedules.

Your group will want to appoint an Event Coordinator/Chairperson – this person will be the point person for everything relating to the event. They will coordinate the event and are in charge of the program, speaker, music, and all other teams; sets up meetings with teams as needed; monitors spending in order to maintain budget guidelines.

Determine your budget. This includes both expenses and income. A sample budget is attached.

Contact the first keynote speaker. If the date works for this person, contact other speakers. Do not contact all the speakers at the same time (to avoid conflict). Adjust the date if speakers are not available to be with you on your first choice of dates. Ask them if they require an honorarium.

  - 3 -

Create an event timeline. Add any deadlines and other requirements to timeline – this will help keep you on track.

Nine to Twelve Months Before the Event

Decide on a theme, based on Scripture. From the theme, develop message titles, seminar topics (optional), decoration themes, and publicity plans.

Begin working with your teams. The following team structures are suggestions. You may use only one or two teams – we’ve tried to list all possibilities.

Decorations team – responsible for putting up and removing all decorations (or selling them after the event).

This includes decorating for the meals, all displays set up during the event, decorating the bathrooms (if desired), and any other extra decorations in any part of the facility. The church owns the following table linens:

- Long, round tablecloths (to the floor)

- Regular length round tablecloths

- Rectangular skirted tablecloths

- Long, rectangular tablecloths (to the floor)

- Regular length rectangular tablecloths

- Cloth napkins

Tablecloths can be used for $10 each to cover cleaning costs; skirted tablecloths are $12 each and cloth napkins are $1 each. We also have several odd-shaped tablecloths that have been donated. If you would like to possibly use these for reception areas, etc. the same $10 fee applies. Any additional cloths desired will need to be rented.

Prayer team – responsible for contacting people who would be willing to pray daily for the needs of the speakers, the team leaders, those attending, and the facilities before and during the event. Consider having weekly prayer meetings and a focused time for leadership and/or church congregation to pray prior to the event. Remember to schedule any meetings on the church calendar. There is nothing too trivial to pray over!

Food team – responsible for planning an attractive menu. You may need one or two meals, depending on the length of the event. Meals are a critical element. This team is also responsible for refreshment centers set up with light snacks such as coffee, sodas, and mints. Supply the Facility Mgr with a setup for the Fellowship Hall several days prior to the event.

Lodging team – responsible for making lodging arrangements. This may be for out-of-town leaders or securing reduced rates for event attendees.

Secretary/Registration team – responsible for participant registrations; childcare registration (if offered); correspondence to registrants; all monies received; and keeping up with requests for lodging. Supply the Facility Mgr with a setup for the Registration area several days prior to the event.

Childcare team – as registrants request childcare (optional), this team will make the necessary preparations. Contact the FBC Director of Preschool & Children’s Ministries to secure childcare prior to any advertising of such. Childcare registration should be closed two weeks before the event to allow for adequate preparation.

Publicity team – responsible for all publicity except registration brochures. Publicity can be through local newspapers, the Western Recorder, Christian radio stations, or cable television.

Booklet team – responsible for preparation of the program booklet (optional). This booklet contains the schedule, information about the speakers, speaker’s outlines, Scripture references, and places to take notes.

  - 4 -

Packet team – responsible for the (optional) free packet given to each attendee (pen, program booklet, tissues, breath mints, key chains, etc.). Prepare and mail letters to potential sponsors requesting consideration in their budgets. Check with local businesses for giveaways and door prizes. Include a donor list in the packet. This team will need to order packets at least three to four months before the event.

Transportation team – plans transportation as needed for speakers and participants.

Counseling team – prepares or obtains decision cards, tracts, church information, and other follow-up materials. Trains people to counsel.

Worship Media/Audiovisual team – works to secure equipment and volunteers as needed. Contact Tim Wilson, Minister of Music (tim.wilson@firstbaptistnet.com or 623-4028, ext. 217) for information on reserving equipment and securing volunteer assistance for sound/cameras/projection support for event. When completing the Audio/Visual and Sound and Lights Form you will want to annotate completely what needs you may have so that volunteers can be secured.

Greeter team – responsible for greeting and directing to registration, childcare, and event rooms. May want to work with FBC Greeter Ministry Team.

Security team – responsible for working with FBC Security Team to decide if security is needed for the event.

Follow-up team – calls or sends letter to those who attended from outside the church. Contacts those who made decisions at the event.

Four to Six Months Before the Event

After you have decided on seminar (small group) topics, pray about who God wants you to ask to lead. After you have seminar leaders in mind, give the list to fellow ministry members to pray about. Once you have prayed and are assured that the leaders are right for your event, contact each one.

Decide about offering scholarships and the process for advertising and obtaining scholarships.

Contact and secure musicians: soloists, instrumentalists, music leaders. Give them direction about the philosophy of the event and what is expected of them.

Decide on registration cost. Establish fee structures and policies, being certain to include clear cancellation policies.

Design registration brochure and logo. Locally we use CopyRite Printing (624-1251) for our printing needs. You will want to obtain a quote on the brochure as well as any other needs you might have for the event. What might you need?

  - Invitation to event

  - Response card

  - Response envelope

  - Programs

  - Agenda

  - Seating cards

  - Napkins

Compile mailing list (see Publicity on pg 8).

Lodging Team: Prepare a list of hotels for those who may be traveling from out of town. Secure reduced rates (if possible). Include these in your brochures along with contact information.

Work with church staff person to advertise all upcoming conference information.

    - 5 -

For an FBC ministry event, remember to schedule any planning meetings needed. All of these need to be placed on the church calendar.

Secure a photographer for the event, if desired.

Two to Three Months Before the Event

Send out registration brochures.

Write your keynote speakers periodically and let them know how plans are progressing. Give them all the information you can. If preparing a program booklet, give them a deadline to have their outlines submitted. Ask what you can do for them as they prepare to come. Give them encouragement and direction about the philosophy of the event and what is expected of them.

Work individually with each chairperson about their responsibilities. Even though group meetings may seem better, you can save time by working individually. This also facilitates the decision-making process.

Finalize the schedule and confirm that all details are being handled.

Review/finalize budget, task sheets and tentative timeline.

Work with Pat Allen, Kitchen Coordinator, on use of the kitchen and to receive approval/certification on kitchen policies and equipment. Pat can be reached at 624-2482.

Secretary/Registration Team: Purchase nametags and nametag holders if desired. Decide if you want to pre-print these or have them completed upon arrival. A registration plan needs to be put in place if you are wanting the church administrative staff to handle/assist with registration. If this is the case, you must advise/discuss with Director of Administrative Services so he can properly direct the staff. What has worked well in the past is one person from the Team is selected to handle all registrations and monies. As these are received at the church via mail or walk-ins both registration forms and monies are placed in a central location (an envelope marked for the event kept in a central location works well). The Team person comes in several times each week and processes the registrations and payments (makes copies, etc). The monies are then placed in a Finance Office envelope and turned into the Finance Manager labeled for the conference. The Finance Office only needs monies, not registration forms.

One Month Before the Event

Make plans for a pre-event reception/prayer time. This reception or prayer time is normally held the afternoon or evening before the event and includes speakers, chairpersons, workers, and musicians. The reception can be in someone’s home or at the church. This is a special time of dedication and prayer for the event. Send an invitation to all seminar leaders/speakers, chairpersons, workers, and musicians asking them to come to the reception.

If preparing a program booklet, if you don’t have all the speaker’s/leader’s outlines, call and request them. The booklet needs to be printed and reproduced so they can be assembled at least two weeks before the event.

Plan three to four workdays during the last two weeks before the conference or retreat. Put these dates on the church calendar. Clear the dates with your Booklet, Packet, and Decoration teams, because these are the ones who will need the most help.

Publicity Team: Place newspaper ads, follow-up with news media, on-air announcements.

Hold walk-through of event with responsible teams and church support staff (Technology & Communications Mgr/Director of Administrative Services and Facility Mgr). Get enlarged site plan/room diagram, assign seats/tables, if needed.

Review needs for signs at registration, directional, etc.

Give estimate of guests expected to caterer/food service.

  - 6 -

Remember to work closely with the FBC Finance Mgr. in processing all invoices related to the event.

Confirm setup/tear down times with FBC Facility Mgr. (Includes individual teams that may have particular setup needs – Registration, Food, etc.) Discuss who will be responsible for opening/closing the building on the day of the event.

Two Weeks Before the Event

Finalize plans with your chairpersons, making sure details are covered and they have plenty of volunteer help.

Lodging Team: Confirm reservations for speakers and leaders.

Contact individuals in your group to act as hostesses and to introduce the speakers.

Complete the program booklet and assemble.

Packet Team: Stuff the packets and store them until the event.

Write guest speakers/leaders, telling them how many are registered for the event and their individual seminars, and send them a copy of the program booklet.

Complete program plans.

Consider not scheduling any extra programs for your group the week prior to the event.

Give the FBC Finance Mgr. an itemized list of honorariums, including speakers, singers, musicians, and worship media personnel as well as any other invoices that need to be processed. Request for Payment (RFP) forms can be obtained from the Church Office. An RFP will need to be completed for each person/vendor.

One Week Before the Event

Meet with all teams for last-minute details.

Finish phone follow-ups.

Confirm number attending.

Give caterer revised numbers. Finalize catering guarantee, refreshments.

Finish seating/table arrangements.

Secure 2-3 volunteers to assist with emergencies. Secure registration staff. Secure someone to man the phone an hour prior to the event through one hour after the event starts. Hold training session with volunteers; finalize assignments.

Distribute seating chart, assignments to hosts/hostesses.

Establish amount of petty cash needed for tips/emergencies. Obtain cash the day before the event.

Obtain checks from FBC Finance Mgr. to distribute at event.

If using event evaluation forms, plan to place collection receptacles around the church in convenient locations.

The Day of the Event

Reconfirm refreshments/meal schedule for volunteers.

  - 7 -

Go over all the final details with caterer and setup staff.

Check with volunteers to make sure all tasks are covered.

Set up registration area.

Relax and enjoy the day! It’s in God’s hands and He gets all of the credit and glory!

After the Event

Send thank-you notes to all who helped with the event including door prize and gift bag donors and church Support Staff (administrative support staff, facility staff, etc.).

Pack and inventory all material – many of your materials may be reusable. It’s a big investment, so take care of it.

Do financial reconciliation. With a big event, you’ll have many invoices and you need to make sure you have been billed correctly and pay in a timely fashion. Watch expense reports, since a lot of cost can be hidden in those reports.

Perform post-budget performance review. Were you on budget? Could you have saved money?

Collect and organize data for final meeting reports. Obtain evaluations from staff, volunteers, and consultants. It is very important to evaluate what went right and what went not so right so the next time is easier.

Publicity

While prayer and planning are two of the most essential ingredients to a successful event, you cannot overlook publicity. You must get the word out!

One of the most effective ways to publicize is through personal invitation. After you have developed your theme and enlisted your speakers, you will want to produce an appealing brochure you can send to as many individuals as possible.

Your target audience might include: Individuals in FBC

Individuals on mailing lists from outside FBC’s family (from previous events or from another churches’ mailing list)

Individuals in churches in your state (obtain this information from the KY Baptist Convention or Tates Creek Baptist Association offices)

Another way to publicize the event is to send correspondence to all the churches in your area asking them to publicize the event. You will need to follow up the correspondence with a phone call, making sure someone has agreed to help you; encourage their support.

As previously mentioned, you can advertise in your local newspapers, the Western Recorder, on Christian radio, and local cable channels.

Develop an active file for free advertising: Facebook/Twitter, community calendars, listener-supported radio stations (K-LOVE), and public service announcements.

Don’t wait too late to advertise! A month before the conference is not sufficient time! Don’t advertise too early, either! Four months before the conference gives them plenty of time to put the brochure aside and forget (unless you are going to follow up later). Six weeks prior to the event seems to be a good time frame.

  - 8 -

Technical Information

There is no public wi-fi at FBC. If internet access is needed for an event, contact Roy Madden. Laptops, with wireless availability, can be provided.

If presentations are being created for an event to be used in the Sanctuary, the smallest text size that can be used is 36. PowerPoint 2010 and MediaShout are used at FBC. Someone to run the presentation will need to be secured; contact Tim Wilson.

Event Signage

Below are size and placement guidelines for both temporary exterior and interior signage for an event:

Exterior to be placed near the main entrance

Banners should be 4x6 feet. Sign Source or Signs & More are contacts for banners. Any banners must be pre-approved by Roy Madden. A permitting process with the City of Richmond has to be done and dates for the banner to be put out and taken down need to be added to the church calendar for facility staff use – Roy Madden will handle these details.

Interior

Paper/cardstock signs for the interior are permissible but should not cover up any existing signage. Interior signs can be letter, legal or poster (11x17") size. Interior signs placed on the walls must be placed using only masking tape or painters tape. Scotch tape should be used for signs placed on the exterior glass doors. All signage placed inside the building must be removed shortly after the end of the event by the Event Coordinator or designee. Copiers (black & white and color) and paper/cardstock are available for use from the church office; reimbursement costs are required. If a particular color of paper/cardstock is required, contact Debbie Kelley one month prior to event so that it can be ordered.

- 9 -

Priority

Maintaining an appropriate focus on your event is important. It is easy to get sidetracked. Here are a few suggestions that will help you keep your priorities in order.

Focus on God’s Goodness

Count your blessings and consider the people who are going to benefit from the event! Talk about it often; pray about it always; keep the goal in front of your leaders at all times.

Support Committees

Support the committee chairpeople and let them do their jobs. If it’s not exactly the way you would do it, that’s OK.

Keep Your Head!

When you have 20-30 people working on a project, disagreements and cross purposes occur. Everyone looks to see how upset the leader is going to get. Remember that you set the tone.

Set Goals

Set a number of attendees, stick to that goal, and close registration when you reach it. This is an unpopular thing to do, and no one likes that responsibility, but you do a disservice to the ones who have registered early when you crowd in more than you had planned for.

Be a Servant

As a church sponsoring an event, your role is that of a servant (or servants). During the event, take the posture of a servant!

Purpose

Why is it so important to mention purpose? Isn’t the purpose to have an event? Isn’t the purpose to get through the event with no major catastrophes? Isn’t the purpose to stay within the budget?

There can be a lot of purposes, all good, but the most important purpose for having an event is to bring honor and glory to the Lord!

What brings honor and glory to the Lord?

Changed lives and restored homes A time of spiritual restoration

Seed-planting resulting in salvation God receiving all the credit

How can you go wrong planning and conducting an event with that as your purpose?

- 10 -

FBC Event Forms

- 11 -

FBC Event Overview

This Event's Audience:

This Event's Purpose:

This Event's Objectives:

1

2

3

4

How does this event fit our ministry vision/goal?

What elements are vital to make this event effective?

With whom can we partner to make this event more effective?

What parallel events are happening at or around this event?

- 12 -

Building / Facility Use Application

425 Eastern ByPass

Richmond, KY 40475

859.623.4028 (Office)

859.623.5978 (Fax)

wes.napier@firstbaptistnet.com

Ministry or Event: __________________________________________________________________________

________________________________________ Event Coordinator

Date requested: ______________________________

_______________________________________ E-mail

___________________________________________ Home/Work/Cell Phone

Room(s) / Area(s) Requested: ________________________________________________________________ (room setup diagram on next page)

| Specific Date(s) | Day(s) of Week | Entry | Departure |
| --- | --- | --- | --- |
|  |  | Time | Time |
| ____________ | ___________ | ________ | ________ |
| ____________ | ___________ | ________ | ________ |

List activities/purpose of event: _______________________________________________________________

________________________________________________________________________________________

Will voluntary offerings/contributions/fees be collected or solicited?

____ Yes

____ No

Number of person to be present: _____ ____ Adult group (19 years or older)

Number of chaperones 21 or older to be present: ____ ____ Youth group (18 years of age or under)

Is this an FBC-sponsored or FBC-budgeted event? ____ Yes

____ No (See Fee Schedule)

Will set-up / clean-up be done within your group? ____ Yes

____ No (See Fee Schedule)

--------------------------------------------------- CHURCH OFFICE USE ONLY -------------------------------------------------------

ACTION: ____ Approved (Application accepted.)

____ Denied

Fees Due: $ ___________

COMMENT: _______________________________________________________________________

| Authorized Signature: ________________________________________ | Date: ____________ |
| --- | --- |
| Entered on Church Calendar: __________ | Copy To: _________________________________________ |
|  | - 13 - |  |

Setup Instructions for Building / Facility Use Application

Requested by: __________________________________	Room Requested: __________________________

DIAGRAM OF ROOM SET UP

(Please draw diagram showing location and number of chairs, tables, other special

equipment needs, etc.; include location of doors, windows, etc. so that facility staff will have an

orientation of the room.  A diagram will be needed for each room.)

Special Equipment and/or Needs

| ____ White Marker Board | ____ Extension Cord | ____ Easel |
| --- | --- | --- |
| ____ Projector | ____ Laptop | ____ Sound System |
| ____ Round Tables | ____ 6 ft Tables | ____ 8 ft Tables |
| ____ Chairs | ____ Linens | ____ Speaker Stand/Lecturn |
| ____ TV w/ VCR/DVD | ____ Other: ___________ | ____ Other: ___________ |
|  | - 14 - |  |

FBC Event Fee Schedule

|  | FBC Ministry | Outside Event |
| --- | --- | --- |
| Use of Church | No Charge |  | $ | 250.00 user fee |
| Sound & Light Technician | $ | 100.00 |  | $ | 100.00 |  |
| Fee includes up to 4 hours; $25 each hour over 4 hours |  |  |  |
| Media Tech (PowerPoint) |  |  |  |  |  |  |
| Design Work | $ | 25.00 |  | $ | 50.00 |  |
| Running system during event | $ | 50.00 |  | $ | 100.00 |  |
| Fee includes up to 2 hours; $25 each hour over 2 hours |  |  |  |
| Church Videography | $ | 600.00 |  | $ | 800.00 |  |
| Custodial Fees | $ | 16/hour | $ | 16/hour |
| Billed in 1-hour increments |  |  |  |  |  |  |
| Pre-Event Resetting of Platform | $ | 16/hour | $ | 16/hour |
| Post-Event Resetting of Platform | $ | 16/hour | $ | 16/hour |
| Pianist | $ | 25/hour (min. 8 hrs) | $ | 25/hour (min. 8 hrs) |

Tablecloth & Napkin Fees can be found on page 4

Notice

Six months notice is required to secure a Media Tech and/or Video Team. If staffing cannot be secured within four months of the event, the Event Coordinator will be notified. A one month notice is required to secure a Sound & Light Tech. None of these services can be guaranteed until staffing is secured.

Cancellation Policy

If cancellation is received 45 days or more before the event, all fees paid up to that time will be refunded.

If cancellation is received less than 45 days before the event, no fees will be refunded.

- 15 -

FBC Ministry Event Checklist

Event: __________________________________________________________________________________

Event Date(s): ______________________________	Start Time: _____________	End Time: __________

Approximate Attendance: __________

Date Completed &

Person Responsible

INITIAL CONTACT WITH THE GROUP

Confirm the dates for the events and all subsequent meetings

Agree upon physical arrangements (rooms and setup)

Clarify equipment needs

Clarify food needs

Agree upon cost, if any

___________________________________________________________

STAFFING

Prepare and delegate staff assignments

Select and invite guest speakers

Select musicians, soloists, etc.

Honorariums, etc.

___________________________________________________________

PUBLICITY/PRINTING

Decide upon title/theme

Prepare a letter or brochure and necessary signs

Arrange mailings

Misc. pieces: postcards, note cards, event evaluations, visitor cards, childcare cards, stationary, decision cards, program booklet

Place event on church website & newsletter, PowerPoint

Printing needs: How many of each? Type of paper? Ink color(s)?

___________________________________________________________

FACILITY PREPARATION

Sanctuary

Fellowship Hall

Kitchen

Nursery

Additional Rooms (#___________)

___________________________________________________________

PROGRAM PREPARATION

Emcee appointed

Special music selected

Special announcements determined

Persons involved informed of their responsibility

Time limitation discussed with all participants

___________________________________________________________

___________________________________________________________

Additional items on next page.

- 16 -

Date Completed &

Person Responsible

EQUIPMENT PREPARATION

Audio-visual needs (i.e. sound system, piano, PowerPoint, portable Projector and/or sound system, etc.)

Podium (# ________)

Chairs	(# ________)

Tables	(#________)

Display and registration area with table and chairs

Name tags

Registration forms, if needed

Marking pens

Money box and change

___________________________________________________________

___________________________________________________________

Rented equipment will be provided by the following:

Company / Person __________________________	Phone ________

FOOD PREPARATION

Table and chairs for meal (room setup form completed)

Coffee, hot water, tea, cream & sugar, etc.

Menu

Extension cords

Any necessary cabinet keys

Trash containers

Table decorations

Silver, dishes (real or paper?), napkins, etc.

Adequate volunteers for serving

Special area for dirty dishes

Clean-up (custodial needs)

___________________________________________________________

___________________________________________________________

OTHER SPECIAL NEEDS

Deaf interpretation

If childcare in use, access to parent pager system

Decorations

___________________________________________________________

FOLLOW UP

Special thank you notes written

Cost analysis completed

Special commitments and promises followed up ___________________________________________________________ ___________________________________________________________

EVALUATION

SUGGESTIONS FOR NEXT EVENT

- 17 -

Public Relations Intake Form

Submit to church office if publicity within the church is desired:

From: __________________________________

Event Chairperson

________________________________________ Ministry/Event

__________________________________ Phone

________________________________________ Email address

__________________________________

Event

I am requesting publicity in the following manner:

| [ | ] | Pulpit announcement |
| --- | --- | --- |
| [ | ] | Website |
| [ | ] | Facebook/Twitter |
| [ | ] | Worship bulletin |
| [ | ] | E-mail blast (Top 5) |
| [ | ] | Digital signage/IMAG |
| [ | ] | Poster/Banner/Flyer/Bulletin Board |
| [ | ] | Cable TV announcements |
| [ | ] | Richmond Register/TV Magazine ad |

Other needed information: ______________________________________________________________

___________________________________________________________________________________

___________________________________________________________________________________

___________________________________________________________________________________

___________________________________________________________________________________

Event materials:	[	]	are attached	[	]	are not attached

- 18 -

Sample Event Budget

Event Expenses

| Arrangements |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Facilities | $ | 250.00 |  |  |  |  |  |
| Food (includes food for workers during planning) | 2,550.00 |  |  |  |  |  |
| Total |  |  |  |  |  | $ 2,800.00 |  |
| Hospitality |  |  |  |  |  |  |  |
| Hospitality (Reception) | $ | 600.00 |  |  |  |  |  |
| Packets (printed bags, tissues, lotion, novelty items) | 1,750.00 |  |  |  |  |  |
| Photo expense (photographing conference/scrapbook) |  | 100.00 |  |  |  |  |  |
| Name tags |  | 200.00 |  |  |  |  |  |
| Miscellaneous expense |  | 150.00 |  |  |  |  |  |
| Total |  |  |  |  |  | $ 2,800.00 |  |
| Program |  |  |  |  |  |  |  |
| Honorarium (instrumentalists, soloists) | $ | 800.00 |  |  |  |  |  |
| Honorarium (speakers, leaders) | 3,000.00 |  |  |  |  |  |
| Transportation and lodging for guest leaders | 1,900.00 |  |  |  |  |  |
| Total |  |  |  |  |  | $ 5,700.00 |  |
| Public Relations |  |  |  |  |  |  |  |
| Newspaper advertisement | $ | 400.00 |  |  |  |  |  |
| Radio advertisement |  | 400.00 |  |  |  |  |  |
| Statewide mail out (postage) |  | 500.00 |  |  |  |  |  |
| Printed materials (brochure & program) |  | 800.00 |  |  |  |  |  |
| Postage (newsletters, registration information) |  | 200.00 |  |  |  |  |  |
| Miscellaneous publicity |  | 200.00 |  |  |  |  |  |
| Total |  |  |  |  |  | $ 2,500.00 |  |
| Decorations |  |  |  |  |  |  |  |
| General decorations | $ 1,200.00 |  |  |  |
| Sanctuary decorations |  | 250.00 |  |  |  |
| Displays and bulletin boards |  | 150.00 |  |  |  |
| Miscellaneous decorating expense |  | 150.00 |  |  |  |
| Total |  |  |  |  |  | $ 1,750.00 |  |
| Childcare | $ 1,000.00 |  |  |  |
| Total |  |  |  |  |  | $ 1,000.00 |  |
| Miscellaneous |  |  |  |  |  |  |  |
| Receptionist during event | $ | 150.00 |  |  |  |
| Maintenance/moving during event |  | 300.00 |  |  |  |
| Total |  |  |  |  |  | $ 450.00 |  |
| TOTAL EXPENSES | $17,000.00 |

Event Income

| 750 attendees @ $20.00 | $15,000.00 |
| --- | --- |
| 50 attendees at no expense (speakers, music, scholarships, no shows) |  |
| Ministry Budget Donation | 2,000.00 |
| TOTAL INCOME | $17,000.00 |

- 19 -

Printing Services Worksheet

(Submission Timeline)

|  | TYPE OF JOB |  | PRODUCTION/PRINTING TIME |
| --- | --- | --- | --- |
| Ad - b&w |  | ( | ) | Days |
| Ad - color |  | ( | ) | Days |
| Ad - insert |  | ( | ) | Days |
| Ad Slick |  | ( | ) | Days |
| Brochure - 3 or 4 | panel foldout | ( | ) | Days |
| Brochure - multi-panel foldout | ( | ) | Days |
| Brochure - single fold | ( | ) | Days |
| Displays/Posters |  | ( | ) | Days |
| Flyer/Announcement/Invitation | ( | ) | Days |
| Flyer - 2 sided |  | ( | ) | Days |
| Letter - ( | pages) | ( | ) | Days |
| Notebook - attendee | ( | ) | Days |
| Postcard - basic |  | ( | ) | Days |
| Postcard - customized | ( | ) | Days |
| Press Release |  | ( | ) | Days |
| Signs |  | ( | ) | Days |
| Tickets |  | ( | ) | Days |

A copy of this worksheet needs to be submitted to the Finance Office so that when an invoice from the vendor is received she will have an idea of expenses and what is being charged.

CopyRite Printing (624-1251) does the majority of FBC’s printing but any printer can be used.

- 20 -

FBC Audio-Visual Work Order Request

Section A:  Information on Requested Work

Date Requested: ____________________	Requested by: ________________________________________

Event Chairperson: ____________________________________________ Phone No.: _________________

Date(s) of Event: _________________________________	Time(s): ________________________________

Type of Event: ____________________________________________________________________________

Rooms to be Used:	________________________________________________________________________

Is the Event to be Recorded? __________ If so, what media is desired? ______________________________

Note: A meeting with the Minister of Music or Technical Director will be required at least six months prior to the event to review the scope of event needs.

List Separately the Equipment Needed:

Other Needs/Comments:

(Please attach any other pertinent information)

Section B:  Audio-Visual Department Use Only

Date Received: ____________________________________	By: __________________________________

Assigned To: _____________________________________________________________________________

Account Number to Charge: _________________________________________________________________

Comments: ______________________________________________________________________________

- 21 -

FBC Sound & Lighting Work Order Request

Section A:  Information on Requested Work

Date Requested: ____________________	Requested by: ________________________________________

Event Chairperson: ____________________________________________ Phone No.: _________________

Date(s) of Event: _________________________________	Time(s): ________________________________

Type of Event: ____________________________________________________________________________

Rooms to be Used:	________________________________________________________________________

Is the Event to be Recorded? ___________	If so, what media is desired? ____________________________

Note: A meeting with the Minister of Music or Technical Director will be required at least six months prior to the event to review the scope of event needs (including types of microphones required, boom-stands required, etc.).

Sound Needed:

(include number of microphones and stands needed; Include if portable sound systems & speakers required)

Lighting Needed:

(include spotlights, if needed)

Other Needs/Comments:

(Please attach any other pertinent information)

Section B:  Sound & Lighting Department Use Only

Date Received: ____________________________________	By: __________________________________

Assigned To: _____________________________________________________________________________

Account Number to Charge: _________________________________________________________________

Comments: ______________________________________________________________________________

- 22 -

Response Card Sample

Begin immediately to plan for your next event. Compile information from the Response Card and Event Evaluation. Follow-up on decisions made at the event. Use the other information to begin praying over your next special event. Ask God to direct you and the other leaders in your church so you can continue to meet needs through your events.

Response Card

I would like to be on the mailing list for your church.

I would like to be on the mailing list for your ministry or event. I would like to know more about what this church can do for me. I have some spiritual questions. Please have someone call me. I would like to talk to someone about knowing Christ personally. Today, for the first time, I asked Jesus to be my Lord and Savior. Today, I recommitted my life to Christ.

Today, I committed to a special ministry of _____________________ for Christ.

Comments about this event: ____________________________________________

___________________________________________________________________

___________________________________________________________________

Prayer Request: _____________________________________________________

___________________________________________________________________

Name: _____________________________________________________________

Address: ___________________________________________________________

City/State/Zip: _______________________________________________________

Phone Number: ______________________________________________________

E-mail: _____________________________________________________________

- 23 -

FBC Event Evaluation

Event ______________________________________________	Date ______________

Please circle the number which best represents your opinion and complete the statements with your thoughts. When you have completed this evaluation, please place it in the designated area. Thank you for your assistance.

| Questions | Poor |  |  |  | Excellent |
| --- | --- | --- | --- | --- | --- |
| Overall rating of this event | 1 | 2 | 3 | 4 | 5 |
| Materials distributed | 1 | 2 | 3 | 4 | 5 |
| How well this event met your objectives | 1 | 2 | 3 | 4 | 5 |
| Facilities environment | 1 | 2 | 3 | 4 | 5 |
| Other: _______________________________ | 1 | 2 | 3 | 4 | 5 |
| Other: _______________________________ | 1 | 2 | 3 | 4 | 5 |

How did you hear about this event?

__ Brochure __ Newsletter

__ Radio

__ Website

__ Friend

__ E-mail

__ Event Leader ___ Newspaper __ Other ___________________________

Would you recommend this event to other people?

___ Yes

___ No

The best thing about this event was _________________________________________________________

______________________________________________________________________________________

If I could change one thing about this event, I would ____________________________________________

______________________________________________________________________________________

What topics would be most beneficial for the next event? ________________________________________

______________________________________________________________________________________

Please make any additional comments ______________________________________________________

______________________________________________________________________________________

Optional Information:

Name: _______________________________________________________________________________

Address: _____________________________________________________________________________

Phone: ____________________ E-mail: ___________________________________________________

- 24 -

FBC Event Debriefing Sheet

- The objectives that were met and how:

*

*

*

*

- The target audience that was reached (who came):

- What went well?

- What was not as good as we had hoped?

- What do we repeat/not repeat?

- What needs to be done now to maximize our gain?

- Is this event worth repeating (effort/resources spent vs. outcome)?

- If the event is to be repeated, when will it be scheduled for next year?

  - 25 -